## sheet one
ID | Task ID | Name | Type | Colour | Duration | Rollup | Predecessor | Successor | Status | Ready | Index | Department | Workarea | Planner | Manager | Rm.Dur | Sugg.RD | Act.Dur | Rm.Dur.Held | Rm.Dur.Held Till | Planned Start | Planned End | Sugg.Start | Sugg.End | Act Start | Act End | Manual Start | Manual End | Suggestion | Planned Resource | Planned Resource Roll-Up | Proj Resource | Proj Resource Roll-Up | Material Rule | Planned Material Roll-Up | Actual Material Roll-Up | Projected Material Roll-Up | Earned Value Rule | Planned Earned Value | Actual Earned Value | Projected Earned Value | Cost Rule | Budgeted Cost | Tot.Planned Cost Roll-Up | Tot.Act Cost Roll-Up | Tot.Proj Cost Roll-Up | Mat.Planned Cost Roll-Up | Mat.Actual Cost Roll-Up | Mat.Proj Cost Roll-Up | Exc.Planned Cost Roll-Up | Exc.Act Cost Roll-Up | Exc.Proj Cost Roll-Up | Revenue Rule | Budgeted Revenue | Planned Revenue Roll-Up | Actual Revenue Roll-Up | Projected Revenue Roll-Up | Contractor | Contractor Roll-Up | Planned Material | Actual Material | Projected Material | Planned Cost | Actual Cost | Projected Cost | Planned Material Cost | Actual Material Cost | Projected Material Cost | Planned Execution Cost | Actual Execution Cost | Projected Execution Cost | Planned Revenue | Actual Revenue | Score Planned | Score Executed | Score Pending | Score Weight | Score Percent | Volume Planned | Volume Executed | Volume Pending
1 | 77 | Category 2 - COATER - Engg | TASK |  | 5d | 5d |  | 2 | CO | YES | [7 empty] | 2h |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM |  |  | 11-Sep-25 03:51 PM | 11-Sep-25 04:51 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
1.1 |  | COATER ASSY. | Subtask |  | 5d | 5d |  |  | CO | YES | [7 empty] | 2h |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM |  |  | 11-Sep-25 03:51 PM | 11-Sep-25 04:51 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
1.1.1 |  | Completion | step
1.1.1.1 |  | VERTICAL CHEMICAL COATER ASSY. | date |  | 5d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM |  |  | 11-Sep-25 03:51 PM | 11-Sep-25 04:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2 | 78 | Category 2 - COATER - Ordering & Manufacturing | TASK |  | 120d | 120d | 1 | 60 | IP | YES | 003-025 |  |  |  |  | 1d |  | 176d5h |  |  | 17-Aug-25 08:00 AM | 26-Dec-25 02:00 PM |  | 24-Mar-26 02:25 AM | 11-Sep-25 03:53 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
2.1 |  | VERTICAL CHEMICAL COATER ASSY. | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 154d9h |  |  | 17-Aug-25 08:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Sep-25 03:54 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
2.1.1 |  | Release of PO | step |  |  |  |  | 2.1.2
2.1.1.1 |  | FIXED FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.2 |  | FIXED FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.3 |  | FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.4 |  | FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.5 |  | BEARING HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.6 |  | SLIDING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.7 |  | BEARING HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.8 |  | TOP BRG. COVER (APPLICATOR ROLL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.9 |  | TOP BEARING COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.10 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.11 |  | FOUNDATION WELD PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 17-Oct-25 10:40 AM | 17-Oct-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.12 |  | FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.13 |  | HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.14 |  | LINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:44 PM | 11-Nov-25 08:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.15 |  | ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.16 |  | RACK PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.17 |  | RACK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.18 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.19 |  | SLIDDING BLOCK-HGH45CA | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d3h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 12-Nov-25 01:32 PM | 14-Nov-25 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.20 |  | RACK PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d3h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 12-Nov-25 01:32 PM | 14-Nov-25 04:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.21 |  | PINION | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.22 |  | HYD MOTOR-250 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 51d5h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 14-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.23 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d3h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 12-Nov-25 01:32 PM | 14-Nov-25 04:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.24 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.25 |  | CONNECTING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.26 |  | GEAR BOX-15-K.W, M0922.6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.27 |  | GEAR BOX-22 K.W, M09225.0 RATIO 5.07 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 17-Oct-25 10:25 AM | 17-Oct-25 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.28 |  | 15 K.W, MOTOR- M2BAX160MLB4 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 17-Oct-25 10:25 AM | 17-Oct-25 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.29 |  | 22 K.W, MOTOR- M2BAX180MLB4 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 27-Oct-25 09:59 AM | 27-Oct-25 10:59 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.30 |  | TOP BEARING COVER PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 27-Oct-25 09:59 AM | 27-Oct-25 10:59 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.31 |  | HEX BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.32 |  | HUB | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.33 |  | BRG STOPPER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.34 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.35 |  | PLATE 150x70x10 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.36 |  | STOPPER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 17-Oct-25 10:45 AM | 17-Oct-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.37 |  | STOPPER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 17-Oct-25 10:45 AM | 17-Oct-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.38 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.39 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.40 |  | WHEEL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.41 |  | ISA 50 X 50 X 600 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.42 |  | ISA 50 X 50 X 600 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 17-Oct-25 10:45 AM | 17-Oct-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.43 |  | NYLON PAD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 17-Oct-25 10:45 AM | 17-Oct-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.44 |  | ISA 50x50X5.00 LONG 75.00 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:06 PM | 11-Nov-25 08:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.45 |  | COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 17-Oct-25 10:45 AM | 17-Oct-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.46 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.47 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.48 |  | FLANGE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.49 |  | SPRING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 147d3h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.1.50 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d3h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 12-Nov-25 01:32 PM | 14-Nov-25 04:17 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.51 |  | LOAD CELL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d6h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 17-Nov-25 09:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.52 |  | PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d3h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 12-Nov-25 01:32 PM | 14-Nov-25 04:17 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.53 |  | HUB | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.54 |  | PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.55 |  | LOVE JOY COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 51d4h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 14-Nov-25 04:17 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.56 |  | SLIDE-HGH45CA,L-780 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d3h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 12-Nov-25 01:32 PM | 14-Nov-25 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.57 |  | SLIDE-HGH45CA,L-885 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d3h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 12-Nov-25 01:32 PM | 14-Nov-25 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.58 |  | SLIDE-HGH45CA,L-990 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 27-Oct-25 09:56 AM | 27-Oct-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.59 |  | HUSKY PUMP 1" AODD MODEL NO.-P230, MAKE- WILDEN. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 27-Oct-25 09:56 AM | 27-Oct-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.60 |  | APPLICATOR ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.61 |  | PICK UP ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.62 |  | FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.63 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.64 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.65 |  | ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 11-Nov-25 08:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.66 |  | CONNECTING ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.67 |  | WORM SCREW JACK-2.5 TONS(STK-250MM) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.68 |  | FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.69 |  | FLANGE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.70 |  | WHEEL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 06-Oct-25 05:45 PM | 06-Oct-25 06:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.71 |  | WHEEL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 17-Oct-25 10:25 AM | 11-Nov-25 07:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.72 |  | HYD.CYL. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d15h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 17-Oct-25 10:25 AM | 14-Nov-25 04:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.73 |  | WORM SCREW JACK-2 TON | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.74 |  | NYLON COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 08-Oct-25 10:01 AM | 08-Oct-25 11:01 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.75 |  | DRIVE SIDE FRAME ASSLY | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 51d4h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 14-Nov-25 04:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.76 |  | CARDAN SHAFT KI FLEX-150 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.77 |  | SUPPORT ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.78 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.79 |  | SS TANK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.80 |  | TRAY SUPPORT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d3h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 12-Nov-25 01:32 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.81 |  | TRAY SUPPORT 02 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.82 |  | PULL CORD SWITCH ZQ 700-11 WITH ACCESSORIES,MAKE SCHMERSAL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.83 |  | L- PLATE-01 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 30-Oct-25 10:29 AM | 30-Oct-25 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.84 |  | L- PLATE-02 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 55d12h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 12-Nov-25 01:32 PM | 12-Jan-26 04:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.85 |  | DRIVE BOTTOM FRAME ASSY. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 19-Sep-25 03:04 PM | 19-Sep-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.86 |  | TRAY | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 12-Nov-25 01:32 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.1.87 |  | BKT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 12h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 12-Nov-25 12:17 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.88 |  | PIPE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d15h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.1.89 |  | BELLOW COVER 03 (L-200) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d15h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.1.90 |  | BELLOW COVER 04 ( L-150 ) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d15h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.1.91 |  | BELLOW COVER-07 ( L-300 ) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d15h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.1.92 |  | BELLOW COVER 03 (L-190 ) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d15h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.1.93 |  | BELLOW COVER -10 (L-150 ) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d15h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.1.94 |  | BELLOW COVER-05 (L-400) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d15h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.1.95 |  | BELLOW COVER-09 ( L-150 ) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d15h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.1.96 |  | BELLOW COVER-05 (L-490) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d15h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.1.97 |  | 6210_Z-DEEP GROVE BALL BEARING-ID50XOD90X20 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d15h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.98 |  | GRACO HEAVY DUTY AGITATOR | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d15h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.99 |  | GN 300.4-108-M12-SW | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d15h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.100 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.101 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.102 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.103 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.104 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.105 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.106 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.107 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.108 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.109 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.110 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.111 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.112 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.113 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 110 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.114 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.115 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.116 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.117 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.118 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-W-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.119 |  | Hexagon Nut Style 1 IS 1364-Part3 - M8-W-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.120 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.121 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.122 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.123 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.124 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.125 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.126 |  | Socket Head Cap Screw IS 2269 - M10 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.127 |  | Socket Head Cap Screw IS 2269 - M10 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.128 |  | Socket Head Cap Screw IS 2269 - M10 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.129 |  | Socket Head Cap Screw IS 2269 - M10 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.130 |  | Socket Head Cap Screw IS 2269 - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.131 |  | Socket Head Cap Screw IS 2269 - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.132 |  | Socket Head Cap Screw IS 2269 - M12 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.133 |  | Socket Head Cap Screw IS 2269 - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.134 |  | Socket Head Cap Screw IS 2269 - M6 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.135 |  | Retaining Ring (Normal) External IS 3075(Part1) - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.136 |  | Spring Lock Washer IS 6735 - 10 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.137 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.138 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.139 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.140 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.141 |  | Spring Lock Washer IS 6735 - 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.142 |  | Socket Countersunk Head Cap Screw IS 6761 - M8 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 40d5h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 13-Nov-25 12:39 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.143 |  | Clevis Pin IS 6862 - 20 x 100-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 40d5h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 13-Nov-25 12:39 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.1.144 |  | REXNORD -C-B224M75H | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d6h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 13-Nov-25 12:39 PM | 17-Nov-25 09:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2 |  | Ready for Assy | step |  |  |  | 2.1.1
2.1.2.1 |  | FIXED FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 56d13h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 31-Dec-25 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.2 |  | FIXED FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 56d13h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 31-Dec-25 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.3 |  | FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 56d13h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 31-Dec-25 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.4 |  | FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 56d13h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 31-Dec-25 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.5 |  | BEARING HOUSING | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 56d13h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 31-Dec-25 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.6 |  | SLIDING PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 56d13h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 31-Dec-25 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.7 |  | BEARING HOUSING | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 56d13h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 31-Dec-25 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.8 |  | TOP BRG. COVER (APPLICATOR ROLL) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 56d13h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 31-Dec-25 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.9 |  | TOP BEARING COVER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 56d13h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 31-Dec-25 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.10 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:44 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.11 |  | FOUNDATION WELD PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.12 |  | FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 56d13h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 31-Dec-25 03:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.13 |  | HOUSING | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 56d13h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 31-Dec-25 03:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.14 |  | LINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.15 |  | ROD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.16 |  | RACK PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.17 |  | RACK | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.18 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.19 |  | SLIDDING BLOCK-HGH45CA | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Dec-25 09:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.20 |  | RACK PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d4h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.21 |  | PINION | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.22 |  | HYD MOTOR-250 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d15h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:44 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.23 |  | PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d4h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.24 |  | PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.25 |  | CONNECTING PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.26 |  | GEAR BOX-15-K.W, M0922.6 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.27 |  | GEAR BOX-22 K.W, M09225.0 RATIO 5.07 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:25 AM | 27-Dec-25 09:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.28 |  | 15 K.W, MOTOR- M2BAX160MLB4 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.29 |  | 22 K.W, MOTOR- M2BAX180MLB4 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.30 |  | TOP BEARING COVER PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d4h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.31 |  | HEX BLOCK | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.32 |  | HUB | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.33 |  | BRG STOPPER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.34 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.35 |  | PLATE 150x70x10 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.36 |  | STOPPER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:44 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.37 |  | STOPPER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:44 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.38 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.39 |  | PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.40 |  | WHEEL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.41 |  | ISA 50 X 50 X 600 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.42 |  | ISA 50 X 50 X 600 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:44 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.43 |  | NYLON PAD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d15h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:44 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.44 |  | ISA 50x50X5.00 LONG 75.00 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:06 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.45 |  | COUPLING | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:44 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.46 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.47 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.48 |  | FLANGE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:44 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.49 |  | SPRING | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 121d14h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.50 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d4h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.51 |  | LOAD CELL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 121d14h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.52 |  | PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d4h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.53 |  | HUB | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.54 |  | PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.55 |  | LOVE JOY COUPLING | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.56 |  | SLIDE-HGH45CA,L-780 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Dec-25 09:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.57 |  | SLIDE-HGH45CA,L-885 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Dec-25 09:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.58 |  | SLIDE-HGH45CA,L-990 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 56d2h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 27-Oct-25 09:56 AM | 27-Dec-25 09:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.59 |  | HUSKY PUMP 1" AODD MODEL NO.-P230, MAKE- WILDEN. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 113d |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 27-Oct-25 09:56 AM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.60 |  | APPLICATOR ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d2h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 27-Dec-25 09:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.61 |  | PICK UP ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 79d8h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 12-Jan-26 06:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.62 |  | FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 79d6h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 12-Jan-26 04:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.63 |  | BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.64 |  | BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.65 |  | ROD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.66 |  | CONNECTING ROD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d2h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.67 |  | WORM SCREW JACK-2.5 TONS(STK-250MM) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 121d14h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.68 |  | FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 79d6h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 12-Jan-26 04:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.69 |  | FLANGE ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.70 |  | WHEEL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d4h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.71 |  | WHEEL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:25 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.72 |  | HYD.CYL. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 79d6h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:25 AM | 12-Jan-26 04:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.73 |  | WORM SCREW JACK-2 TON | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 110d |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.74 |  | NYLON COUPLING | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Dec-25 09:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.75 |  | DRIVE SIDE FRAME ASSLY | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 121d14h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.76 |  | CARDAN SHAFT KI FLEX-150 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 121d14h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.77 |  | SUPPORT ARM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d2h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.78 |  | TIE ROD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.79 |  | SS TANK | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 121d14h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.80 |  | TRAY SUPPORT | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d4h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.81 |  | TRAY SUPPORT 02 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d2h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.82 |  | PULL CORD SWITCH ZQ 700-11 WITH ACCESSORIES,MAKE SCHMERSAL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 110d |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.83 |  | L- PLATE-01 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 67d10h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 30-Oct-25 10:29 AM | 12-Jan-26 04:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.84 |  | L- PLATE-02 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 55d12h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 12-Jan-26 04:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.85 |  | DRIVE BOTTOM FRAME ASSY. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 121d14h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 17-Oct-25 10:40 AM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.86 |  | TRAY | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 98d3h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.87 |  | BKT | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d6h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:17 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.88 |  | PIPE | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 98d3h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.89 |  | BELLOW COVER 03 (L-200) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 98d3h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.90 |  | BELLOW COVER 04 ( L-150 ) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 98d3h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.91 |  | BELLOW COVER-07 ( L-300 ) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 98d3h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.92 |  | BELLOW COVER 03 (L-190 ) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 98d3h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.93 |  | BELLOW COVER -10 (L-150 ) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 98d3h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.94 |  | BELLOW COVER-05 (L-400) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 98d3h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.95 |  | BELLOW COVER-09 ( L-150 ) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 98d3h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.96 |  | BELLOW COVER-05 (L-490) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 98d3h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.97 |  | 6210_Z-DEEP GROVE BALL BEARING-ID50XOD90X20 THK. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 55d12h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:32 PM | 12-Jan-26 04:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.98 |  | GRACO HEAVY DUTY AGITATOR | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d15h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.99 |  | GN 300.4-108-M12-SW | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d15h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Feb-26 06:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
2.1.2.100 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 35 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.101 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.102 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.103 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 70 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.104 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 25 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.105 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.106 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.107 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.108 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.109 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 100 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.110 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.111 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 65 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.112 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 80 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.113 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 110 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.114 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.115 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 65 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.116 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 55 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.117 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.118 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-W-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.119 |  | Hexagon Nut Style 1 IS 1364-Part3 - M8-W-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.120 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.121 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.122 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.123 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.124 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.125 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.126 |  | Socket Head Cap Screw IS 2269 - M10 x 25 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.127 |  | Socket Head Cap Screw IS 2269 - M10 x 55 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.128 |  | Socket Head Cap Screw IS 2269 - M10 x 70 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.129 |  | Socket Head Cap Screw IS 2269 - M10 x 90 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.130 |  | Socket Head Cap Screw IS 2269 - M12 x 40 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.131 |  | Socket Head Cap Screw IS 2269 - M12 x 45 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.132 |  | Socket Head Cap Screw IS 2269 - M12 x 80 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.133 |  | Socket Head Cap Screw IS 2269 - M16 x 45 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.134 |  | Socket Head Cap Screw IS 2269 - M6 x 40 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.135 |  | Retaining Ring (Normal) External IS 3075(Part1) - 12 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.136 |  | Spring Lock Washer IS 6735 - 10 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.137 |  | Spring Lock Washer IS 6735 - 12 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.138 |  | Spring Lock Washer IS 6735 - 16 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.139 |  | Spring Lock Washer IS 6735 - 20 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.140 |  | Spring Lock Washer IS 6735 - 24 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.141 |  | Spring Lock Washer IS 6735 - 30 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 41d17h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 07:12 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.142 |  | Socket Countersunk Head Cap Screw IS 6761 - M8 x 25 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 40d5h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 13-Nov-25 12:39 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.143 |  | Clevis Pin IS 6862 - 20 x 100-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 40d5h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 13-Nov-25 12:39 PM | 27-Dec-25 09:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
2.1.2.144 |  | REXNORD -C-B224M75H | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 3d6h |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM |  |  | 13-Nov-25 12:39 PM | 17-Nov-25 09:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3 | 19 | Category 1 -STEERING ROLL ASSY. - Ordering & Manufacturing | TASK |  | 60d | 60d | 16 | 61 | IP | YES | 006-027 |  |  |  |  | 1d |  | 152d15h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 24-Mar-26 02:25 AM | 07-Oct-25 02:11 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
3.1 |  | SINGLE STEERING ROLL ASSY. #1 (2 qty) | Subtask |  | 60d | 60d |  |  | CO | YES | [7 empty] | 129d16h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  |  | 07-Oct-25 02:12 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
3.1.1 |  | Release of PO | step |  |  |  |  | 3.1.2
3.1.1.1 |  | STEERING ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:39 PM | 03-Nov-25 01:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.2 |  | MOVING FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:39 PM | 03-Nov-25 01:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.3 |  | FIX FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:39 PM | 03-Nov-25 01:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.4 |  | HOLDING BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.5 |  | CYL. BRACKET- 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.6 |  | CYL. BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.7 |  | HYD. CYL. BORE-Ø80,ROD- Ø45,STK-200MM,RC | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 02:25 PM | 07-Oct-25 03:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.8 |  | PEDSTAL PAD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.9 |  | HOLDING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.10 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.11 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.12 |  | HUB | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.13 |  | ROTATING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.14 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.15 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.16 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.17 |  | O RING- OD- 5, ID- 110mm, LENGTH- 362mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:43 PM | 12-Dec-25 12:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.18 |  | STUD TYPE CAM ROLL BEARING DIA-80,WIDTH- 35,MCFD-80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:43 PM | 12-Nov-25 01:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.19 |  | BEARING HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.20 |  | RETAINER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.21 |  | RETAINER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.22 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.23 |  | END COVER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.24 |  | END COVER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 04:55 PM | 29-Oct-25 05:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.25 |  | DOWEL PIN-Ø10X20.0 MM LONG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:57 PM | 03-Nov-25 01:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.26 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:57 PM | 03-Nov-25 01:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.27 |  | 110X130X10_OIL SEAL_AIA1100831 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 11:20 AM | 03-Nov-25 12:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.28 |  | BEARING,THRUST BALL,51314,SKF (THRUST BALL BEARING SR 70IDx125ODx40THK) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:43 PM | 12-Nov-25 01:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.29 |  | BEARING,ANGULAR CONTACT BALL,7212,SKF(ANGULER CONTACT BALL BEARING S 60IDx95ODx18THK) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:43 PM | 12-Nov-25 01:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.30 |  | 22220_E-SPHERICAL ROLLER BEARING- ID100XOD180X46 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:43 PM | 12-Nov-25 01:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.31 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.32 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.33 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.34 |  | Socket Head Cap Screw IS 2269 - M20 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.35 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.36 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.37 |  | Spring Lock Washer IS 3063 - 8- A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.39 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.40 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.42 |  | Retaining Ring (Normal) External IS 3075(Part1) - 42 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.43 |  | Hexagon Nut Style 1 IS 1364- Part3 - M30-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.44 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.45 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.47 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.48 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.52 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.53 |  | Socket Head Cap Screw IS 2269 - M16 x 110 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.1.54 |  | Hexagon nut IS 1363-Part2 - M12-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:56 PM | 03-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2 |  | Ready for Assy | step |  |  |  | 3.1.1
3.1.2.1 |  | STEERING ROLL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 44d14h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.2 |  | MOVING FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 44d14h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.3 |  | FIX FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 44d14h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.4 |  | HOLDING BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.5 |  | CYL. BRACKET- 2 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.6 |  | CYL. BRACKET | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.7 |  | HYD. CYL. BORE-Ø80,ROD- Ø45,STK-200MM,RC | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 44d14h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.8 |  | PEDSTAL PAD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.9 |  | HOLDING PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.10 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.11 |  | PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.12 |  | HUB | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.13 |  | ROTATING PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.14 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.15 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.16 |  | RETAINER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.17 |  | O RING- OD- 5, ID- 110mm, LENGTH- 362mm | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:43 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.18 |  | STUD TYPE CAM ROLL BEARING DIA-80,WIDTH- 35,MCFD-80 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:43 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.19 |  | BEARING HOUSING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.20 |  | RETAINER-RH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.21 |  | RETAINER-LH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.22 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.23 |  | END COVER-RH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.24 |  | END COVER-LH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 04:55 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.25 |  | DOWEL PIN-Ø10X20.0 MM LONG | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d8h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 12-Nov-25 12:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.26 |  | GREASE NIPPLE 1/8" BSP | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d8h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 12-Nov-25 12:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.27 |  | 110X130X10_OIL SEAL_AIA1100831 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 44d14h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.28 |  | BEARING,THRUST BALL,51314,SKF (THRUST BALL BEARING SR 70IDx125ODx40THK) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:43 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.29 |  | BEARING,ANGULAR CONTACT BALL,7212,SKF(ANGULER CONTACT BALL BEARING S 60IDx95ODx18THK) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:43 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.30 |  | 22220_E-SPHERICAL ROLLER BEARING- ID100XOD180X46 THK. | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:43 PM | 27-Dec-25 10:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.31 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.32 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.33 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.34 |  | Socket Head Cap Screw IS 2269 - M20 x 40 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.35 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.36 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.37 |  | Spring Lock Washer IS 3063 - 8- A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.39 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.40 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.42 |  | Retaining Ring (Normal) External IS 3075(Part1) - 42 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.43 |  | Hexagon Nut Style 1 IS 1364- Part3 - M30-D-N | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.44 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.45 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.47 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.48 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.52 |  | Spring Lock Washer IS 6735 - 16 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.53 |  | Socket Head Cap Screw IS 2269 - M16 x 110 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.1.2.54 |  | Hexagon nut IS 1363-Part2 - M12-N | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 08-Nov-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2 |  | DOUBLE STEERING ROLL ASSY. @ CAG (3qty) | Subtask |  | 60d | 60d |  |  | CO | YES | [7 empty] | 134d4h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  |  | 07-Oct-25 02:12 PM | 03-Mar-26 02:33 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
3.2.1 |  | Release of PO | step |  |  |  |  | 3.2.2
3.2.1.1 |  | STEERING ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:46 PM | 03-Nov-25 01:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.2 |  | MOVING FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:46 PM | 03-Nov-25 01:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.3 |  | FIX FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:46 PM | 03-Nov-25 01:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.4 |  | HOLDING BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.5 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.6 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.7 |  | HYDRAULIC CYL. BORE DIA. 80, ROD DIA.45 STROKE 200(FRONT AND REAR EYE MTG.) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:30 AM | 08-Nov-25 10:30 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.8 |  | PEDSTAL PAD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.9 |  | BASE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.10 |  | HUB | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.11 |  | ROTATING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.12 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.13 |  | SPACER- 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.14 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.15 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.16 |  | HOLDING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.17 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.18 |  | BEARING,THRUST BALL,51314,SKF (THRUST BALL BEARING SR 70IDx125ODx40THK) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:16 PM | 12-Nov-25 01:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.19 |  | BEARING,ANGULAR CONTACT BALL,7212,SKF(ANGULER CONTACT BALL BEARING S 60IDx95ODx18THK) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:16 PM | 12-Nov-25 01:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.20 |  | 22220_E-SPHERICAL ROLLER BEARING- ID100XOD180X46 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:16 PM | 12-Nov-25 01:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.21 |  | AIA1100810-OIL SEAL- ID110XOD130X8 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 11:21 AM | 03-Nov-25 12:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.22 |  | Retaining Ring (Normal) External IS 3075(Part1) - 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:56 PM | 12-Nov-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.23 |  | O-RING n-5, I.D.-110 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:56 PM | 12-Dec-25 12:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.24 |  | STUD TYPE CAM ROLL BEARING DIA-80,WIDTH- 35,MCFD-80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:12 PM | 12-Nov-25 01:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.25 |  | Socket Head Cap Screw IS 2269 - M20 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.26 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.27 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.28 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.29 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.30 |  | Socket Head Cap Screw IS 2269 - M16 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.31 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.32 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.33 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.34 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.35 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.36 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.37 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.38 |  | Hexagon nut IS 1363-Part2 - M12-C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.40 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.41 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.43 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.44 |  | Spring Lock Washer IS 3063 - 8- A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.45 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.46 |  | Hexagon Nut Style 1 IS 1364- Part3 - M30-D-C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.47 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.48 |  | DOWEL PIN-Ø10X20.0 MM LONG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:56 PM | 29-Oct-25 06:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.49 |  | BEARING HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.50 |  | RETAINER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.51 |  | END COVER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.52 |  | RETAINER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.53 |  | END COVER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.1.54 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:40 PM | 29-Oct-25 06:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2 |  | Ready for Assy | step |  |  |  | 3.2.1
3.2.2.1 |  | STEERING ROLL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 44d14h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 27-Dec-25 10:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.2 |  | MOVING FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 44d14h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 27-Dec-25 10:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.3 |  | FIX FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 44d14h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:57 AM | 27-Dec-25 10:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.4 |  | HOLDING BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.5 |  | BRACKET | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.6 |  | BRACKET | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.7 |  | HYDRAULIC CYL. BORE DIA. 80, ROD DIA.45 STROKE 200(FRONT AND REAR EYE MTG.) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:30 AM | 16-Jan-26 02:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.8 |  | PEDSTAL PAD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.9 |  | BASE PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.10 |  | HUB | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.11 |  | ROTATING PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.12 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.13 |  | SPACER- 1 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.14 |  | RETAINER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.15 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.16 |  | HOLDING PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.17 |  | PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.18 |  | BEARING,THRUST BALL,51314,SKF (THRUST BALL BEARING SR 70IDx125ODx40THK) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:16 PM | 27-Dec-25 10:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.19 |  | BEARING,ANGULAR CONTACT BALL,7212,SKF(ANGULER CONTACT BALL BEARING S 60IDx95ODx18THK) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:16 PM | 27-Dec-25 10:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.20 |  | 22220_E-SPHERICAL ROLLER BEARING- ID100XOD180X46 THK. | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:16 PM | 27-Dec-25 10:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.21 |  | AIA1100810-OIL SEAL- ID110XOD130X8 THK. | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 59d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 16-Jan-26 02:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.22 |  | Retaining Ring (Normal) External IS 3075(Part1) - 40 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:30 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.23 |  | O-RING n-5, I.D.-110 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.24 |  | STUD TYPE CAM ROLL BEARING DIA-80,WIDTH- 35,MCFD-80 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:12 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.25 |  | Socket Head Cap Screw IS 2269 - M20 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.26 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.27 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.28 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.29 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.30 |  | Socket Head Cap Screw IS 2269 - M16 x 100 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.31 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.32 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.33 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.34 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.35 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.36 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.37 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.38 |  | Hexagon nut IS 1363-Part2 - M12-C | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.40 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.41 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.43 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.44 |  | Spring Lock Washer IS 3063 - 8- A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.45 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.46 |  | Hexagon Nut Style 1 IS 1364- Part3 - M30-D-C | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.47 |  | GREASE NIPPLE 1/8" BSP | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.48 |  | DOWEL PIN-Ø10X20.0 MM LONG | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 41d5h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:01 PM | 27-Dec-25 10:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.49 |  | BEARING HOUSING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.50 |  | RETAINER-RH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.51 |  | END COVER-RH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.52 |  | RETAINER-LH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.53 |  | END COVER-LH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.2.2.54 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 53d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:40 PM | 27-Dec-25 10:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3 |  | DOUBLE STEERING ROLL ASSY. BEFORE ENTRY ACC ASSY. | Subtask |  | 60d | 60d |  |  | CO | YES | [7 empty] | 129d16h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  |  | 07-Oct-25 02:12 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
3.3.1 |  | Release of PO | step |  |  |  |  | 3.3.2
3.3.1.1 |  | STEERING ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:34 PM | 03-Nov-25 01:34 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.2 |  | MOVING FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:43 PM | 03-Nov-25 01:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.3 |  | FIX FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 12:43 PM | 03-Nov-25 01:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.4 |  | HOLDING BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.5 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.6 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.7 |  | HYDRAULIC CYL. BORE DIA. 125, ROD DIA.70 STROKE 200(FRONT AND REAR EYE MTG.) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 02:19 PM | 07-Oct-25 03:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.8 |  | PEDSTAL PAD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.9 |  | HYD. CYL. FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.10 |  | PEDSTAL PAD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.11 |  | BEARING HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.12 |  | BASE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.13 |  | HUB | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.14 |  | ROTATING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.15 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.16 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.17 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.18 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.19 |  | HOLDING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.20 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.21 |  | HOLDING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.22 |  | O RING DIA 5.0 ,, ID 110MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:59 PM | 12-Dec-25 12:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.23 |  | RETAINER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.24 |  | RETAINER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.25 |  | END COVER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.26 |  | END COVER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.27 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Oct-25 05:57 PM | 29-Oct-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.28 |  | BEARING,THRUST BALL,51314,SKF (THRUST BALL BEARING SR 70IDx125ODx40THK) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:15 PM | 12-Nov-25 01:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.29 |  | BEARING,ANGULAR CONTACT BALL,7212,SKF(ANGULER CONTACT BALL BEARING S 60IDx95ODx18THK) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:15 PM | 12-Nov-25 01:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.30 |  | 22220_E-SPHERICAL ROLLER BEARING-ID100XOD180X46 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:15 PM | 12-Nov-25 01:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.31 |  | AIA1100810-OIL SEAL- ID110XOD130X8 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Nov-25 11:21 AM | 03-Nov-25 12:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.32 |  | Retaining Ring (Normal) External IS 3075(Part1) - 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:58 PM | 12-Nov-25 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.33 |  | STUD TYPE CAM ROLL BEARING DIA-80,WIDTH-35,MCFD-80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:13 PM | 12-Nov-25 01:13 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.34 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.35 |  | DOWEL PIN Ø10X30MM LONG. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.36 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.37 |  | Socket Head Cap Screw IS 2269 - M20 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.39 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.40 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.43 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.44 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.45 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.47 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.48 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.50 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.51 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.53 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.54 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.56 |  | Socket Head Cap Screw IS 2269 - M16 x 120 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.59 |  | Hexagon Nut Style 2 IS 1364-Part6 - M12-D-C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.1.60 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 30-Oct-25 03:28 PM | 30-Oct-25 04:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2 |  | Ready for Assy | step |  |  |  | 3.3.1
3.3.2.1 |  | STEERING ROLL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.2 |  | MOVING FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.3 |  | FIX FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.4 |  | HOLDING BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.5 |  | BRACKET | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.6 |  | BRACKET | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.7 |  | HYDRAULIC CYL. BORE DIA. 125, ROD DIA.70 STROKE 200(FRONT AND REAR EYE MTG.) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:59 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.8 |  | PEDSTAL PAD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.9 |  | HYD. CYL. FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.10 |  | PEDSTAL PAD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.11 |  | BEARING HOUSING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.12 |  | BASE PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.13 |  | HUB | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.14 |  | ROTATING PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.15 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.16 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.17 |  | RETAINER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.18 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.19 |  | HOLDING PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.20 |  | PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.21 |  | HOLDING PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.22 |  | O RING DIA 5.0 ,, ID 110MM | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:59 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.23 |  | RETAINER-RH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.24 |  | RETAINER-LH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.25 |  | END COVER-RH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.26 |  | END COVER-LH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.27 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 109d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:57 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.28 |  | BEARING,THRUST BALL,51314,SKF (THRUST BALL BEARING SR 70IDx125ODx40THK) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:15 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.29 |  | BEARING,ANGULAR CONTACT BALL,7212,SKF(ANGULER CONTACT BALL BEARING S 60IDx95ODx18THK) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:15 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.30 |  | 22220_E-SPHERICAL ROLLER BEARING-ID100XOD180X46 THK. | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:15 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.31 |  | AIA1100810-OIL SEAL- ID110XOD130X8 THK. | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:15 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.32 |  | Retaining Ring (Normal) External IS 3075(Part1) - 40 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:59 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.33 |  | STUD TYPE CAM ROLL BEARING DIA-80,WIDTH-35,MCFD-80 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:13 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
3.3.2.34 |  | GREASE NIPPLE 1/8" BSP | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.35 |  | DOWEL PIN Ø10X30MM LONG. | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.36 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-C | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.37 |  | Socket Head Cap Screw IS 2269 - M20 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.39 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.40 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.43 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.44 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.45 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.47 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.48 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.50 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.51 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.53 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.54 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.56 |  | Socket Head Cap Screw IS 2269 - M16 x 120 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.59 |  | Hexagon Nut Style 2 IS 1364-Part6 - M12-D-C | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
3.3.2.60 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 70 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:56 AM | 08-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4 | 7 | Category 1 - COIL CAR ASSY @ UNCOILER - Ordering & Manufacturing | TASK |  | 60d | 65d | 17 | 82 | IP | YES | 006-013 |  |  |  |  | 65d | 65d | 216d14h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 02-Jun-26 04:25 AM | 07-Oct-25 03:04 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
4.1 |  | COIL CAR ASSY. @ UNCOILER (2qty) | Subtask |  | 60d | 60d |  |  | CO | YES | [7 empty] | 133d4h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  |  | 07-Oct-25 03:04 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
4.1.1 |  | Release of PO | step |  |  |  |  | 4.1.2
4.1.1.1 |  | SADDLE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.2 |  | BOTTOM FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.3 |  | GUID ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.4 |  | HYD. MOTOR(OMT- 315) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.5 |  | DOUBLE ACTING HYD. CYL. BORE DIA. Ø 250, PISTON ROD DIA. Ø 175, STROKE 1200MM, WORKING PRESSURE -80 BAR, CIRCULAR FRONT FLANGE MOUNTING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 07-Oct-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.6 |  | BRG. BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.7 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.8 |  | BRG. BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.9 |  | CHAIN COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.10 |  | BRG. BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.11 |  | BRG. BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.12 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.13 |  | CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.14 |  | WHEEL SHAFT -1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.15 |  | MOTOR GEAR | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.16 |  | PINION | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.17 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.18 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.19 |  | COVER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.20 |  | COVER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.21 |  | WHEEL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.22 |  | WHEEL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.23 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.24 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.25 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.26 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.27 |  | PAD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.28 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.29 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.30 |  | WHEEL SHAFT-2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.31 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.32 |  | BEARING,SPHERICAL,22218 E ,SKF (SPHERICAL ROLLER BRG 90IDx160ODx40THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d15h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 11-Nov-25 12:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.33 |  | ACC1100801-OIL SEAL- ID110XOD130X12 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.34 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.35 |  | Socket Head Cap Screw IS 2269 - M16 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.37 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.39 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.40 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.42 |  | Plain Washer (Type A) IS 2016 - 6.6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.43 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.45 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.46 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.47 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.48 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.51 |  | Spring Lock Washer IS 3063 - 6-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.53 |  | Spring Lock Washer IS 3063 - 12-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.54 |  | Spring Lock Washer IS 3063 - 10-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.56 |  | IS 1364 HHB(Grade B) - M24 x 100 x 54- N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.57 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.58 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.59 |  | Socket Head Cap Screw IS 2269 - M10 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.60 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.61 |  | Spring Lock Washer IS 6735 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.62 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M30 x 110 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.1.63 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 07-Oct-25 03:07 PM | 14-Nov-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.1.2 |  | Ready for Assy | step |  |  |  | 4.1.1
4.1.2.1 |  | SADDLE FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.2 |  | BOTTOM FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.3 |  | GUID ROD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.4 |  | HYD. MOTOR(OMT- 315) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.5 |  | DOUBLE ACTING HYD. CYL. BORE DIA. Ø 250, PISTON ROD DIA. Ø 175, STROKE 1200MM, WORKING PRESSURE -80 BAR, CIRCULAR FRONT FLANGE MOUNTING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 133d4h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 07-Oct-25 03:08 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.6 |  | BRG. BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.7 |  | BRACKET | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.8 |  | BRG. BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.9 |  | CHAIN COVER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.10 |  | BRG. BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.11 |  | BRG. BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.12 |  | BUSH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.13 |  | CLEVIS | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.14 |  | WHEEL SHAFT -1 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.15 |  | MOTOR GEAR | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.16 |  | PINION | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.17 |  | RETAINER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.18 |  | RETAINER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.19 |  | COVER PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.20 |  | COVER PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.21 |  | WHEEL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.22 |  | WHEEL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.23 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.24 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.25 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.26 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.27 |  | PAD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.28 |  | RETAINER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.29 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.30 |  | WHEEL SHAFT-2 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.31 |  | RETAINER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.32 |  | BEARING,SPHERICAL,22218 E ,SKF (SPHERICAL ROLLER BRG 90IDx160ODx40THK. mm) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:47 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.33 |  | ACC1100801-OIL SEAL- ID110XOD130X12 THK. | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.34 |  | GREASE NIPPLE 1/8" BSP | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.35 |  | Socket Head Cap Screw IS 2269 - M16 x 90 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 35 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.37 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.39 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.40 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.42 |  | Plain Washer (Type A) IS 2016 - 6.6 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.43 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 16 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.45 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.46 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.47 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.48 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 20 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.51 |  | Spring Lock Washer IS 3063 - 6-B | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.53 |  | Spring Lock Washer IS 3063 - 12-B | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.54 |  | Spring Lock Washer IS 3063 - 10-B | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.56 |  | IS 1364 HHB(Grade B) - M24 x 100 x 54- N | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.57 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.58 |  | Spring Lock Washer IS 6735 - 24 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.59 |  | Socket Head Cap Screw IS 2269 - M10 x 35 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.60 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.61 |  | Spring Lock Washer IS 6735 - 33 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.62 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M30 x 110 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.1.2.63 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:45 PM | 02-Mar-26 03:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
4.2 |  | DRAG CHAIN ASSY. @ UNCOILER | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 50d17h | 50d17h | 167d12h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 17-May-26 01:00 PM | 14-Nov-25 04:47 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
4.2.1 |  | Release of PO | step |  |  |  |  | 4.2.2
4.2.1.1 |  | SHIM | date |  | 10d |  |  |  | IP | YES | [5 empty] | 17h |  | 19d8h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  | 23-Mar-26 09:00 PM | 02-Mar-26 04:00 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.2 |  | PLATE-230.0x170.0x12.0MM THK | date |  | 10d |  |  |  | IP | YES | [5 empty] | 17h |  | 19d8h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  | 23-Mar-26 09:00 PM | 02-Mar-26 04:00 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.3 |  | RAIL I.R.S. NO. 52. LENGTH-8975.0 MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.4 |  | HOSE PIPE 3/4",LT-90° ONE SIDE,(R2) 5500MM LONG (FOR HYD. MOTOR) | date |  | 10d |  |  |  | IP | YES | [5 empty] | 17h |  | 19d8h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  | 23-Mar-26 09:00 PM | 02-Mar-26 04:00 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.5 |  | HOSE PIPE 1",LT-90° ONE SIDE,(R2) 5500MM LONG (FOR HYD. CYLINDER) | date |  | 10d |  |  |  | IP | YES | [5 empty] | 17h |  | 19d8h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  | 23-Mar-26 09:00 PM | 02-Mar-26 04:00 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.6 |  | HOSE PIPE 1/4",LT-90° ONE SIDE,(R2) 5500MM LONG (FOR HYD. MOTOR DRAIN) | date |  | 10d |  |  |  | IP | YES | [5 empty] | 17h |  | 19d8h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  | 23-Mar-26 09:00 PM | 02-Mar-26 04:00 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.7 |  | DRAG CHAIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 09-Jan-26 12:50 PM | 09-Jan-26 01:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.8 |  | FRAME | date |  | 10d |  |  |  | IP | YES | [5 empty] | 17h |  | 19d8h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  | 23-Mar-26 09:00 PM | 02-Mar-26 04:00 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.9 |  | BRACKET | date |  | 10d |  |  |  | IP | YES | [5 empty] | 17h |  | 19d8h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  | 23-Mar-26 09:00 PM | 02-Mar-26 04:00 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.10 |  | DRAG CHAIN SUPPORT FRAME | date |  | 10d |  |  |  | IP | YES | [5 empty] | 17h |  | 19d8h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  | 23-Mar-26 09:00 PM | 02-Mar-26 04:00 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.11 |  | STOPPER | date |  | 10d |  |  |  | IP | YES | [5 empty] | 17h |  | 19d8h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  | 23-Mar-26 09:00 PM | 02-Mar-26 04:00 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.13 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.14 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.15 |  | Hexagon Flange Nut IS 15581 - M12-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.16 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.17 |  | Plain Washer (Type B) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.18 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.1.19 |  | RAIL CLAMP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2 |  | Ready for Assy | step |  |  |  | 4.2.1
4.2.2.1 |  | SHIM | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 24-Mar-26 01:00 AM | 17-May-26 01:00 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.2 |  | PLATE-230.0x170.0x12.0MM THK | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 24-Mar-26 01:00 AM | 17-May-26 01:00 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.3 |  | RAIL I.R.S. NO. 52. LENGTH-8975.0 MM | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.4 |  | HOSE PIPE 3/4",LT-90° ONE SIDE,(R2) 5500MM LONG (FOR HYD. MOTOR) | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 24-Mar-26 01:00 AM | 17-May-26 01:00 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.5 |  | HOSE PIPE 1",LT-90° ONE SIDE,(R2) 5500MM LONG (FOR HYD. CYLINDER) | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 24-Mar-26 01:00 AM | 17-May-26 01:00 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.6 |  | HOSE PIPE 1/4",LT-90° ONE SIDE,(R2) 5500MM LONG (FOR HYD. MOTOR DRAIN) | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 24-Mar-26 01:00 AM | 17-May-26 01:00 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.7 |  | DRAG CHAIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.8 |  | FRAME | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 24-Mar-26 01:00 AM | 17-May-26 01:00 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.9 |  | BRACKET | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 24-Mar-26 01:00 AM | 17-May-26 01:00 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.10 |  | DRAG CHAIN SUPPORT FRAME | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 24-Mar-26 01:00 AM | 17-May-26 01:00 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.11 |  | STOPPER | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 24-Mar-26 01:00 AM | 17-May-26 01:00 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.13 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.14 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M12 x 50 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.15 |  | Hexagon Flange Nut IS 15581 - M12-N | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.16 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.17 |  | Plain Washer (Type B) IS 2016 - 14 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.18 |  | Spring Lock Washer IS 6735 - 12 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.2.2.19 |  | RAIL CLAMP | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:00 PM | 02-Mar-26 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.3 |  | COIL SADDLE ASSY. @ UNCOILER | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 17h | 17h | 119d13h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 23-Mar-26 09:00 PM | 12-Nov-25 03:09 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
4.3.1 |  | Release of PO | step |  |  |  |  | 4.3.2
4.3.1.1 |  | FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 03:09 PM | 12-Nov-25 04:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.3.1.2 |  | PAD 180 X 660 X 25MM THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 03:09 PM | 14-Nov-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.3.1.3 |  | SHEAR BLOCK- 15X15X80MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 03:09 PM | 14-Nov-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.3.1.4 |  | Socket Head Cap Screw IS 2269 - M10 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 03:09 PM | 14-Nov-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.3.1.5 |  | STOPPER 10X10X140 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 03:09 PM | 14-Nov-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.3.2 |  | Ready for Assy | step |  |  |  | 4.3.1
4.3.2.1 |  | FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 03:09 PM | 14-Nov-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.3.2.2 |  | PAD 180 X 660 X 25MM THK | date |  | 50d |  |  |  | IP | YES | [5 empty] | 17h |  | 119d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 23-Mar-26 09:00 PM | 12-Nov-25 03:09 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.3.2.3 |  | SHEAR BLOCK- 15X15X80MM | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 03:09 PM | 14-Nov-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.3.2.4 |  | Socket Head Cap Screw IS 2269 - M10 x 35 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 03:09 PM | 14-Nov-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.3.2.5 |  | STOPPER 10X10X140 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 03:09 PM | 14-Nov-25 04:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
4.4 |  | PIT COVER 1 @ UNCOILER | Subtask |  | 65d | 65d |  |  | IP | YES | [5 empty] | 65d | 65d | 83d13h |  |  | 22-Oct-25 03:00 AM | 01-Jan-26 05:00 AM |  | 02-Jun-26 04:25 AM | 02-Mar-26 12:39 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
4.4.1 |  | Release of PO | step |  |  |  |  | 4.4.2
4.4.1.1 |  | SLIDING FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.2 |  | SLIDING FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.3 |  | SLIDING FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.4 |  | SLIDING FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.5 |  | FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.6 |  | BRACKET | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.7 |  | SLIDING FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.8 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 14-Mar-26 12:32 PM | 14-Mar-26 01:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.9 |  | PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 14-Mar-26 12:32 PM | 14-Mar-26 01:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.10 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 14-Mar-26 12:32 PM | 14-Mar-26 01:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.11 |  | BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 14-Mar-26 12:32 PM | 14-Mar-26 01:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.12 |  | PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 14-Mar-26 12:32 PM | 14-Mar-26 01:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.13 |  | ISMC- 100x10x, LONG- 6500mm | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.14 |  | CAM FOLLOWER KR62 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.15 |  | Hexagon nut IS 1363- Part2 - M24-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.17 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.18 |  | Spring Lock Washer IS 6735 - 10 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.20 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.22 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.23 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.24 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.25 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.26 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.1.27 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:02 PM | 02-Mar-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2 |  | Ready for Assy | step |  |  |  | 4.4.1
4.4.2.1 |  | SLIDING FRAME | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.2 |  | SLIDING FRAME | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.3 |  | SLIDING FRAME | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.4 |  | SLIDING FRAME | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.5 |  | FRAME | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.6 |  | BRACKET | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 02-Apr-26 03:25 PM | 02-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.7 |  | SLIDING FRAME | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.8 |  | SPACER | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.9 |  | PLATE | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.10 |  | SPACER | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.11 |  | BLOCK | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.12 |  | PLATE | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.13 |  | ISMC- 100x10x, LONG- 6500mm | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 02-Apr-26 03:25 PM | 02-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.14 |  | CAM FOLLOWER KR62 | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 02-Apr-26 03:25 PM | 02-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.15 |  | Hexagon nut IS 1363- Part2 - M24-N | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 70 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.17 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.18 |  | Spring Lock Washer IS 6735 - 10 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 20 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.20 |  | Spring Lock Washer IS 6735 - 16 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.22 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.23 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.24 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.25 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.26 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.4.2.27 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 01-Nov-25 04:00 PM | 01-Jan-26 05:00 AM | 23-Mar-26 02:25 AM | 21-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
4.5 |  | PIT COVER 2 @ UNCOILER | Subtask |  | 65d |  |  |  | IP | YES | [5 empty] | 65d |  | 83d13h |  |  | 22-Oct-25 03:00 AM | 01-Jan-26 05:00 AM |  | 02-Jun-26 04:25 AM | 02-Mar-26 12:39 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
5 | 11 | Category 1 - COIL CAR ASSY @ RECOILER - Ordering & Manufacturing | TASK |  | 65d | 65d | 27 | 83 | IP | NO | 006-011 |  |  |  |  | 65d | 65d | 216d14h |  |  | 16-Oct-25 12:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 04-Jun-26 04:25 AM | 07-Oct-25 03:10 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
5.1 |  | COIL CAR ASSY. @ RECOILER | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 1d |  | 152d14h |  |  | 16-Oct-25 12:00 PM | 20-Dec-25 09:00 PM |  | 26-Mar-26 02:25 AM | 07-Oct-25 03:10 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
5.1.1 |  | Release of PO | step |  |  |  |  | 5.1.2
5.1.1.1 |  | SADDLE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.2 |  | BOTTOM FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.3 |  | GUID ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.4 |  | HYD. MOTOR(OMT- 315) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.5 |  | DOUBLE ACTING HYD. CYL. BORE DIA. Ø 250, PISTON ROD DIA. Ø 175, STROKE 1200MM, WORKING PRESSURE -80 BAR, CIRCULAR FRONT FLANGE MOUNTING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 12:31 PM | 11-Nov-25 01:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.6 |  | BRG. BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.7 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.8 |  | BRG. BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.9 |  | CHAIN COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.10 |  | BRG. BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.11 |  | BRG. BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.12 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.13 |  | CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.14 |  | WHEEL SHAFT -1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.15 |  | MOTOR GEAR | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.16 |  | PINION | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.17 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.18 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.19 |  | COVER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.20 |  | COVER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.21 |  | WHEEL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.22 |  | WHEEL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.23 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.24 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.25 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.26 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.27 |  | PAD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.28 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.29 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.30 |  | WHEEL SHAFT-2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.31 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.32 |  | BEARING,SPHERICAL,22218 E ,SKF (SPHERICAL ROLLER BRG 90IDx160ODx40THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 12:31 PM | 11-Nov-25 01:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.33 |  | ACC1100801-OIL SEAL- ID110XOD130X12 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.34 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.35 |  | Socket Head Cap Screw IS 2269 - M16 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.37 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.39 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.40 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.42 |  | Plain Washer (Type A) IS 2016 - 6.6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.43 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.45 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.46 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.47 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.48 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.51 |  | Spring Lock Washer IS 3063 - 6-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.53 |  | Spring Lock Washer IS 3063 - 12-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.54 |  | Spring Lock Washer IS 3063 - 10-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.56 |  | IS 1364 HHB(Grade B) - M24 x 100 x 54- N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.57 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.58 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.59 |  | Socket Head Cap Screw IS 2269 - M10 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.60 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.61 |  | Spring Lock Washer IS 6735 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.62 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M30 x 110 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.1.63 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:42 PM | 14-Nov-25 05:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2 |  | Ready for Assy | step |  |  |  | 5.1.1
5.1.2.1 |  | SADDLE FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.2 |  | BOTTOM FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.3 |  | GUID ROD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.4 |  | HYD. MOTOR(OMT- 315) | date |  | 50d |  |  |  | IP | YES | [5 empty] | 1d |  | 117d13h |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  | 23-Mar-26 09:00 PM | 14-Nov-25 04:42 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.5 |  | DOUBLE ACTING HYD. CYL. BORE DIA. Ø 250, PISTON ROD DIA. Ø 175, STROKE 1200MM, WORKING PRESSURE -80 BAR, CIRCULAR FRONT FLANGE MOUNTING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:48 PM | 03-Mar-26 11:28 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.6 |  | BRG. BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.7 |  | BRACKET | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.8 |  | BRG. BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.9 |  | CHAIN COVER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.10 |  | BRG. BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.11 |  | BRG. BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.12 |  | BUSH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.13 |  | CLEVIS | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.14 |  | WHEEL SHAFT -1 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.15 |  | MOTOR GEAR | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.16 |  | PINION | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.17 |  | RETAINER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.18 |  | RETAINER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.19 |  | COVER PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.20 |  | COVER PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.21 |  | WHEEL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.22 |  | WHEEL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.23 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.24 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.25 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.26 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.27 |  | PAD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.28 |  | RETAINER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.29 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.30 |  | WHEEL SHAFT-2 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.31 |  | RETAINER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.32 |  | BEARING,SPHERICAL,22218 E ,SKF (SPHERICAL ROLLER BRG 90IDx160ODx40THK. mm) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:48 PM | 03-Mar-26 11:29 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.33 |  | ACC1100801-OIL SEAL- ID110XOD130X12 THK. | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.34 |  | GREASE NIPPLE 1/8" BSP | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.35 |  | Socket Head Cap Screw IS 2269 - M16 x 90 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 35 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.37 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.39 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.40 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.42 |  | Plain Washer (Type A) IS 2016 - 6.6 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.43 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 16 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.45 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.46 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.47 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.48 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 20 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.51 |  | Spring Lock Washer IS 3063 - 6-B | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.53 |  | Spring Lock Washer IS 3063 - 12-B | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.54 |  | Spring Lock Washer IS 3063 - 10-B | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.56 |  | IS 1364 HHB(Grade B) - M24 x 100 x 54- N | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.57 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.58 |  | Spring Lock Washer IS 6735 - 24 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.59 |  | Socket Head Cap Screw IS 2269 - M10 x 35 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.60 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.61 |  | Spring Lock Washer IS 6735 - 33 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.62 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M30 x 110 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.1.2.63 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 99d |  |  | 27-Oct-25 04:00 PM | 20-Dec-25 09:00 PM |  |  | 14-Nov-25 04:42 PM | 03-Mar-26 11:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2 |  | DRAG CHAIN ASSY. @ RECOILER | Subtask |  | 65d | 65d |  |  | IP | YES | [5 empty] | 65d | 65d | 130d15h |  |  | 16-Oct-25 12:00 PM | 26-Dec-25 02:00 PM |  | 04-Jun-26 04:25 AM | 09-Jan-26 12:52 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
5.2.1 |  | Release of PO | step |  |  |  |  | 5.2.2
5.2.1.1 |  | SHIM | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.2 |  | PLATE-230.0x170.0x12.0MM THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.3 |  | RAIL I.R.S. NO. 52. LENGTH- 8975.0 MM | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.4 |  | HOSE PIPE 3/4",LT-90° ONE SIDE,(R2) 5500MM LONG (FOR HYD. MOTOR) | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.5 |  | HOSE PIPE 1",LT-90° ONE SIDE,(R2) 5500MM LONG (FOR HYD. CYLINDER) | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.6 |  | HOSE PIPE 1/4",LT-90° ONE SIDE,(R2) 5500MM LONG (FOR HYD. MOTOR DRAIN) | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.7 |  | DRAG CHAIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 09-Mar-26 12:12 PM | 09-Mar-26 01:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.8 |  | FRAME | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.9 |  | BRACKET | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.10 |  | DRAG CHAIN SUPPORT FRAME | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.11 |  | STOPPER | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.13 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.14 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M12 x 50 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.15 |  | Hexagon Flange Nut IS 15581 - M12-N | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.16 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.17 |  | Plain Washer (Type B) IS 2016 - 14 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.18 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.1.19 |  | RAIL CLAMP | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2 |  | Ready for Assy | step |  |  |  | 5.2.1
5.2.2.1 |  | SHIM | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.2 |  | PLATE-230.0x170.0x12.0MM THK | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.3 |  | RAIL I.R.S. NO. 52. LENGTH- 8975.0 MM | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.4 |  | HOSE PIPE 3/4",LT-90° ONE SIDE,(R2) 5500MM LONG (FOR HYD. MOTOR) | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.5 |  | HOSE PIPE 1",LT-90° ONE SIDE,(R2) 5500MM LONG (FOR HYD. CYLINDER) | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.6 |  | HOSE PIPE 1/4",LT-90° ONE SIDE,(R2) 5500MM LONG (FOR HYD. MOTOR DRAIN) | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.7 |  | DRAG CHAIN | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 09-Mar-26 12:12 PM | 09-Mar-26 01:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.8 |  | FRAME | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.9 |  | BRACKET | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.10 |  | DRAG CHAIN SUPPORT FRAME | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.11 |  | STOPPER | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.13 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.14 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M12 x 50 | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.15 |  | Hexagon Flange Nut IS 15581 - M12-N | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.16 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.17 |  | Plain Washer (Type B) IS 2016 - 14 | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.18 |  | Spring Lock Washer IS 6735 - 12 | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.2.2.19 |  | RAIL CLAMP | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.3 |  | COIL SADDLE ASSY. @ RECOILER | Subtask |  | 65d | 65d |  |  | IP | YES | [5 empty] | 1d |  | 152d14h |  |  | 16-Oct-25 12:00 PM | 26-Dec-25 02:00 PM |  | 26-Mar-26 02:25 AM | 07-Oct-25 03:10 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
5.3.1 |  | Release of PO | step |  |  |  |  | 5.3.2
5.3.1.1 |  | FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:04 PM | 14-Nov-25 05:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.3.1.2 |  | PAD 180 X 660 X 25MM THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:04 PM | 14-Nov-25 05:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.3.1.3 |  | SHEAR BLOCK- 15X15X80MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:04 PM | 14-Nov-25 05:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.3.1.4 |  | Socket Head Cap Screw IS 2269 - M10 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:04 PM | 14-Nov-25 05:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.3.1.5 |  | STOPPER 10X10X140 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Nov-25 04:04 PM | 14-Nov-25 05:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.3.2 |  | Ready for Assy | step |  |  |  | 5.3.1
5.3.2.1 |  | FRAME | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:04 PM | 14-Nov-25 05:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.3.2.2 |  | PAD 180 X 660 X 25MM THK | date |  | 55d |  |  |  | IP | YES | [5 empty] | 1d |  | 117d14h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  | 23-Mar-26 09:00 PM | 14-Nov-25 04:04 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.3.2.3 |  | SHEAR BLOCK- 15X15X80MM | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:04 PM | 14-Nov-25 05:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.3.2.4 |  | Socket Head Cap Screw IS 2269 - M10 x 35 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:04 PM | 14-Nov-25 05:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.3.2.5 |  | STOPPER 10X10X140 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 14-Nov-25 04:04 PM | 14-Nov-25 05:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
5.4 |  | PIT COVER-1A @ RECOILER | Subtask |  | 65d | 65d |  |  | IP | YES | [5 empty] | 65d | 65d | 72d6h |  |  | 16-Oct-25 12:00 PM | 26-Dec-25 02:00 PM |  | 04-Jun-26 04:25 AM | 14-Mar-26 12:35 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
5.4.1 |  | Release of PO | step |  |  |  |  | 5.4.2
5.4.1.1 |  | SLIDING FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.2 |  | SLIDING FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.3 |  | SLIDING FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.4 |  | SLIDING FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.5 |  | FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.6 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Mar-26 12:35 PM | 14-Mar-26 01:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.7 |  | SLIDING FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.8 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Mar-26 12:35 PM | 14-Mar-26 01:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.9 |  | PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Mar-26 12:35 PM | 14-Mar-26 01:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.10 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Mar-26 12:35 PM | 14-Mar-26 01:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.11 |  | BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Mar-26 12:35 PM | 14-Mar-26 01:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.12 |  | PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 14-Mar-26 12:35 PM | 14-Mar-26 01:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.13 |  | ISMC- 100x10x, LONG- 6500mm | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.14 |  | CAM FOLLOWER KR62 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.15 |  | Hexagon nut IS 1363- Part2 - M24-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.17 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.18 |  | Spring Lock Washer IS 6735 - 10 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.20 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.22 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.23 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.24 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.25 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.26 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.1.27 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 20-Mar-26 10:37 AM | 20-Mar-26 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2 |  | Ready for Assy | step |  |  |  | 5.4.1
5.4.2.1 |  | SLIDING FRAME | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.2 |  | SLIDING FRAME | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.3 |  | SLIDING FRAME | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.4 |  | SLIDING FRAME | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.5 |  | FRAME | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.6 |  | BRACKET | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.7 |  | SLIDING FRAME | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.8 |  | SPACER | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.9 |  | PLATE | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.10 |  | SPACER | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.11 |  | BLOCK | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.12 |  | PLATE | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.13 |  | ISMC- 100x10x, LONG- 6500mm | date |  | 55d |  |  |  | NS | NO | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.14 |  | CAM FOLLOWER KR62 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.15 |  | Hexagon nut IS 1363- Part2 - M24-N | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 70 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.17 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.18 |  | Spring Lock Washer IS 6735 - 10 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 20 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.20 |  | Spring Lock Washer IS 6735 - 16 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.22 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.23 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.24 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.25 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.26 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.4.2.27 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 55d |  |  |  | NS | YES | [5 empty] | 55d |  |  |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 23-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
5.5 |  | PIT COVER-1B @ RECOILER | Subtask |  | 65d |  |  |  | NS | YES | [5 empty] | 65d |  |  |  |  | 16-Oct-25 12:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 04-Jun-26 04:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
6 | 27 | Category 2 - ENTRY ACCUMULATOR ASSY. - Ordering & Manufacturing | TASK |  | 120d | 120d | 23 | 63 | IP | YES | 008-026 |  |  |  |  | 1d |  | 151d17h |  |  | 16-Aug-25 01:00 AM | 25-Dec-25 02:00 PM |  | 24-Mar-26 02:25 AM | 08-Oct-25 10:15 AM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
6.1 |  | ENTRY TOP FRAME | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 130d3h |  |  | 16-Aug-25 01:00 AM | 25-Dec-25 02:00 PM |  |  | 08-Oct-25 10:15 AM | 27-Feb-26 06:25 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
6.1.1 |  | Release of PO | step |  |  |  |  | 6.1.2
6.1.1.1 |  | AIA2400802-OIL SEAL-ID240XOD270X15 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:17 AM | 03-Nov-25 12:17 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.2 |  | BEARING BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.3 |  | STOPPER PLATE 150 x 90 x 20 MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.4 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.5 |  | END COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.6 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.7 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.8 |  | GEARBOX 55KW,RATIO-153.086:1,H4N 500 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 10:19 AM | 03-Nov-25 11:19 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.9 |  | SPROCKET SHAFT 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.10 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.11 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.12 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.13 |  | COUPLING AHG-110 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 10:19 AM | 03-Nov-25 11:19 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.14 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.15 |  | COUPLING AHG-110 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 08-Nov-25 11:39 AM | 08-Nov-25 12:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.16 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.17 |  | CHAQUERD PLATE 3000X1250X6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 20d9h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:33 AM | 04-Dec-25 05:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.18 |  | GEARBOX SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:33 AM | 12-Nov-25 12:33 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.19 |  | AHG-104 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 10:19 AM | 03-Nov-25 11:19 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.20 |  | MOTOR SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.21 |  | MOTOR SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.22 |  | MOTOR SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 11d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.23 |  | SPROCKET SHAFT 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.24 |  | SPOCKET KEY 50 X 28 X 285 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 21d1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 04-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.25 |  | COUPLING KEY 50 X 28 X 170 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 21d1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 04-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.26 |  | SPOCKET KEY 50 X 28 X 105 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 21d1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 04-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.27 |  | TOP FRAME FAB. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 08-Nov-25 11:43 AM | 08-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.28 |  | BRAKE STAND | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.29 |  | SLING PULLEY BLOCK ASSY | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.30 |  | LIFTING FORK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:59 PM | 29-Oct-25 04:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.31 |  | MOTOR-FRAME (M2BAX 315SMA8) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.32 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.34 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.35 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.37 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.40 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M42 x 130 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.43 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.44 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.45 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.46 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.47 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.48 |  | Plain Washer (Type A) IS 2016 - 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.49 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.50 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.51 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.52 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.53 |  | Spring Lock Washer IS 3063 - 42-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.54 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.55 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.56 |  | Spring Lock Washer IS 6735 - 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.57 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.58 |  | NUT M80X6-DEL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.59 |  | SKF_23044 CC_W33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 21d1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 04-Dec-25 04:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.60 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.61 |  | STOPPER 20X20X100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.1.62 |  | SPROCKET 2.5 INCH 25 TEETH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:57 PM | 29-Oct-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2 |  | Ready for Assy | step |  |  |  | 6.1.1
6.1.2.1 |  | AIA2400802-OIL SEAL-ID240XOD270X15 THK. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 28d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 03-Nov-25 11:17 AM | 04-Dec-25 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.2 |  | BEARING BLOCK | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.3 |  | STOPPER PLATE 150 x 90 x 20 MM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.4 |  | RETAINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.5 |  | END COVER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.6 |  | RETAINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.7 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.8 |  | GEARBOX 55KW,RATIO-153.086:1,H4N 500 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 03:33 PM | 11-Nov-25 04:33 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.9 |  | SPROCKET SHAFT 1 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.10 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.11 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.12 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.13 |  | COUPLING AHG-110 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 03:33 PM | 11-Nov-25 04:33 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.14 |  | TIE ROD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.15 |  | COUPLING AHG-110 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 08-Nov-25 11:39 AM | 12-Nov-25 11:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.16 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.17 |  | CHAQUERD PLATE 3000X1250X6 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 20d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:34 AM | 04-Dec-25 05:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.18 |  | GEARBOX SHIM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 10d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:34 AM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.19 |  | AHG-104 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d11h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 08-Nov-25 11:43 AM | 11-Nov-25 03:33 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.20 |  | MOTOR SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.21 |  | MOTOR SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.22 |  | MOTOR SHIM | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 11d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.23 |  | SPROCKET SHAFT 2 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 24-Nov-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.24 |  | SPOCKET KEY 50 X 28 X 285 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 33d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 18-Dec-25 09:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.25 |  | COUPLING KEY 50 X 28 X 170 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 33d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 18-Dec-25 09:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.26 |  | SPOCKET KEY 50 X 28 X 105 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 33d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 18-Dec-25 09:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.27 |  | TOP FRAME FAB. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d11h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 08-Nov-25 11:43 AM | 11-Nov-25 03:33 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.28 |  | BRAKE STAND | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 55d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 29-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.29 |  | SLING PULLEY BLOCK ASSY | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d7h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 24-Nov-25 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.30 |  | LIFTING FORK | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:59 PM | 29-Oct-25 04:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.31 |  | MOTOR-FRAME (M2BAX 315SMA8) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 27-Feb-26 06:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.32 |  | GREASE NIPPLE 1/8" BSP | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.34 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.35 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.37 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.40 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 80 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 90 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M42 x 130 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.43 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.44 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.45 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.46 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.47 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.48 |  | Plain Washer (Type A) IS 2016 - 45 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.49 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.50 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.51 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.52 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.53 |  | Spring Lock Washer IS 3063 - 42-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.54 |  | Spring Lock Washer IS 6735 - 16 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.55 |  | Spring Lock Washer IS 6735 - 24 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.56 |  | Spring Lock Washer IS 6735 - 30 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.57 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 27-Feb-26 06:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.58 |  | NUT M80X6-DEL | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.59 |  | SKF_23044 CC_W33 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 27-Feb-26 06:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.60 |  | SHEAR BIOCK- 10x10x50mm | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.61 |  | STOPPER 20X20X100 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:21 PM | 11-Nov-25 08:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.1.2.62 |  | SPROCKET 2.5 INCH 25 TEETH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 33d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 29-Oct-25 03:57 PM | 04-Dec-25 04:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2 |  | ENTRY FIX FRAME | Subtask |  | 100d | 100d |  |  | CO | YES | [7 empty] | 43d11h |  |  | 16-Aug-25 01:00 AM | 03-Dec-25 05:00 PM |  |  | 29-Oct-25 03:46 PM | 16-Dec-25 01:25 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
6.2.1 |  | Release of PO | step |  |  |  |  | 6.2.2
6.2.1.1 |  | FIXED FRAME FABRICATION | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.2 |  | FEMALE BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.3 |  | MALE BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.4 |  | COVER PLATE Ø230 x 15 MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.5 |  | BELLEVILLE SPRING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.6 |  | ENTRY ACCUMULATOR ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.7 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.8 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.9 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.10 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.11 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.13 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.14 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M12-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.15 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.17 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.18 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.20 |  | Hexagon Nut Style 1 IS 1364- Part3 - M12-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.21 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.22 |  | Socket Head Cap Screw IS 2269 - M12 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.23 |  | Clevis Pin IS 6862 - 10 x 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.24 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.25 |  | BEARING HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.26 |  | RETAINER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.27 |  | RETAINER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.28 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.29 |  | END COVER LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.30 |  | END COVER RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.31 |  | BEARING,SPHERICAL,22216 E(SPHERICAL ROLLER BEARING DR 80IDx140ODx33THK) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.32 |  | OIL SEAL-90ID x 110OD x 10THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d4h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 08-Nov-25 11:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.33 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.34 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.35 |  | Spring Lock Washer IS 6735 - 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.1.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 110 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:47 PM | 29-Oct-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2 |  | Ready for Assy | step |  |  |  | 6.2.1
6.2.2.1 |  | FIXED FRAME FABRICATION | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.2 |  | FEMALE BLOCK | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 19d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 24-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.3 |  | MALE BLOCK | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 19d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 24-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.4 |  | COVER PLATE Ø230 x 15 MM | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 19d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 24-Nov-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.5 |  | BELLEVILLE SPRING | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 39d8h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 16-Dec-25 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.6 |  | ENTRY ACCUMULATOR ROLL | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.7 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.8 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.9 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.10 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.11 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.13 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.14 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M12-N | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.15 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 60 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.17 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.18 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 65 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.20 |  | Hexagon Nut Style 1 IS 1364- Part3 - M12-D-N | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.21 |  | Spring Lock Washer IS 6735 - 12 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.22 |  | Socket Head Cap Screw IS 2269 - M12 x 90 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.23 |  | Clevis Pin IS 6862 - 10 x 20-A | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.24 |  | GREASE NIPPLE 1/8" BSP | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.25 |  | BEARING HOUSING | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.26 |  | RETAINER-RH | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.27 |  | RETAINER-LH | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.28 |  | END PLATE | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.29 |  | END COVER LH | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.30 |  | END COVER RH | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.31 |  | BEARING,SPHERICAL,22216 E(SPHERICAL ROLLER BEARING DR 80IDx140ODx33THK) | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.32 |  | OIL SEAL-90ID x 110OD x 10THK | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.33 |  | BASE FRAME | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.34 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.35 |  | Spring Lock Washer IS 6735 - 30 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.2.2.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 110 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3 |  | ENTRY MOVING FRAME | Subtask |  | 100d | 100d |  |  | CO | YES | [7 empty] | 130d3h |  |  | 16-Aug-25 01:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Oct-25 10:15 AM | 27-Feb-26 06:26 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
6.3.1 |  | Release of PO | step |  |  |  |  | 6.3.2
6.3.1.1 |  | BEARING,SPHERICAL,22216 E(SPHERICAL ROLLER BEARING DR 80IDx140ODx33THK) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 08-Nov-25 11:35 AM | 08-Nov-25 12:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.2 |  | ENTRY ACCUMULATOR ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 08-Nov-25 11:35 AM | 08-Nov-25 12:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.3 |  | WHEEL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:44 PM | 29-Oct-25 04:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.4 |  | WHEEL PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:44 PM | 29-Oct-25 04:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.5 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:44 PM | 29-Oct-25 04:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.6 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 08-Nov-25 11:35 AM | 08-Nov-25 12:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.7 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:44 PM | 29-Oct-25 04:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.8 |  | SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d11h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:44 PM | 16-Dec-25 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.9 |  | LIFTING FORK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:44 PM | 29-Oct-25 04:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.10 |  | MOVING FRAME FAB. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 12:02 PM | 03-Nov-25 01:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.11 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:44 PM | 29-Oct-25 04:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.12 |  | LIFTING FORK ASSY | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.13 |  | OIL SEAL-90ID x 110OD x 10THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 08-Nov-25 11:35 AM | 08-Nov-25 12:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.14 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.15 |  | NUT M80X6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.16 |  | RETAINER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:44 PM | 29-Oct-25 04:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.17 |  | RETAINER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:44 PM | 29-Oct-25 04:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.18 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:44 PM | 29-Oct-25 04:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.19 |  | END COVER LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:44 PM | 29-Oct-25 04:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.20 |  | END COVER RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:44 PM | 29-Oct-25 04:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.21 |  | BEARING HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:44 PM | 29-Oct-25 04:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.22 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.23 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.24 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.25 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.26 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.27 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.28 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.29 |  | Hexagon Flange Nut IS 15581 - M12-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.30 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.31 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.32 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.33 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.34 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.35 |  | Socket Head Cap Screw IS 2269 - M12 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.36 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.37 |  | Spring Lock Washer IS 3063 - 12-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.38 |  | Spring Lock Washer IS 3063 - 20-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.39 |  | Spring Lock Washer IS 3063 - 24-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.1.40 |  | Clevis Pin IS 6862 - 10 x 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:57 AM | 03-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2 |  | Ready for Assy | step |  |  |  | 6.3.1
6.3.2.1 |  | BEARING,SPHERICAL,22216 E(SPHERICAL ROLLER BEARING DR 80IDx140ODx33THK) | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.2 |  | ENTRY ACCUMULATOR ROLL | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.3 |  | WHEEL | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 14d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 24-Nov-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.4 |  | WHEEL PIN | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 14d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 24-Nov-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.5 |  | SPACER | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 14d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 24-Nov-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.6 |  | BUSH | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 14d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 24-Nov-25 11:01 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.7 |  | END PLATE | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 14d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 24-Nov-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.8 |  | SHIM | date |  | 90d |  |  |  | CO | NO | [5 empty] | 0d |  | 34d8h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 16-Dec-25 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.9 |  | LIFTING FORK | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 14d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 24-Nov-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.10 |  | MOVING FRAME FAB. | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.11 |  | BRACKET | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 14d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 24-Nov-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.12 |  | LIFTING FORK ASSY | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 14d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 24-Nov-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.13 |  | OIL SEAL-90ID x 110OD x 10THK | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.14 |  | GREASE NIPPLE 1/8" BSP | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.15 |  | NUT M80X6 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.16 |  | RETAINER-RH | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 14d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 24-Nov-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.17 |  | RETAINER-LH | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 14d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 24-Nov-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.18 |  | END PLATE | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 14d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 24-Nov-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.19 |  | END COVER LH | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 14d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 24-Nov-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.20 |  | END COVER RH | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 14d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 24-Nov-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.21 |  | BEARING HOUSING | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 14d3h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 24-Nov-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.22 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.23 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.24 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 60 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.25 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 65 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.26 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.27 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.28 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.29 |  | Hexagon Flange Nut IS 15581 - M12-N | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.30 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.31 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.32 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.33 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.34 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.35 |  | Socket Head Cap Screw IS 2269 - M12 x 100 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.36 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.37 |  | Spring Lock Washer IS 3063 - 12-B | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.38 |  | Spring Lock Washer IS 3063 - 20-B | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.39 |  | Spring Lock Washer IS 3063 - 24-B | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.3.2.40 |  | Clevis Pin IS 6862 - 10 x 30-A | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 11:35 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4 |  | ENTRY COUNTER WEIGHT | Subtask |  | 100d | 100d |  |  | CO | YES | [7 empty] | 130d3h |  |  | 16-Aug-25 01:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Oct-25 10:15 AM | 27-Feb-26 06:26 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
6.4.1 |  | Release of PO | step |  |  |  |  | 6.4.2
6.4.1.1 |  | OILSEAL- 156x186x15 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 08-Nov-25 02:34 PM | 08-Nov-25 03:34 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.2 |  | SPHERICAL ROLLER BRG D 140IDx250ODx68T HK. mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 10d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:42 AM | 24-Nov-25 11:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.3 |  | BEARING BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:40 PM | 29-Oct-25 04:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.4 |  | SPROCKET SHAFT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:40 PM | 29-Oct-25 04:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.5 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:40 PM | 29-Oct-25 04:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.6 |  | END COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:40 PM | 29-Oct-25 04:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.7 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:40 PM | 29-Oct-25 04:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.8 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:40 PM | 29-Oct-25 04:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.9 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:40 PM | 29-Oct-25 04:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.10 |  | COUNTER WEIGHT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 36d4h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:53 AM | 12-Dec-25 04:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.11 |  | COUNTER WEIGHT COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d15h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:42 AM | 12-Dec-25 04:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.12 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:53 AM | 03-Nov-25 12:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.13 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:53 AM | 03-Nov-25 12:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.14 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:53 AM | 03-Nov-25 12:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.15 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:53 AM | 03-Nov-25 12:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:53 AM | 03-Nov-25 12:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.17 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:53 AM | 03-Nov-25 12:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.18 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:53 AM | 03-Nov-25 12:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.19 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:53 AM | 03-Nov-25 12:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.20 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:53 AM | 03-Nov-25 12:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.21 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:53 AM | 03-Nov-25 12:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.22 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:53 AM | 03-Nov-25 12:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.23 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:53 AM | 03-Nov-25 12:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.24 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 03-Nov-25 11:53 AM | 03-Nov-25 12:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.1.25 |  | SPROCKET 2.5 INCH 25 TEETH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 29-Oct-25 03:48 PM | 29-Oct-25 04:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2 |  | Ready for Assy | step |  |  |  | 6.4.1
6.4.2.1 |  | OILSEAL- 156x186x15 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 14d1h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 08-Nov-25 02:34 PM | 24-Nov-25 11:10 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.2 |  | SPHERICAL ROLLER BRG D 140IDx250ODx68T HK. mm | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d4h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 12-Nov-25 11:42 AM | 27-Feb-26 06:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
6.4.2.3 |  | BEARING BLOCK | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d11h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 29-Oct-25 03:40 PM | 16-Dec-25 01:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.4 |  | SPROCKET SHAFT | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d11h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 29-Oct-25 03:40 PM | 16-Dec-25 01:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.5 |  | RETAINER | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d11h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 29-Oct-25 03:40 PM | 16-Dec-25 01:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.6 |  | END COVER | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d11h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 29-Oct-25 03:40 PM | 16-Dec-25 01:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.7 |  | END PLATE | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d11h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 29-Oct-25 03:40 PM | 16-Dec-25 01:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.8 |  | SPACER | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d11h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 29-Oct-25 03:40 PM | 16-Dec-25 01:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.9 |  | SPACER | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d11h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 29-Oct-25 03:40 PM | 16-Dec-25 01:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.10 |  | COUNTER WEIGHT | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 39d8h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 16-Dec-25 01:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.11 |  | COUNTER WEIGHT COVER | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d1h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 12-Nov-25 11:42 AM | 16-Dec-25 01:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.12 |  | GREASE NIPPLE 1/8" BSP | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.13 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.14 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.15 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 100 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.17 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.18 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.19 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.20 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.21 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.22 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.23 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.24 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 03-Nov-25 11:53 AM | 12-Nov-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
6.4.2.25 |  | SPROCKET 2.5 INCH 25 TEETH | date |  | 90d |  |  |  | CO | YES | [5 empty] | 0d |  | 12d11h |  |  | 27-Aug-25 05:00 AM | 03-Dec-25 05:00 PM |  |  | 29-Oct-25 03:48 PM | 12-Nov-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
7 | 95 | Category 5 - SHEAR ASSY - Ordering & Manufacturing | TASK |  | 100d | 100d | 58 | 74 | IP | NO | 011-031 |  |  |  |  | 1d | 1d | 132d8h |  |  | 17-Aug-25 08:00 AM | 04-Dec-25 05:00 PM | 28-Mar-26 02:25 AM | 29-Mar-26 09:25 AM | 29-Oct-25 05:49 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
7.1 |  | DOUBLE DECKER ENTRY SHEAR ASSY. | Subtask |  | 100d | 100d |  |  | IP | YES | [5 empty] | 1d |  | 132d8h |  |  | 17-Aug-25 08:00 AM | 04-Dec-25 05:00 PM |  | 29-Mar-26 09:25 AM | 29-Oct-25 05:49 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
7.1.1 |  | Release of PO | step |  |  |  |  | 7.1.2
7.1.1.1 |  | DOUBLE DECKER ENTRY SHEAR ASSY | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 12-Nov-25 02:29 PM | 12-Nov-25 03:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
7.1.2 |  | Ready for Assy | step |  |  |  | 7.1.1
7.1.2.1 |  | DOUBLE DECKER ENTRY SHEAR ASSY | date |  | 90d |  |  |  | IP | YES | [5 empty] | 1d |  | 119d15h |  |  | 28-Aug-25 05:00 AM | 04-Dec-25 05:00 PM |  | 23-Mar-26 09:00 PM | 12-Nov-25 02:29 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
7.2 |  | DELIVERY SHEAR ASSY. | Subtask |  | 100d | 100d |  |  | IP | YES | [5 empty] | 1d |  | 132d8h |  |  | 17-Aug-25 08:00 AM | 04-Dec-25 05:00 PM |  | 29-Mar-26 09:25 AM | 29-Oct-25 05:49 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
7.2.1 |  | Release of PO | step |  |  |  |  | 7.2.2
7.2.1.1 |  | DELIVERY SHEAR ASSY | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  |  | 12-Nov-25 02:29 PM | 12-Nov-25 03:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
7.2.2 |  | Ready for Assy | step |  |  |  | 7.2.1
7.2.2.1 |  | DELIVERY SHEAR ASSY | date |  | 90d |  |  |  | IP | YES | [5 empty] | 1d |  | 119d15h |  |  | 28-Aug-25 05:00 AM | 04-Dec-25 05:00 PM |  | 23-Mar-26 09:00 PM | 12-Nov-25 02:29 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8 | 39 | Category 1 - DEFLECTOR ROLL ASSY - Ordering & Manufacturing | TASK |  | 65d | 65d | 26 | 54 | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:50 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.1 |  | DEFLECTOR ROLL ASSY. | Subtask |  | 65d | 65d |  |  | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:50 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.1.1 |  | Release of PO | step |  |  |  |  | 8.1.2
8.1.1.1 |  | DEFLECTOR ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:09 AM | 08-Nov-25 11:09 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.2 |  | BEARING HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.3 |  | RETAINER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.4 |  | RETAINER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.5 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.6 |  | END COVER LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.7 |  | END COVER RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.8 |  | BEARING,SPHERICAL,22216 E(SPHERICAL ROLLER BEARING DR 80IDx140ODx33THK) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:06 AM | 08-Nov-25 11:06 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.9 |  | AIA0900804-OIL SEAL_90x110x8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d13h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:10 AM | 11-Nov-25 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.10 |  | DOWEL PIN-Ø10X20.00 MM LONG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.11 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.12 |  | Hexagon Had Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.13 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.14 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.15 |  | Socket Head Cap Screw IS 2269 - M12 x100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.16 |  | Hexagon Head Screw (Grade C) IS1363(Part2) - M10 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.17 |  | Spring Lock Washer IS 6735 - 10 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.1.18 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2 |  | Ready for Assy | step |  |  |  | 8.1.1
8.1.2.1 |  | DEFLECTOR ROLL | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:09 AM | 08-Nov-25 11:09 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2.2 |  | BEARING HOUSING | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2.3 |  | RETAINER-RH | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2.4 |  | RETAINER-LH | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2.5 |  | END PLATE | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2.6 |  | END COVER LH | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2.7 |  | END COVER RH | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2.8 |  | BEARING,SPHERICAL,22216 E(SPHERICAL ROLLER BEARING DR 80IDx140ODx33THK) | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d9h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:06 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
8.1.2.9 |  | AIA0900804-OIL SEAL_90x110x8 | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d2h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:06 AM | 08-Dec-25 02:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2.10 |  | DOWEL PIN-Ø10X20.00 MM LONG | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2.11 |  | GREASE NIPPLE 1/8" BSP | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2.12 |  | Hexagon Had Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2.13 |  | Spring Lock Washer IS 6735 - 12 | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2.14 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2.15 |  | Socket Head Cap Screw IS 2269 - M12 x100 | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2.16 |  | Hexagon Head Screw (Grade C) IS1363(Part2) - M10 x 40 | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2.17 |  | Spring Lock Washer IS 6735 - 10 | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.1.2.18 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 10:03 AM | 08-Nov-25 11:03 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.2 |  | DEFLECTOR ROLL FRAME ASSY.#1 (AFTER D.D SHEAR) | Subtask |  | 65d | 65d |  |  | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:50 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.2.1 |  | Release of PO | step |  |  |  |  | 8.2.2
8.2.1.1 |  | FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 09-Dec-25 11:03 AM | 09-Dec-25 12:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.2.1.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:12 PM | 11-Nov-25 07:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.2.1.3 |  | Spring Lock Washer IS 6735- 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:12 PM | 11-Nov-25 07:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.2.1.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:12 PM | 11-Nov-25 07:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.2.2 |  | Ready for Assy | step |  |  |  | 8.2.1
8.2.2.1 |  | FRAME | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 72d10h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 09-Dec-25 11:03 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
8.2.2.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:12 PM | 11-Nov-25 07:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.2.2.3 |  | Spring Lock Washer IS 6735- 24 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:12 PM | 11-Nov-25 07:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.2.2.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:12 PM | 11-Nov-25 07:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.3 |  | DEFLECTOR ROLL FRAME ASSY.#2 (BEFORE BRIDLE ROLL ASSY.#1) | Subtask |  | 65d | 65d |  |  | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:51 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.3.1 |  | Release of PO | step |  |  |  |  | 8.3.2
8.3.1.1 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:44 PM | 11-Nov-25 06:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.3.1.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:44 PM | 11-Nov-25 06:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.3.1.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:44 PM | 11-Nov-25 06:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.3.1.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:44 PM | 11-Nov-25 06:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.3.2 |  | Ready for Assy | step |  |  |  | 8.3.1
8.3.2.1 |  | BASE FRAME | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:44 PM | 11-Nov-25 06:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.3.2.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:44 PM | 11-Nov-25 06:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.3.2.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:44 PM | 11-Nov-25 06:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.3.2.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:44 PM | 11-Nov-25 06:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.4 |  | DEFLECTOR ROLL FRAME ASSY.#3 (AFTER HOT AIR DRYER) | Subtask |  | 65d | 65d |  |  | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:51 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.4.1 |  | Release of PO | step |  |  |  |  | 8.4.2
8.4.1.1 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:45 PM | 11-Nov-25 06:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.4.1.2 |  | PLATE 470 X 220 X 30MM THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:45 PM | 11-Nov-25 06:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.4.1.3 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:45 PM | 11-Nov-25 06:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.4.1.4 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:45 PM | 11-Nov-25 06:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.4.1.5 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:45 PM | 11-Nov-25 06:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.4.1.6 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:45 PM | 11-Nov-25 06:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.4.2 |  | Ready for Assy | step |  |  |  | 8.4.1
8.4.2.1 |  | BASE FRAME | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:45 PM | 11-Nov-25 06:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.4.2.2 |  | PLATE 470 X 220 X 30MM THK | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:45 PM | 11-Nov-25 06:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.4.2.3 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:45 PM | 11-Nov-25 06:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.4.2.4 |  | Spring Lock Washer IS 6735 - 24 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:45 PM | 11-Nov-25 06:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.4.2.5 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:45 PM | 11-Nov-25 06:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.4.2.6 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:45 PM | 11-Nov-25 06:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.5 |  | DEFLECTOR ROLL FRAME ASSY.#4&5 (AFTER HOT AIR DRYER) | Subtask |  | 65d | 65d |  |  | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:51 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.5.1 |  | Release of PO | step |  |  |  |  | 8.5.2
8.5.1.1 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:52 PM | 11-Nov-25 06:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.5.1.2 |  | PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:52 PM | 11-Nov-25 06:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.5.1.3 |  | STOPPER 20X20X100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:52 PM | 11-Nov-25 06:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.5.1.4 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:52 PM | 11-Nov-25 06:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.5.1.5 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:52 PM | 11-Nov-25 06:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.5.1.6 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:52 PM | 11-Nov-25 06:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.5.1.7 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:52 PM | 11-Nov-25 06:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.5.2 |  | Ready for Assy | step |  |  |  | 8.5.1
8.5.2.1 |  | BASE FRAME | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:52 PM | 11-Nov-25 06:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.5.2.2 |  | PLATE | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:52 PM | 11-Nov-25 06:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.5.2.3 |  | STOPPER 20X20X100 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:52 PM | 11-Nov-25 06:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.5.2.4 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:52 PM | 11-Nov-25 06:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.5.2.5 |  | Spring Lock Washer IS 6735 - 24 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:52 PM | 11-Nov-25 06:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.5.2.6 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:52 PM | 11-Nov-25 06:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.5.2.7 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:52 PM | 11-Nov-25 06:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.6 |  | DEFLECTOR ROLL FRAME ASSY.#6 (BEFORE BRIDLE ROLL ASSY.#2) | Subtask |  | 65d | 65d |  |  | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:51 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.6.1 |  | Release of PO | step |  |  |  |  | 8.6.2
8.6.1.1 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:09 PM | 11-Nov-25 07:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.6.1.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:09 PM | 11-Nov-25 07:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.6.1.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:09 PM | 11-Nov-25 07:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.6.1.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:09 PM | 11-Nov-25 07:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.6.2 |  | Ready for Assy | step |  |  |  | 8.6.1
8.6.2.1 |  | BASE FRAME | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:09 PM | 11-Nov-25 07:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.6.2.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:09 PM | 11-Nov-25 07:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.6.2.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:09 PM | 11-Nov-25 07:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.6.2.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:09 PM | 11-Nov-25 07:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.7 |  | DEFLECTOR ROLL FRAME ASSY.#7 (AFTER ENTRY ACC ASSY.) | Subtask |  | 65d | 65d |  |  | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:51 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.7.1 |  | Release of PO | step |  |  |  |  | 8.7.2
8.7.1.1 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:53 PM | 11-Nov-25 06:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.7.1.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:53 PM | 11-Nov-25 06:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.7.1.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:53 PM | 11-Nov-25 06:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.7.1.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:53 PM | 11-Nov-25 06:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.7.2 |  | Ready for Assy | step |  |  |  | 8.7.1
8.7.2.1 |  | BASE FRAME | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:53 PM | 11-Nov-25 06:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.7.2.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:53 PM | 11-Nov-25 06:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.7.2.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:53 PM | 11-Nov-25 06:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.7.2.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:53 PM | 11-Nov-25 06:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.8 |  | DEFLECTOR ROLL FRAME ASSY.#8 (BEFORE BRIDLE ROLL ASY.#03) | Subtask |  | 65d | 65d |  |  | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Oct-25 05:51 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.8.1 |  | Release of PO | step |  |  |  |  | 8.8.2
8.8.1.1 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:54 PM | 11-Nov-25 06:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.8.1.2 |  | PLATE 470 X 220 X 30MM THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:54 PM | 11-Nov-25 06:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.8.1.3 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:54 PM | 11-Nov-25 06:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.8.1.4 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:54 PM | 11-Nov-25 06:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.8.1.5 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:54 PM | 11-Nov-25 06:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.8.1.6 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:54 PM | 11-Nov-25 06:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.8.2 |  | Ready for Assy | step |  |  |  | 8.8.1
8.8.2.1 |  | BASE FRAME | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:54 PM | 11-Nov-25 06:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.8.2.2 |  | PLATE 470 X 220 X 30MM THK | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:54 PM | 11-Nov-25 06:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.8.2.3 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:54 PM | 11-Nov-25 06:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.8.2.4 |  | Spring Lock Washer IS 6735 - 24 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:54 PM | 11-Nov-25 06:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.8.2.5 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:54 PM | 11-Nov-25 06:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.8.2.6 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:54 PM | 11-Nov-25 06:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.9 |  | DEFLECTOR ROLL FRAME ASSY.#9 (AFTER TURN DOWN ROLL ASSY.) | Subtask |  | 1d | 65d |  |  | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 17-Oct-25 10:00 AM |  |  | 29-Oct-25 05:52 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.9.1 |  | Release of PO | step |  |  |  |  | 8.9.2
8.9.1.1 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:57 PM | 11-Nov-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.9.1.2 |  | PLATE 470 X 220 X 30MM THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:57 PM | 11-Nov-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.9.1.3 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:57 PM | 11-Nov-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.9.1.4 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:57 PM | 11-Nov-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.9.1.5 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:57 PM | 11-Nov-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.9.1.6 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 05:57 PM | 11-Nov-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.9.2 |  | Ready for Assy | step |  |  |  | 8.9.1
8.9.2.1 |  | BASE FRAME | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:57 PM | 11-Nov-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.9.2.2 |  | PLATE 470 X 220 X 30MM THK | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:57 PM | 11-Nov-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.9.2.3 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:57 PM | 11-Nov-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.9.2.4 |  | Spring Lock Washer IS 6735 - 24 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:57 PM | 11-Nov-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.9.2.5 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:57 PM | 11-Nov-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.9.2.6 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 05:57 PM | 11-Nov-25 06:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.10 |  | DEFLECTOR ROLL FRAME ASSY.#10 (BEFORE WATER SPRAY UNIT) | Subtask |  | 1d | 65d |  |  | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 17-Oct-25 10:00 AM |  |  | 29-Oct-25 05:53 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.10.1 |  | Release of PO | step |  |  |  |  | 8.10.2
8.10.1.1 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:00 PM | 11-Nov-25 07:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.10.1.2 |  | PLATE 470 X 220 X 30MM THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:00 PM | 11-Nov-25 07:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.10.1.3 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:00 PM | 11-Nov-25 07:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.10.1.4 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:00 PM | 11-Nov-25 07:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.10.1.5 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:00 PM | 11-Nov-25 07:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.10.1.6 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:00 PM | 11-Nov-25 07:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.10.2 |  | Ready for Assy | step |  |  |  | 8.10.1
8.10.2.1 |  | BASE FRAME | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:00 PM | 11-Nov-25 07:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.10.2.2 |  | PLATE 470 X 220 X 30MM THK | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:00 PM | 11-Nov-25 07:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.10.2.3 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:00 PM | 11-Nov-25 07:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.10.2.4 |  | Spring Lock Washer IS 6735 - 24 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:00 PM | 11-Nov-25 07:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.10.2.5 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:00 PM | 11-Nov-25 07:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.10.2.6 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:00 PM | 11-Nov-25 07:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.11 |  | DEFLECTOR ROLL FRAME ASSY.#11 (BEFORE BRIDLE ROLL ASY.#04) | Subtask |  | 1d | 65d |  |  | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 17-Oct-25 10:00 AM |  |  | 29-Oct-25 05:53 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.11.1 |  | Release of PO | step |  |  |  |  | 8.11.2
8.11.1.1 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:02 PM | 11-Nov-25 07:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.11.1.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:02 PM | 11-Nov-25 07:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.11.1.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:02 PM | 11-Nov-25 07:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.11.1.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:02 PM | 11-Nov-25 07:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.11.2 |  | Ready for Assy | step |  |  |  | 8.11.1
8.11.2.1 |  | BASE FRAME | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:02 PM | 11-Nov-25 07:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.11.2.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:02 PM | 11-Nov-25 07:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.11.2.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:02 PM | 11-Nov-25 07:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.11.2.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:02 PM | 11-Nov-25 07:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.12 |  | DEFLECTOR ROLL FRAME ASSY.#12 (AFTER BRIDLE ROLL ASSY.# 8) | Subtask |  | 1d | 65d |  |  | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 17-Oct-25 10:00 AM |  |  | 29-Oct-25 05:53 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.12.1 |  | Release of PO | step |  |  |  |  | 8.12.2
8.12.1.1 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:03 PM | 11-Nov-25 07:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.12.1.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:03 PM | 11-Nov-25 07:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.12.1.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:03 PM | 11-Nov-25 07:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.12.1.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:03 PM | 11-Nov-25 07:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.12.2 |  | Ready for Assy | step |  |  |  | 8.12.1
8.12.2.1 |  | BASE FRAME | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:03 PM | 11-Nov-25 07:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.12.2.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:03 PM | 11-Nov-25 07:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.12.2.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:03 PM | 11-Nov-25 07:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.12.2.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:03 PM | 11-Nov-25 07:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.13 |  | DEFLECTOR ROLL FRAME ASSY.#13&14 (BEFORE CHEMICAL COATER) | Subtask |  | 1d | 65d |  |  | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 17-Oct-25 10:00 AM |  |  | 29-Oct-25 05:53 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.13.1 |  | Release of PO | step |  |  |  |  | 8.13.2
8.13.1.1 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:04 PM | 11-Nov-25 07:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.13.1.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:04 PM | 11-Nov-25 07:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.13.1.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:04 PM | 11-Nov-25 07:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.13.1.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:04 PM | 11-Nov-25 07:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.13.2 |  | Ready for Assy | step |  |  |  | 8.13.1
8.13.2.1 |  | BASE FRAME | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:04 PM | 11-Nov-25 07:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.13.2.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:04 PM | 11-Nov-25 07:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.13.2.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:04 PM | 11-Nov-25 07:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.13.2.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:04 PM | 11-Nov-25 07:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.14 |  | DEFLECTOR ROLL FRAME ASSY.#15 (BEFORE BRIDLE ROLL ASY.#09) | Subtask |  | 1d | 65d |  |  | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 17-Oct-25 10:00 AM |  |  | 29-Oct-25 05:53 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.14.1 |  | Release of PO | step |  |  |  |  | 8.14.2
8.14.1.1 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:05 PM | 11-Nov-25 07:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.14.1.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:05 PM | 11-Nov-25 07:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.14.1.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:05 PM | 11-Nov-25 07:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.14.1.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:05 PM | 11-Nov-25 07:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.14.2 |  | Ready for Assy | step |  |  |  | 8.14.1
8.14.2.1 |  | BASE FRAME | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:05 PM | 11-Nov-25 07:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.14.2.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:05 PM | 11-Nov-25 07:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.14.2.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:05 PM | 11-Nov-25 07:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.14.2.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 55d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:05 PM | 11-Nov-25 07:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.15 |  | DEFLECTOR ROLL FRAME ASSY.#16 (BEFORE LOGO MARKER) | Subtask |  | 1d | 75d |  |  | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 17-Oct-25 10:00 AM |  |  | 29-Oct-25 05:53 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.15.1 |  | Release of PO | step |  |  |  |  | 8.15.2
8.15.1.1 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:06 PM | 11-Nov-25 07:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.15.1.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:06 PM | 11-Nov-25 07:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.15.1.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:06 PM | 11-Nov-25 07:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.15.1.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:06 PM | 11-Nov-25 07:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.15.2 |  | Ready for Assy | step |  |  |  | 8.15.1
8.15.2.1 |  | BASE FRAME | date |  | 65d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 06-Jan-26 06:00 PM |  |  | 11-Nov-25 06:06 PM | 11-Nov-25 07:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.15.2.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 65d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 06-Jan-26 06:00 PM |  |  | 11-Nov-25 06:06 PM | 11-Nov-25 07:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.15.2.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 65d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 06-Jan-26 06:00 PM |  |  | 11-Nov-25 06:06 PM | 11-Nov-25 07:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.15.2.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 65d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 06-Jan-26 06:00 PM |  |  | 11-Nov-25 06:06 PM | 11-Nov-25 07:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.16 |  | DEFLECTOR ROLL FRAME ASSY.#17 (BEFORE BRIDLE ROLL ASSY.#10) | Subtask |  | 1d | 65d |  |  | CO | YES | [7 empty] | 109d10h |  |  | 16-Oct-25 12:00 PM | 17-Oct-25 10:00 AM |  |  | 29-Oct-25 05:53 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
8.16.1 |  | Release of PO | step |  |  |  |  | 8.16.2
8.16.1.1 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:07 PM | 11-Nov-25 07:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.16.1.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:07 PM | 11-Nov-25 07:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.16.1.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:07 PM | 11-Nov-25 07:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.16.1.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Oct-25 12:00 PM | 27-Oct-25 04:00 PM |  |  | 11-Nov-25 06:07 PM | 11-Nov-25 07:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.16.2 |  | Ready for Assy | step |  |  |  | 8.16.1
8.16.2.1 |  | BASE FRAME | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:07 PM | 11-Nov-25 07:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.16.2.2 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:07 PM | 11-Nov-25 07:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.16.2.3 |  | Spring Lock Washer IS 6735 - 24 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:07 PM | 11-Nov-25 07:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
8.16.2.4 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 55d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Oct-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:07 PM | 11-Nov-25 07:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
9 | 100 | Category 3/4 - Ordering & Manufacturing (1) | TASK |  | 70d | 70d | 59 | 85 | IP | NO | 014-012 |  |  |  |  | 70d | 70d | 201d8h |  |  | 06-Sep-25 07:00 AM | 22-Nov-25 02:00 AM | 28-Mar-26 02:25 AM | 12-Jun-26 05:25 PM | 29-Oct-25 05:54 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
9.1 |  | COATING THK GAUGE ASSY. (SPACE PROVISION) | Subtask |  | 70d |  |  |  | NS | YES | [5 empty] | 70d |  |  |  |  | 06-Sep-25 07:00 AM | 22-Nov-25 02:00 AM | 28-Mar-26 02:25 AM | 12-Jun-26 05:25 PM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
9.2 |  | CHEMICAL HANDLING SYSTEM | Subtask |  | 70d |  |  |  | IP | YES | [5 empty] | 70d |  | 119d7h |  |  | 06-Sep-25 07:00 AM | 22-Nov-25 02:00 AM |  | 12-Jun-26 05:25 PM | 27-Jan-26 05:47 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
9.3 |  | STRIP INDUCTION HEATER ASSY. WITH DRYER | Subtask |  | 70d |  |  |  | NS | YES | [5 empty] | 70d |  |  |  |  | 06-Sep-25 07:00 AM | 22-Nov-25 02:00 AM | 28-Mar-26 02:25 AM | 12-Jun-26 05:25 PM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
9.4 |  | EDGE WIPER ASSY. | Subtask |  | 70d |  |  |  | NS | YES | [5 empty] | 70d |  |  |  |  | 06-Sep-25 07:00 AM | 22-Nov-25 02:00 AM | 28-Mar-26 02:25 AM | 12-Jun-26 05:25 PM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
9.5 |  | SEAM WELDER ASSY. | Subtask |  | 70d | 70d |  |  | IP | YES | [5 empty] | 70d | 70d | 201d8h |  |  | 06-Sep-25 07:00 AM | 22-Nov-25 02:00 AM |  | 12-Jun-26 05:25 PM | 29-Oct-25 05:54 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
9.5.1 |  | Release of PO | step |  |  |  |  | 9.5.2
9.5.1.1 |  | SEAM WELDER ASSY. | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 06-Sep-25 07:00 AM | 17-Sep-25 01:00 PM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
9.5.2 |  | Ready for Assy | step |  |  |  | 9.5.1
9.5.2.1 |  | SEAM WELDER ASSY. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 17-Sep-25 01:00 PM | 22-Nov-25 02:00 AM | 08-Apr-26 06:25 AM | 12-Jun-26 05:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
9.6 |  | TENSION LEVELLER (TLL) | Subtask |  | 70d | 70d |  |  | IP | YES | [5 empty] | 70d | 70d | 201d8h |  |  | 06-Sep-25 07:00 AM | 22-Nov-25 02:00 AM |  | 12-Jun-26 05:25 PM | 29-Oct-25 05:54 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
9.6.1 |  | Release of PO | step |  |  |  |  | 9.6.2
9.6.1.1 |  | TENSION LEVELLER (TLL) | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 06-Sep-25 07:00 AM | 17-Sep-25 01:00 PM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
9.6.2 |  | Ready for Assy | step |  |  |  | 9.6.1
9.6.2.1 |  | TENSION LEVELLER (TLL) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 17-Sep-25 01:00 PM | 22-Nov-25 02:00 AM | 08-Apr-26 06:25 AM | 12-Jun-26 05:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
9.7 |  | FUME EXHAUST SYSTEM FOR CLANING SECTION | Subtask |  | 70d |  |  |  | NS | YES | [5 empty] | 70d |  |  |  |  | 06-Sep-25 07:00 AM | 22-Nov-25 02:00 AM | 28-Mar-26 02:25 AM | 12-Jun-26 05:25 PM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
9.8 |  | SEMI AUTOMATIC STRIP STRAPPING MACHINE | Subtask |  | 70d |  |  |  | NS | YES | [5 empty] | 70d |  |  |  |  | 06-Sep-25 07:00 AM | 22-Nov-25 02:00 AM | 28-Mar-26 02:25 AM | 12-Jun-26 05:25 PM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
10 | 30 | Category 2 - EXIT ACCUMULATOR ASSY. - Ordering & Manufacturing | TASK |  | 120d | 120d | 24 | 65 | IP | YES | 009-024 |  |  |  |  | 1d17h | 1d17h | 129d5h |  |  | 16-Aug-25 01:00 AM | 25-Dec-25 02:00 PM |  | 24-Mar-26 09:00 PM | 03-Nov-25 12:30 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
10.1 |  | EXIT TOP FRAME | Subtask |  | 1d | 120d |  |  | IP | YES | [5 empty] | 17h | 17h | 128d5h |  |  | 16-Aug-25 01:00 AM | 16-Aug-25 09:00 PM |  | 23-Mar-26 09:00 PM | 03-Nov-25 12:30 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
10.1.1 |  | Release of PO | step |  |  |  |  | 10.1.2
10.1.1.1 |  | AIA2400802-OIL SEAL-ID240XOD270X15 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.2 |  | BEARING BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.3 |  | STOPPER PLATE 150 x 90 x 20 MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.4 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.5 |  | END COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.6 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.7 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.8 |  | GEARBOX 55KW,RATIO-153.086:1,H4N 500 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.9 |  | SPROCKET SHAFT 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.10 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.11 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.12 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.13 |  | COUPLING AHG-110 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.14 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.15 |  | COUPLING AHG-110 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.16 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.17 |  | CHAQUERD PLATE 3000X1250X6 | date |  | 10d |  |  |  | IP | YES | [5 empty] | 17h |  | 119d16h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  | 23-Mar-26 09:00 PM | 12-Nov-25 12:08 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.18 |  | GEARBOX SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.19 |  | AHG-104 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d17h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 18-Dec-25 10:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.20 |  | MOTOR SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.21 |  | MOTOR SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.22 |  | MOTOR SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 05:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.23 |  | SPROCKET SHAFT 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.24 |  | SPOCKET KEY 50 X 28 X 285 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d17h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 18-Dec-25 10:41 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.25 |  | COUPLING KEY 50 X 28 X 170 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d17h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 18-Dec-25 10:46 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.26 |  | SPOCKET KEY 50 X 28 X 105 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d17h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 18-Dec-25 10:46 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.27 |  | TOP FRAME FAB. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.28 |  | BRAKE STAND | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.29 |  | SLING PULLEY BLOCK ASSY | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.30 |  | LIFTING FORK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.31 |  | MOTOR-FRAME (M2BAX 315SMA8) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.32 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.34 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.35 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.37 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.40 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M42 x 130 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.43 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.44 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.45 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.46 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.47 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.48 |  | Plain Washer (Type A) IS 2016 - 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.49 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.50 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.51 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.52 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.53 |  | Spring Lock Washer IS 3063 - 42-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.54 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.55 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.56 |  | Spring Lock Washer IS 6735 - 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.57 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 04:48 PM | 11-Nov-25 05:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.58 |  | NUT M80X6-DEL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.59 |  | SKF_23044 CC_W33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d16h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.60 |  | STOPPER 10X10X50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.61 |  | STOPPER 20X20X100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.1.62 |  | YD-SPKT-250-01-00-000 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2 |  | Ready for Assy | step |  |  |  | 10.1.1
10.1.2.1 |  | AIA2400802-OIL SEAL-ID240XOD270X15 THK. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d6h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 03-Mar-26 01:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.2 |  | BEARING BLOCK | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.3 |  | STOPPER PLATE 150 x 90 x 20 MM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.4 |  | RETAINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.5 |  | END COVER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.6 |  | RETAINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.7 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.8 |  | GEARBOX 55KW,RATIO-153.086:1,H4N 500 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.9 |  | SPROCKET SHAFT 1 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.10 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.11 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.12 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.13 |  | COUPLING AHG-110 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 51d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 07-Jan-26 12:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.14 |  | TIE ROD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.15 |  | COUPLING AHG-110 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 51d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 07-Jan-26 12:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.16 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.17 |  | CHAQUERD PLATE 3000X1250X6 | date |  | 110d |  |  |  | IP | NO | [5 empty] | 1d |  | 120d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  | 23-Mar-26 09:00 PM | 12-Nov-25 12:08 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.18 |  | GEARBOX SHIM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 05:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.19 |  | AHG-104 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 51d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 07-Jan-26 12:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.20 |  | MOTOR SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.21 |  | MOTOR SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.22 |  | MOTOR SHIM | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 05:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.23 |  | SPROCKET SHAFT 2 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.24 |  | SPOCKET KEY 50 X 28 X 285 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 45d13h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 01-Jan-26 10:02 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.25 |  | COUPLING KEY 50 X 28 X 170 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 45d13h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 01-Jan-26 10:02 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.26 |  | SPOCKET KEY 50 X 28 X 105 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 45d13h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 01-Jan-26 10:02 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.27 |  | TOP FRAME FAB. | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.28 |  | BRAKE STAND | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.29 |  | SLING PULLEY BLOCK ASSY | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.30 |  | LIFTING FORK | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.31 |  | MOTOR-FRAME (M2BAX 315SMA8) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d6h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 03-Mar-26 01:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.32 |  | GREASE NIPPLE 1/8" BSP | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.34 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.35 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.37 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.40 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 80 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 90 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M42 x 130 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.43 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.44 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.45 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.46 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.47 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.48 |  | Plain Washer (Type A) IS 2016 - 45 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.49 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.50 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.51 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.52 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.53 |  | Spring Lock Washer IS 3063 - 42-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.54 |  | Spring Lock Washer IS 6735 - 16 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.55 |  | Spring Lock Washer IS 6735 - 24 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.56 |  | Spring Lock Washer IS 6735 - 30 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.57 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 110d |  |  |  | IP | YES | [5 empty] | 17h |  | 119d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  | 23-Mar-26 09:00 PM | 12-Nov-25 12:08 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.58 |  | NUT M80X6-DEL | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.59 |  | SKF_23044 CC_W33 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 05:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.60 |  | STOPPER 10X10X50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.61 |  | STOPPER 20X20X100 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 14-Nov-25 04:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.1.2.62 |  | YD-SPKT-250-01-00-000 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:08 PM | 08-Dec-25 04:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2 |  | EXIT FIX FRAME | Subtask |  | 1d | 120d |  |  | IP | YES | [5 empty] | 1d |  | 120d14h |  |  | 16-Aug-25 01:00 AM | 16-Aug-25 09:00 PM |  | 24-Mar-26 02:25 AM | 11-Nov-25 04:07 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
10.2.1 |  | Release of PO | step |  |  |  |  | 10.2.2
10.2.1.1 |  | BEARING,SPHERICAL,22216 E(SPHERICAL ROLLER BEARING DR 80IDx140ODx33THK) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.2 |  | EXIT ACCUMULATOR ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.3 |  | COVER PLATE Ø230 x 15 MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 14-Nov-25 04:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.4 |  | BELLEVILLE SPRING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.5 |  | FIXED FRAME FABRICATION | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.6 |  | FEMALE BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 14-Nov-25 04:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.7 |  | MALE BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 14-Nov-25 04:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.8 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 14-Nov-25 04:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.9 |  | OIL SEAL-90ID x 110OD x 10THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 14-Nov-25 04:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.10 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.11 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.13 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.14 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.15 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.17 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 110 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.18 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.19 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M12-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.20 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.21 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.22 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.23 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.24 |  | Socket Head Cap Screw IS 2269 - M12 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.25 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.26 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.27 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.28 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.29 |  | Spring Lock Washer IS 6735 - 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.30 |  | Clevis Pin IS 6862 - 10 x 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.31 |  | RETAINER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 04:08 PM | 11-Nov-25 05:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.32 |  | RETAINER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 04:08 PM | 11-Nov-25 05:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.33 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 04:08 PM | 11-Nov-25 05:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.34 |  | END COVER LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 04:08 PM | 11-Nov-25 05:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.35 |  | END COVER RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 04:08 PM | 11-Nov-25 05:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.1.36 |  | BEARING HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 04:08 PM | 11-Nov-25 05:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2 |  | Ready for Assy | step |  |  |  | 10.2.1
10.2.2.1 |  | BEARING,SPHERICAL,22216 E(SPHERICAL ROLLER BEARING DR 80IDx140ODx33THK) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 08-Dec-25 04:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.2 |  | EXIT ACCUMULATOR ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 14-Nov-25 04:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.3 |  | COVER PLATE Ø230 x 15 MM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 08-Dec-25 04:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.4 |  | BELLEVILLE SPRING | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d6h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 03-Mar-26 01:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.5 |  | FIXED FRAME FABRICATION | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.6 |  | FEMALE BLOCK | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 08-Dec-25 04:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.7 |  | MALE BLOCK | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 08-Dec-25 04:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.8 |  | BASE FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 08-Dec-25 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.9 |  | OIL SEAL-90ID x 110OD x 10THK | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d6h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 03-Mar-26 01:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.10 |  | GREASE NIPPLE 1/8" BSP | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.11 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.13 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.14 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 65 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.15 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.17 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 110 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.18 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.19 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M12-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.20 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.21 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.22 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.23 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.24 |  | Socket Head Cap Screw IS 2269 - M12 x 90 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.25 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.26 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.27 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.28 |  | Spring Lock Washer IS 6735 - 12 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.29 |  | Spring Lock Washer IS 6735 - 30 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.30 |  | Clevis Pin IS 6862 - 10 x 20-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:56 AM | 12-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.31 |  | RETAINER-RH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 04:08 PM | 12-Nov-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.32 |  | RETAINER-LH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 04:08 PM | 12-Nov-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.33 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 04:08 PM | 12-Nov-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.34 |  | END COVER LH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 04:08 PM | 12-Nov-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.35 |  | END COVER RH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 04:08 PM | 12-Nov-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.2.2.36 |  | BEARING HOUSING | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 04:08 PM | 12-Nov-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3 |  | EXIT MOVING FRAME | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 1d |  | 128d6h |  |  | 16-Aug-25 01:00 AM | 25-Dec-25 02:00 PM |  | 24-Mar-26 02:25 AM | 03-Nov-25 12:30 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
10.3.1 |  | Release of PO | step |  |  |  |  | 10.3.2
10.3.1.1 |  | BEARING,SPHERICAL,22216 E(SPHERICAL ROLLER BEARING DR 80IDx140ODx33THK) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:00 PM | 12-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.2 |  | EXIT ACCUMULATOR ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:00 PM | 12-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.3 |  | WHEEL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 14-Nov-25 04:33 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.4 |  | WHEEL PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 14-Nov-25 04:33 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.5 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 14-Nov-25 04:33 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.6 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d16h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 05:33 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.7 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 14-Nov-25 04:33 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.8 |  | SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:38 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.9 |  | LIFTING FORK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 14-Nov-25 04:33 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.10 |  | MOVING FRAME FAB. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.11 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 14-Nov-25 04:33 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.12 |  | LIFTING FORK ASSY | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 14-Nov-25 04:33 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.13 |  | OIL SEAL-90ID x 110OD x 10THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 14-Nov-25 04:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.14 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.15 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.17 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.18 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.20 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.22 |  | Hexagon Flange Nut IS 15581 - M12-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.23 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.24 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.25 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.26 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.27 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.28 |  | Socket Head Cap Screw IS 2269 - M12 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.29 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.30 |  | Spring Lock Washer IS 3063 - 12-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.31 |  | Spring Lock Washer IS 3063 - 20-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.32 |  | Spring Lock Washer IS 3063 - 24-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.33 |  | Clevis Pin IS 6862 - 10 x 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.34 |  | NUT M80X6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:03 PM | 12-Nov-25 01:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.35 |  | RETAINER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 04:09 PM | 11-Nov-25 05:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.36 |  | RETAINER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 04:09 PM | 11-Nov-25 05:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.37 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 04:09 PM | 11-Nov-25 05:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.38 |  | END COVER LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 04:09 PM | 11-Nov-25 05:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.39 |  | END COVER RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 04:09 PM | 11-Nov-25 05:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.1.40 |  | BEARING HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 04:09 PM | 11-Nov-25 05:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2 |  | Ready for Assy | step |  |  |  | 10.3.1
10.3.2.1 |  | BEARING,SPHERICAL,22216 E(SPHERICAL ROLLER BEARING DR 80IDx140ODx33THK) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:00 PM | 12-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.2 |  | EXIT ACCUMULATOR ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:00 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.3 |  | WHEEL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.4 |  | WHEEL PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.5 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.6 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 18-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.7 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.8 |  | SHIM | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:38 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.9 |  | LIFTING FORK | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.10 |  | MOVING FRAME FAB. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 05:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.11 |  | BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.12 |  | LIFTING FORK ASSY | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.13 |  | OIL SEAL-90ID x 110OD x 10THK | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d6h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 03-Mar-26 01:28 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.14 |  | GREASE NIPPLE 1/8" BSP | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.15 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.17 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 60 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.18 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 65 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.20 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.22 |  | Hexagon Flange Nut IS 15581 - M12-N | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.23 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.24 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.25 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.26 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.27 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.28 |  | Socket Head Cap Screw IS 2269 - M12 x 100 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.29 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.30 |  | Spring Lock Washer IS 3063 - 12-B | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.31 |  | Spring Lock Washer IS 3063 - 20-B | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.32 |  | Spring Lock Washer IS 3063 - 24-B | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.33 |  | Clevis Pin IS 6862 - 10 x 30-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.34 |  | NUT M80X6 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:03 PM | 08-Dec-25 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.35 |  | RETAINER-RH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 04:09 PM | 12-Nov-25 12:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.36 |  | RETAINER-LH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 04:09 PM | 12-Nov-25 12:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.37 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 04:09 PM | 12-Nov-25 12:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.38 |  | END COVER LH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 04:09 PM | 12-Nov-25 12:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.39 |  | END COVER RH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 04:09 PM | 12-Nov-25 12:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.3.2.40 |  | BEARING HOUSING | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 04:09 PM | 12-Nov-25 12:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4 |  | EXIT COUNTER WEIGHT | Subtask |  | 1d | 120d |  |  | IP | YES | [5 empty] | 1d17h | 1d17h | 129d5h |  |  | 16-Aug-25 01:00 AM | 16-Aug-25 09:00 PM |  | 24-Mar-26 09:00 PM | 03-Nov-25 12:30 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
10.4.1 |  | Release of PO | step |  |  |  |  | 10.4.2
10.4.1.1 |  | OILSEAL-156x186x15 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.2 |  | SPHERICAL ROLLER BRG D 140IDx250ODx68THK. mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d16h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 08-Dec-25 05:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.3 |  | BEARING BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.4 |  | SPROCKET SHAFT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.5 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.6 |  | END COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.7 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.8 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.9 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.10 |  | COUNTER WEIGHT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d15h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 12-Dec-25 04:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.11 |  | COUNTER WEIGHT COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d15h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 12-Dec-25 04:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.12 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.13 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.14 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.15 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.17 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.18 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.19 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.20 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.21 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.22 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.23 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.24 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.1.25 |  | SPROCKET 2.5 INCH 25 TEETH | date |  | 10d |  |  |  | IP | YES | [5 empty] | 17h |  | 119d16h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  | 23-Mar-26 09:00 PM | 12-Nov-25 12:05 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2 |  | Ready for Assy | step |  |  |  | 10.4.1
10.4.2.1 |  | OILSEAL-156x186x15 | date |  | 110d |  |  |  | IP | YES | [5 empty] | 17h |  | 119d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  | 23-Mar-26 09:00 PM | 12-Nov-25 12:05 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.2 |  | SPHERICAL ROLLER BRG D 140IDx250ODx68THK. mm | date |  | 110d |  |  |  | IP | YES | [5 empty] | 17h |  | 119d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  | 23-Mar-26 09:00 PM | 12-Nov-25 12:05 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.3 |  | BEARING BLOCK | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 08-Dec-25 05:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.4 |  | SPROCKET SHAFT | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 08-Dec-25 05:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.5 |  | RETAINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 08-Dec-25 05:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.6 |  | END COVER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 08-Dec-25 05:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.7 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 08-Dec-25 05:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.8 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 08-Dec-25 05:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.9 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 23d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 08-Dec-25 05:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.10 |  | COUNTER WEIGHT | date |  | 110d |  |  |  | IP | YES | [5 empty] | 17h |  | 119d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  | 23-Mar-26 09:00 PM | 12-Nov-25 12:05 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.11 |  | COUNTER WEIGHT COVER | date |  | 110d |  |  |  | IP | YES | [5 empty] | 17h |  | 119d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  | 23-Mar-26 09:00 PM | 12-Nov-25 12:05 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.12 |  | GREASE NIPPLE 1/8" BSP | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.13 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.14 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.15 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x100 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.17 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.18 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.19 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.20 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.21 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.22 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.23 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.24 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 2d5h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 12:05 PM | 14-Nov-25 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
10.4.2.25 |  | SPROCKET 2.5 INCH 25 TEETH | date |  | 110d |  |  |  | IP | NO | [5 empty] | 1d |  | 120d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  | 24-Mar-26 09:00 PM | 12-Nov-25 12:05 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11 | 72 | Category 2 - BRIDLE ROLL ASSY. - Ordering & Manufacturing | TASK |  | 120d | 120d | 20 | 55 | CO | YES | [7 empty] | 105d9h |  |  | 16-Aug-25 01:00 AM | 25-Dec-25 02:00 PM |  |  | 03-Nov-25 01:01 PM | 26-Feb-26 05:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
11.1 |  | BRIDLE ROLL ASSY.#1 | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 69d10h |  |  | 16-Aug-25 01:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Dec-25 10:36 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
11.1.1 |  | Release of PO | step |  |  |  |  | 11.1.2
11.1.1.1 |  | BRIDLE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 09:51 AM | 13-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.2 |  | BRIDLE SNUBBER ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 09:51 AM | 13-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.3 |  | MAIN FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 09:51 AM | 13-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.4 |  | MOTOR AND GEARBOX FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 09:51 AM | 13-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.5 |  | BRAKE STAND- 1A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 01:29 PM | 17-Dec-25 02:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.6 |  | ARM FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 01:29 PM | 17-Dec-25 02:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.7 |  | ARM CLEVIS- RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 01:29 PM | 17-Dec-25 02:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.8 |  | ARM CLEVIS- LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 01:29 PM | 17-Dec-25 02:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.9 |  | ARM FRAME- 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 01:29 PM | 17-Dec-25 02:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.10 |  | CYL. CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 01:29 PM | 17-Dec-25 02:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.11 |  | ARM FRAME- 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 01:29 PM | 17-Dec-25 02:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.12 |  | BRAKE STAND- 1B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 01:29 PM | 17-Dec-25 02:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.13 |  | CHAIN COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 12:05 PM | 19-Dec-25 01:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.14 |  | DUPLEX CHAIN (12B2), ROLLER DIA 12.07mm, PITCH 0.75'' (1150mm LONG), (60 NOS. LINKS), MAKE- RENOLD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 12:51 PM | 19-Dec-25 01:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.15 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 09:51 AM | 13-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.16 |  | CYL. CLEVIS PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 02:48 PM | 17-Dec-25 03:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.17 |  | SPACER- 01 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 02:48 PM | 17-Dec-25 03:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.18 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 02:48 PM | 17-Dec-25 03:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.19 |  | ARM PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 02:48 PM | 17-Dec-25 03:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.20 |  | LOCKING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 02:48 PM | 17-Dec-25 03:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.21 |  | PIN HOLDER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 02:48 PM | 17-Dec-25 03:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.22 |  | ADJUSTING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 02:18 PM | 17-Dec-25 03:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.23 |  | COUPLING- 1A, FULL GEAR, AFG-105 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:18 AM | 13-Dec-25 11:18 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.24 |  | COUPLING- 1B, FULL GEAR, AFG-105 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:18 AM | 13-Dec-25 11:18 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.25 |  | COUPLING- 1A,HALF GEAR, AHG-102 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 09:56 AM | 13-Dec-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.26 |  | COUPLING- 1B,HALF GEAR, AHG-102 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 09:56 AM | 13-Dec-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.27 |  | GEAR BOX SHIM- 1A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 09:57 AM | 13-Dec-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.28 |  | GEAR BOX SHIM- 1B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 09:57 AM | 13-Dec-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.29 |  | MOTOR SHIM- 1A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 09:57 AM | 13-Dec-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.30 |  | MOTOR SHIM- 1B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 09:57 AM | 13-Dec-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.31 |  | SPACER- 02 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 02:16 PM | 17-Dec-25 03:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.32 |  | SPACER- 03 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 02:16 PM | 17-Dec-25 03:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.33 |  | END PLATE (ROLL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 02:16 PM | 17-Dec-25 03:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.34 |  | END PLATE (GEAREDMOTOR) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 02:16 PM | 17-Dec-25 03:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.35 |  | GEAR BOX SPROCKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 01:29 PM | 17-Dec-25 02:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.36 |  | ROLL SPROCKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 01:29 PM | 17-Dec-25 02:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.37 |  | SPACER - 04 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 01:29 PM | 17-Dec-25 02:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.38 |  | SPACER- 05 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 01:29 PM | 17-Dec-25 02:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.39 |  | GEARED MOTOR- 1.5KW,1500RPM,4 POLE, RATIO-25.51:1, MODEL-M062222, MAKE- PBL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 11:50 AM | 19-Dec-25 12:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.40 |  | BRIDLE 1A, GEARBOX RATIO- 11.059, MECH (P) 15KW | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:15 AM | 13-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.41 |  | BRIDLE- 1B, GEARBOX RATIO- 11.33, MECH (P) 11KW | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:15 AM | 13-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.42 |  | 15KW, 6 POLE, 1000 RPM,FOOT MOUNTING, FRAME SIZE- ND180L, MAKE- CG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:15 AM | 13-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.43 |  | 11KW, 6 POLE, 1000 RPM,FOOT MOUNTING, FRAME SIZE-ND160L, MAKE- CG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:15 AM | 13-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.44 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 02:50 PM | 17-Dec-25 03:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.45 |  | BEARING,SPHERICAL,22222E/C3 (SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:15 AM | 13-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.46 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:15 AM | 13-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.47 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:15 AM | 13-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.48 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:15 AM | 13-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.49 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:15 AM | 13-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.50 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.51 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.52 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.53 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.54 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.55 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.58 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.59 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.60 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.61 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.62 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.63 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.64 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.65 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.66 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.67 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.68 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.69 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.70 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.71 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.72 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.1.73 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2 |  | Ready for Assy | step |  |  |  | 11.1.1
11.1.2.1 |  | BRIDLE ROLL | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 09:51 AM | 13-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.2 |  | BRIDLE SNUBBER ROLL | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 09:51 AM | 13-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.3 |  | MAIN FRAME | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 09:51 AM | 13-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.4 |  | MOTOR AND GEARBOX FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 68d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 09:51 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.5 |  | BRAKE STAND- 1A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 01:29 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.6 |  | ARM FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 01:29 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.7 |  | ARM CLEVIS- RH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 01:29 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.8 |  | ARM CLEVIS- LH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 01:29 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.9 |  | ARM FRAME- 1 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 01:29 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.10 |  | CYL. CLEVIS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 01:29 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.11 |  | ARM FRAME- 2 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 01:29 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.12 |  | BRAKE STAND- 1B | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 01:29 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.13 |  | CHAIN COVER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 12:05 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.14 |  | DUPLEX CHAIN (12B2), ROLLER DIA 12.07mm, PITCH 0.75'' (1150mm LONG), (60 NOS. LINKS), MAKE- RENOLD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 12:51 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.15 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d8h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 09:51 AM | 19-Dec-25 12:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.16 |  | CYL. CLEVIS PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 02:48 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.17 |  | SPACER- 01 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 02:48 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.18 |  | KEEPER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 02:48 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.19 |  | ARM PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 02:48 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.20 |  | LOCKING PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 02:48 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.21 |  | PIN HOLDER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 02:48 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.22 |  | ADJUSTING PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 02:18 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.23 |  | COUPLING- 1A, FULL GEAR, AFG-105 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:18 AM | 13-Dec-25 11:18 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.24 |  | COUPLING- 1B, FULL GEAR, AFG-105 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:18 AM | 13-Dec-25 11:18 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.25 |  | COUPLING- 1A,HALF GEAR, AHG-102 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 09:56 AM | 13-Dec-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.26 |  | COUPLING- 1B,HALF GEAR, AHG-102 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 09:56 AM | 13-Dec-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.27 |  | GEAR BOX SHIM- 1A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 09:57 AM | 13-Dec-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.28 |  | GEAR BOX SHIM- 1B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 09:57 AM | 13-Dec-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.29 |  | MOTOR SHIM- 1A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 09:57 AM | 13-Dec-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.30 |  | MOTOR SHIM- 1B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 09:57 AM | 13-Dec-25 10:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.31 |  | SPACER- 02 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 02:16 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.32 |  | SPACER- 03 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 02:16 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.33 |  | END PLATE (ROLL) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 02:16 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.34 |  | END PLATE (GEAREDMOTOR) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 02:16 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.35 |  | GEAR BOX SPROCKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 01:29 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.36 |  | ROLL SPROCKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 01:29 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.37 |  | SPACER - 04 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 01:29 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.38 |  | SPACER- 05 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 01:29 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.39 |  | GEARED MOTOR- 1.5KW,1500RPM,4 POLE, RATIO-25.51:1, MODEL-M062222, MAKE- PBL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 11:50 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.40 |  | BRIDLE 1A, GEARBOX RATIO- 11.059, MECH (P) 15KW | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:15 AM | 13-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.41 |  | BRIDLE- 1B, GEARBOX RATIO- 11.33, MECH (P) 11KW | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:15 AM | 13-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.42 |  | 15KW, 6 POLE, 1000 RPM,FOOT MOUNTING, FRAME SIZE- ND180L, MAKE- CG | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 68d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:15 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.43 |  | 11KW, 6 POLE, 1000 RPM,FOOT MOUNTING, FRAME SIZE-ND160L, MAKE- CG | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 68d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:15 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.44 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 65d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 02:50 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.1.2.45 |  | BEARING,SPHERICAL,22222E/C3 (SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:15 AM | 13-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.46 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:15 AM | 13-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.47 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:15 AM | 13-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.48 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:15 AM | 13-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.49 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:15 AM | 13-Dec-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.50 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.51 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.52 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.53 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.54 |  | SHEAR BIOCK- 10x10x50mm | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.55 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.58 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.59 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.60 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.61 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.62 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.63 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.64 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.65 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.66 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.67 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.68 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.69 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.70 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.71 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.72 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.1.2.73 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:17 AM | 13-Dec-25 11:17 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2 |  | BRIDLE ROLL ASSY.#2 | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 97d13h |  |  | 16-Aug-25 01:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:55 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
11.2.1 |  | Release of PO | step |  |  |  |  | 11.2.2
11.2.1.1 |  | BRIDLE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.2 |  | BRIDLE SNUBBER ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.3 |  | MAIN FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.4 |  | MOTOR AND GEARBOX FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 09-Dec-25 09:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.5 |  | ARM FRAME- 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.6 |  | ARM CLEVIS- RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.7 |  | ARM CLEVIS- LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.8 |  | ARM FRAME- 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.9 |  | ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.10 |  | CYL. CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.11 |  | BRAKE STAND | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.12 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d10h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 12-Dec-25 10:39 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.13 |  | CYL. CLEVIS PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.14 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.15 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.16 |  | ARM PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.17 |  | LOCKING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.18 |  | PIN HOLDER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.19 |  | ADJUSTING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.20 |  | COUPLING, FULL GEAR, AFG-105 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.21 |  | SPACER- 01 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.22 |  | COUPLING,HALF GEAR, AHG-102 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.23 |  | SPACER- 03 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.24 |  | GEAR BOX SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.25 |  | MOTOR SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.26 |  | BRIDLE 2A, GEARBOX RATIO- 11.365, MECH (P) 15KW @1500RPM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.27 |  | BRIDLE 2B, GEARBOX RATIO- 11.365, MECH (P) 15KW @1500RPM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.28 |  | 15KW, 4 POLE, 1500 RPM,FOOT MOUNTING FRAME SIZE-ND160L | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 12-Nov-25 12:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.29 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:15 AM | 18-Nov-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.30 |  | BEARING,SPHERICAL,22222E/C3(SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.31 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.32 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.33 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.34 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.35 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.36 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.37 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.38 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.39 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.40 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.43 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.44 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.45 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.46 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.50 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.51 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.52 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.54 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.55 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.1.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:56 PM | 11-Nov-25 07:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2 |  | Ready for Assy | step |  |  |  | 11.2.1
11.2.2.1 |  | BRIDLE ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:19 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.2 |  | BRIDLE SNUBBER ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.3 |  | MAIN FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:19 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.4 |  | MOTOR AND GEARBOX FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.2.2.5 |  | ARM FRAME- 2 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.6 |  | ARM CLEVIS- RH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.7 |  | ARM CLEVIS- LH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.8 |  | ARM FRAME- 1 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.9 |  | ARM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.10 |  | CYL. CLEVIS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.11 |  | BRAKE STAND | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.12 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.13 |  | CYL. CLEVIS PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.14 |  | TIE ROD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.15 |  | KEEPER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.16 |  | ARM PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.17 |  | LOCKING PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.18 |  | PIN HOLDER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.19 |  | ADJUSTING PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.20 |  | COUPLING, FULL GEAR, AFG-105 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.21 |  | SPACER- 01 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.22 |  | COUPLING,HALF GEAR, AHG-102 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.23 |  | SPACER- 03 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.24 |  | GEAR BOX SHIM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.25 |  | MOTOR SHIM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.26 |  | BRIDLE 2A, GEARBOX RATIO- 11.365, MECH (P) 15KW @1500RPM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 12h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 12-Nov-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.27 |  | BRIDLE 2B, GEARBOX RATIO- 11.365, MECH (P) 15KW @1500RPM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 12h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 12-Nov-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.28 |  | 15KW, 4 POLE, 1500 RPM,FOOT MOUNTING FRAME SIZE-ND160L | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.2.2.29 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:15 AM | 17-Dec-25 02:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.30 |  | BEARING,SPHERICAL,22222E/C3(SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 12h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 12-Nov-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.31 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 17-Dec-25 02:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.32 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 17-Dec-25 02:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.33 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 17-Dec-25 02:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.34 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 17-Dec-25 02:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.35 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.36 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.37 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 12h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 12-Nov-25 11:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.38 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.39 |  | SHEAR BIOCK- 10x10x50mm | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.40 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.43 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.44 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.45 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.46 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.50 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.51 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.52 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.54 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.55 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.2.2.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:56 PM | 09-Dec-25 09:23 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3 |  | BRIDLE ROLL ASSY.#3 | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 97d13h |  |  | 16-Aug-25 01:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:55 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
11.3.1 |  | Release of PO | step |  |  |  |  | 11.3.2
11.3.1.1 |  | BRIDLE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:59 PM | 11-Nov-25 07:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.2 |  | BRIDLE SNUBBER ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.3 |  | MAIN FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:59 PM | 11-Nov-25 07:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.4 |  | MOTOR AND GEARBOX FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 09-Dec-25 10:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.5 |  | ARM FRAME- 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.6 |  | ARM CLEVIS- RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.7 |  | ARM CLEVIS- LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.8 |  | ARM FRAME- 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.9 |  | ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.10 |  | CYL. CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.11 |  | BRAKE STAND | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.12 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 17-Dec-25 03:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.13 |  | CYL. CLEVIS PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.14 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.15 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.16 |  | ARM PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.17 |  | LOCKING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.18 |  | PIN HOLDER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.19 |  | ADJUSTING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.20 |  | COUPLING, FULL GEAR, AFG-105 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:59 PM | 11-Nov-25 07:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.21 |  | SPACER- 01 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.22 |  | COUPLING,HALF GEAR, AHG-102 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:59 PM | 11-Nov-25 07:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.23 |  | SPACER- 03 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.24 |  | GEAR BOX SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.25 |  | MOTOR SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.26 |  | BRIDLE 3B, GEARBOX RATIO- 14.4, MECH (P) 15KW @1500RPM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:59 PM | 11-Nov-25 07:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.27 |  | BRIDLE-3A, GEARBOX RATIO- 14.4, MECH (P) 15KW @1500RPM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:59 PM | 11-Nov-25 07:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.28 |  | 15KW, 4 POLE, 1500 RPM,FOOT MOUNTING FRAME SIZE-ND160L | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.29 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 18-Nov-25 11:45 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.30 |  | BEARING,SPHERICAL,22222E/C3(SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:59 PM | 11-Nov-25 07:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.31 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:59 PM | 11-Nov-25 07:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.32 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:59 PM | 11-Nov-25 07:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.33 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:59 PM | 11-Nov-25 07:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.34 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:59 PM | 11-Nov-25 07:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.35 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:59 PM | 11-Nov-25 07:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.36 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:59 PM | 11-Nov-25 07:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.37 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 06:59 PM | 11-Nov-25 07:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.38 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.39 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.40 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.43 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.44 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.45 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.46 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.50 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.51 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.52 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.54 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.55 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.1.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 11:19 AM | 12-Nov-25 12:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2 |  | Ready for Assy | step |  |  |  | 11.3.1
11.3.2.1 |  | BRIDLE ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d4h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:59 PM | 09-Dec-25 10:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.2 |  | BRIDLE SNUBBER ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.3 |  | MAIN FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d4h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:59 PM | 09-Dec-25 10:36 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.4 |  | MOTOR AND GEARBOX FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.3.2.5 |  | ARM FRAME- 2 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.6 |  | ARM CLEVIS- RH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.7 |  | ARM CLEVIS- LH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.8 |  | ARM FRAME- 1 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.9 |  | ARM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.10 |  | CYL. CLEVIS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.11 |  | BRAKE STAND | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.12 |  | BUSH | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.13 |  | CYL. CLEVIS PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.14 |  | TIE ROD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.15 |  | KEEPER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.16 |  | ARM PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.17 |  | LOCKING PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.18 |  | PIN HOLDER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.19 |  | ADJUSTING PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.20 |  | COUPLING, FULL GEAR, AFG-105 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d4h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:59 PM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.21 |  | SPACER- 01 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.22 |  | COUPLING,HALF GEAR, AHG-102 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d4h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:59 PM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.23 |  | SPACER- 03 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.24 |  | GEAR BOX SHIM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.25 |  | MOTOR SHIM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.26 |  | BRIDLE 3B, GEARBOX RATIO- 14.4, MECH (P) 15KW @1500RPM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 12h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:59 PM | 12-Nov-25 11:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.27 |  | BRIDLE-3A, GEARBOX RATIO- 14.4, MECH (P) 15KW @1500RPM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 12h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:59 PM | 12-Nov-25 11:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.28 |  | 15KW, 4 POLE, 1500 RPM,FOOT MOUNTING FRAME SIZE-ND160L | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.3.2.29 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:20 AM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.30 |  | BEARING,SPHERICAL,22222E/C3(SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 12h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:59 PM | 12-Nov-25 11:20 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.31 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:59 PM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.32 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:59 PM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.33 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:59 PM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.34 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:59 PM | 17-Dec-25 03:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.35 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d4h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:59 PM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.36 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d4h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:59 PM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.37 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d4h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 06:59 PM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.38 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.39 |  | SHEAR BIOCK- 10x10x50mm | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.40 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.43 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.44 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.45 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.46 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.50 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.51 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.52 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.54 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.55 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.3.2.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 24d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Nov-25 11:21 AM | 09-Dec-25 10:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4 |  | BRIDLE ROLL ASSY.#4 | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 97d13h |  |  | 16-Aug-25 01:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:00 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
11.4.1 |  | Release of PO | step |  |  |  |  | 11.4.2
11.4.1.1 |  | BRIDLE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:01 PM | 11-Nov-25 08:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.2 |  | BRIDLE SNUBBER ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:58 AM | 18-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.3 |  | MAIN FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:01 PM | 11-Nov-25 08:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.4 |  | MOTOR AND GEARBOX FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 21d8h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 09-Dec-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.5 |  | ARM FRAME- 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 18-Nov-25 11:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.6 |  | ARM CLEVIS- RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 18-Nov-25 11:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.7 |  | ARM CLEVIS- LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 18-Nov-25 11:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.8 |  | ARM FRAME- 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 18-Nov-25 11:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.9 |  | ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 18-Nov-25 11:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.10 |  | CYL. CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 18-Nov-25 11:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.11 |  | BRAKE STAND | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 18-Nov-25 11:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.12 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.13 |  | CYL. CLEVIS PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 18-Nov-25 11:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.14 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 18-Nov-25 11:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.15 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 18-Nov-25 11:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.16 |  | ARM PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 18-Nov-25 11:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.17 |  | LOCKING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 18-Nov-25 11:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.18 |  | PIN HOLDER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 18-Nov-25 11:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.19 |  | ADJUSTING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 18-Nov-25 11:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.20 |  | COUPLING, FULL GEAR, AFG-105 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:01 PM | 11-Nov-25 08:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.21 |  | SPACER- 01 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 18-Nov-25 11:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.22 |  | COUPLING,HALF GEAR, AHG-102 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:01 PM | 11-Nov-25 08:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.23 |  | SPACER- 02 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 18-Nov-25 11:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.24 |  | GEAR BOX SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 21d8h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 09-Dec-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.25 |  | MOTOR SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 21d8h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:49 PM | 09-Dec-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.26 |  | BRIDLE- 4B, GEARBOX RATIO- 14.4, MECH (P) 15KW @1500RPM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:01 PM | 11-Nov-25 08:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.27 |  | BRIDLE- 4A, GEARBOX RATIO- 14.4, MECH (P) 15KW @1500RPM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:01 PM | 11-Nov-25 08:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.28 |  | 15KW, 4 POLE, 1500 RPM,FOOT MOUNTING, FRAME SIZE-ND160L, MAKE- CG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:48 AM | 09-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.29 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:51 AM | 18-Nov-25 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.30 |  | BEARING,SPHERICAL,22222E/C3(SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:01 PM | 11-Nov-25 08:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.31 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:01 PM | 11-Nov-25 08:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.32 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:01 PM | 11-Nov-25 08:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.33 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:01 PM | 11-Nov-25 08:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.34 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:01 PM | 11-Nov-25 08:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.35 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:01 PM | 11-Nov-25 08:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.36 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:01 PM | 11-Nov-25 08:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.37 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:01 PM | 11-Nov-25 08:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.38 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.39 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.40 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.43 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.44 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.45 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.46 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.50 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.51 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.52 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.54 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.55 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.1.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2 |  | Ready for Assy | step |  |  |  | 11.4.1
11.4.2.1 |  | BRIDLE ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:01 PM | 09-Dec-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.2 |  | BRIDLE SNUBBER ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 26d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:58 AM | 17-Dec-25 03:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.3 |  | MAIN FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:01 PM | 09-Dec-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.4 |  | MOTOR AND GEARBOX FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 93d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.4.2.5 |  | ARM FRAME- 2 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.6 |  | ARM CLEVIS- RH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.7 |  | ARM CLEVIS- LH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.8 |  | ARM FRAME- 1 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.9 |  | ARM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.10 |  | CYL. CLEVIS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.11 |  | BRAKE STAND | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.12 |  | BUSH | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.13 |  | CYL. CLEVIS PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.14 |  | TIE ROD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.15 |  | KEEPER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.16 |  | ARM PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.17 |  | LOCKING PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.18 |  | PIN HOLDER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.19 |  | ADJUSTING PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.20 |  | COUPLING, FULL GEAR, AFG-105 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:01 PM | 09-Dec-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.21 |  | SPACER- 01 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.22 |  | COUPLING,HALF GEAR, AHG-102 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:01 PM | 09-Dec-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.23 |  | SPACER- 02 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 29d |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 17-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.24 |  | GEAR BOX SHIM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 21d8h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 09-Dec-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.25 |  | MOTOR SHIM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 21d8h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:49 PM | 09-Dec-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.26 |  | BRIDLE- 4B, GEARBOX RATIO- 14.4, MECH (P) 15KW @1500RPM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 34d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:01 PM | 19-Dec-25 10:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.27 |  | BRIDLE- 4A, GEARBOX RATIO- 14.4, MECH (P) 15KW @1500RPM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 34d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:01 PM | 19-Dec-25 10:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.28 |  | 15KW, 4 POLE, 1500 RPM,FOOT MOUNTING, FRAME SIZE-ND160L, MAKE- CG | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 72d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:48 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.4.2.29 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 26d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:51 AM | 17-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.30 |  | BEARING,SPHERICAL,22222E/C3(SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:01 PM | 09-Dec-25 10:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.31 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:01 PM | 17-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.32 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:01 PM | 17-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.33 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:01 PM | 17-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.34 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:01 PM | 17-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.35 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:01 PM | 09-Dec-25 10:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.36 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:01 PM | 09-Dec-25 10:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.37 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:01 PM | 09-Dec-25 10:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.38 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.39 |  | SHEAR BIOCK- 10x10x50mm | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.40 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.43 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.44 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.45 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.46 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.50 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.51 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.52 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.54 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.55 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.4.2.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:52 AM | 18-Nov-25 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5 |  | BRIDLE ROLL ASSY.#5 | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 92d8h |  |  | 16-Aug-25 01:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:45 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
11.5.1 |  | Release of PO | step |  |  |  |  | 11.5.2
11.5.1.1 |  | BRIDLE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 17-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.2 |  | BRIDLE SNUBBER ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:29 AM | 18-Nov-25 12:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.3 |  | MAIN FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 17-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.4 |  | MOTOR AND GEARBOX FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 19d17h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 09-Dec-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.5 |  | ARM FRAME- 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 21-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.6 |  | ARM CLEVIS- RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 21-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.7 |  | ARM CLEVIS- LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 21-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.8 |  | ARM FRAME- 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 21-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.9 |  | ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 21-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.10 |  | CYL. CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 21-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.11 |  | BRAKE STAND | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 21-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.12 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.13 |  | CYL. CLEVIS PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 21-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.14 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 21-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.15 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 21-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.16 |  | ARM PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 21-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.17 |  | LOCKING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 21-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.18 |  | PIN HOLDER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 21-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.19 |  | ADJUSTING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 21-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.20 |  | COUPLING- 5B, FULL GEAR, AFG-105 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 17-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.21 |  | SPACER- 01 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 21-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.22 |  | COUPLING- 5B,HALF GEAR, AHG-102 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 17-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.23 |  | SPACER- 02 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 21-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.24 |  | GEAR BOX SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 19d17h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 09-Dec-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.25 |  | MOTOR SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 19d17h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 09-Dec-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.26 |  | COUPLING- 5A, FULL GEAR, AFG-105 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 17-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.27 |  | COUPLING- 5A,HALF GEAR, AHG-102 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 17-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.28 |  | SPACER- 03 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 21-Nov-25 12:58 PM | 21-Nov-25 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.29 |  | GEAR BOX SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:52 PM | 17-Dec-25 04:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.30 |  | 22KW, 6 POLE, 1000 RPM,FOOT MOUNTING FRAME SIZE-ND200L | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:59 AM | 19-Dec-25 11:59 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.31 |  | BRIDLE-5A, GEARBOX RATIO- 13.806, MECH (P) 22KW @1500RPM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:54 PM | 17-Dec-25 04:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.32 |  | BRIDLE 5B, GEARBOX RATIO- 14.175, MECH (P) 30KW @1500RPM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:54 PM | 17-Dec-25 04:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.33 |  | SPACER- 04 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 21-Nov-25 12:58 PM | 21-Nov-25 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.34 |  | 30KW, 6 POLE, 1000 RPM,FOOT MOUNTING FRAME SIZE-ND225L | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 11:32 AM | 09-Dec-25 12:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.35 |  | SPACER- 02 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 21-Nov-25 12:58 PM | 21-Nov-25 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.36 |  | MOTOR SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 11:32 AM | 09-Dec-25 12:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.37 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 21-Nov-25 12:58 PM | 21-Nov-25 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.38 |  | BEARING,SPHERICAL,22222E/C3(SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 17-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.39 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 17-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.40 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 17-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.41 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 17-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.42 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 17-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.43 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 17-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.44 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 17-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.45 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 04:58 PM | 17-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.46 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.47 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.48 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.51 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.52 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.53 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.54 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.58 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.59 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.60 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.61 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.62 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.63 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.64 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.1.65 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2 |  | Ready for Assy | step |  |  |  | 11.5.1
11.5.2.1 |  | BRIDLE ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 11:32 AM | 09-Dec-25 12:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.2 |  | BRIDLE SNUBBER ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 26d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:58 AM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.3 |  | MAIN FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 11:32 AM | 09-Dec-25 12:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.4 |  | MOTOR AND GEARBOX FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 92d8h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.5.2.5 |  | ARM FRAME- 2 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.6 |  | ARM CLEVIS- RH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.7 |  | ARM CLEVIS- LH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.8 |  | ARM FRAME- 1 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.9 |  | ARM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.10 |  | CYL. CLEVIS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.11 |  | BRAKE STAND | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.12 |  | BUSH | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.13 |  | CYL. CLEVIS PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.14 |  | TIE ROD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.15 |  | KEEPER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.16 |  | ARM PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.17 |  | LOCKING PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.18 |  | PIN HOLDER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.19 |  | ADJUSTING PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.20 |  | COUPLING- 5B, FULL GEAR, AFG-105 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 19d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 09-Dec-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.21 |  | SPACER- 01 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.22 |  | COUPLING- 5B,HALF GEAR, AHG-102 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 19d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 09-Dec-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.23 |  | SPACER- 02 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.24 |  | GEAR BOX SHIM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 19d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 09-Dec-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.25 |  | MOTOR SHIM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 19d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 09-Dec-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.26 |  | COUPLING- 5A, FULL GEAR, AFG-105 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.27 |  | COUPLING- 5A,HALF GEAR, AHG-102 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Nov-25 05:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.28 |  | SPACER- 03 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:52 PM | 17-Dec-25 04:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.29 |  | GEAR BOX SHIM | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:52 PM | 17-Dec-25 04:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.30 |  | 22KW, 6 POLE, 1000 RPM,FOOT MOUNTING FRAME SIZE-ND200L | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:59 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.5.2.31 |  | BRIDLE-5A, GEARBOX RATIO- 13.806, MECH (P) 22KW @1500RPM | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:54 PM | 17-Dec-25 04:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.32 |  | BRIDLE 5B, GEARBOX RATIO- 14.175, MECH (P) 30KW @1500RPM | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:54 PM | 17-Dec-25 04:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.33 |  | SPACER- 04 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 7d11h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 11:32 AM | 17-Dec-25 03:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.34 |  | 30KW, 6 POLE, 1000 RPM,FOOT MOUNTING FRAME SIZE-ND225L | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 72d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 11:32 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.5.2.35 |  | SPACER- 02 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 7d11h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 11:32 AM | 17-Dec-25 03:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.36 |  | MOTOR SHIM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 11:32 AM | 09-Dec-25 12:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.37 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.38 |  | BEARING,SPHERICAL,22222E/C3(SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.39 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.40 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.41 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.42 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.43 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.44 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.45 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 27d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 04:58 PM | 17-Dec-25 03:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.46 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.47 |  | SHEAR BIOCK- 10x10x50mm | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.48 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.51 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.52 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.53 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.54 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.58 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.59 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.60 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.61 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.62 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.63 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.64 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.5.2.65 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 03:56 PM | 17-Dec-25 04:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6 |  | BRIDLE ROLL ASSY.#6 (FUTURE PROVISION) | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 92d8h |  |  | 16-Aug-25 01:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Nov-25 05:01 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
11.6.1 |  | Release of PO | step |  |  |  |  | 11.6.2
11.6.1.1 |  | BRIDLE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 05:03 PM | 17-Nov-25 06:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.2 |  | BRIDLE SNUBBER ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:58 AM | 18-Nov-25 12:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.3 |  | MAIN FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 05:03 PM | 17-Nov-25 06:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.4 |  | MOTOR AND GEARBOX FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.5 |  | ARM FRAME- 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.6 |  | ARM CLEVIS- RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.7 |  | ARM CLEVIS- LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.8 |  | ARM FRAME- 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.9 |  | ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.10 |  | CYL. CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.11 |  | BRAKE STAND- 6A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.12 |  | BRAKE STAND- 6B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.13 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.14 |  | CYL. CLEVIS PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.15 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.16 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.17 |  | ARM PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.18 |  | LOCKING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.19 |  | PIN HOLDER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.20 |  | ADJUSTING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.21 |  | COUPLING- 6A, FULL GEAR, AFG-106 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 05:03 PM | 17-Nov-25 06:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.22 |  | COUPLING- 6B, FULL GEAR, AFG-106 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 05:03 PM | 17-Nov-25 06:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.23 |  | COUPLING- 6A,HALF GEAR, AHG-103 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 05:03 PM | 17-Nov-25 06:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.24 |  | COUPLING- 6B ,HALF GEAR, AHG-103 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 05:03 PM | 17-Nov-25 06:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.25 |  | SPACER- 01 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.26 |  | SPACER- 02 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.27 |  | SPACER- 03 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.28 |  | SPACER- 04 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.29 |  | SPACER- 05 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.30 |  | SPACER- 06 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.31 |  | GEAR BOX SHIM- 6A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.32 |  | GEAR BOX SHIM- 6B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.33 |  | MOTOR SHIM- 6A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.34 |  | MOTOR SHIM- 6B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.35 |  | BRIDLE 6A, GEARBOX RATIO- 14.133, MECH (P) 37KW | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.36 |  | BRIDLE 6B, GEARBOX RATIO- 13.922, MECH (P) 55KW | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.37 |  | 37KW, 6 POLE, 1000 RPM,FOOT MOUNTING, FRAME SIZE- ND250M, MAKE- CG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.38 |  | 55KW, 6 POLE, 1000 RPM,FOOT MOUNTING, FRAME SIZE-ND280M, MAKE- CG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.39 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.40 |  | BEARING,SPHERICAL,22222E/C3(SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 05:03 PM | 17-Nov-25 06:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.41 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 05:03 PM | 17-Nov-25 06:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.42 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 05:03 PM | 17-Nov-25 06:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.43 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 05:03 PM | 17-Nov-25 06:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.44 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 05:03 PM | 17-Nov-25 06:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.45 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 05:03 PM | 17-Nov-25 06:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.46 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 05:03 PM | 17-Nov-25 06:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.47 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 17-Nov-25 05:03 PM | 17-Nov-25 06:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.48 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.49 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.50 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.53 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.54 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.55 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.56 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.59 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.60 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.61 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.62 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.63 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.64 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.65 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.66 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.67 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.68 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.69 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.1.70 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2 |  | Ready for Assy | step |  |  |  | 11.6.1
11.6.2.1 |  | BRIDLE ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.2 |  | BRIDLE SNUBBER ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 26d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:58 AM | 17-Dec-25 04:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.3 |  | MAIN FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.4 |  | MOTOR AND GEARBOX FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 19-Dec-25 11:30 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.5 |  | ARM FRAME- 1 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.6 |  | ARM CLEVIS- RH | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.7 |  | ARM CLEVIS- LH | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.8 |  | ARM FRAME- 2 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.9 |  | ARM | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.10 |  | CYL. CLEVIS | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.11 |  | BRAKE STAND- 6A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.12 |  | BRAKE STAND- 6B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.13 |  | BUSH | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.14 |  | CYL. CLEVIS PIN | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.15 |  | TIE ROD | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.16 |  | KEEPER PLATE | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.17 |  | ARM PIN | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.18 |  | LOCKING PIN | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.19 |  | PIN HOLDER PLATE | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.20 |  | ADJUSTING PLATE | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.21 |  | COUPLING- 6A, FULL GEAR, AFG-106 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.22 |  | COUPLING- 6B, FULL GEAR, AFG-106 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.23 |  | COUPLING- 6A,HALF GEAR, AHG-103 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.24 |  | COUPLING- 6B ,HALF GEAR, AHG-103 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.25 |  | SPACER- 01 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.26 |  | SPACER- 02 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.27 |  | SPACER- 03 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.28 |  | SPACER- 04 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.29 |  | SPACER- 05 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.30 |  | SPACER- 06 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.31 |  | GEAR BOX SHIM- 6A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.32 |  | GEAR BOX SHIM- 6B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.33 |  | MOTOR SHIM- 6A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.34 |  | MOTOR SHIM- 6B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.35 |  | BRIDLE 6A, GEARBOX RATIO- 14.133, MECH (P) 37KW | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.36 |  | BRIDLE 6B, GEARBOX RATIO- 13.922, MECH (P) 55KW | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.37 |  | 37KW, 6 POLE, 1000 RPM,FOOT MOUNTING, FRAME SIZE- ND250M, MAKE- CG | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.6.2.38 |  | 55KW, 6 POLE, 1000 RPM,FOOT MOUNTING, FRAME SIZE-ND280M, MAKE- CG | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d16h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.6.2.39 |  | END PLATE | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.40 |  | BEARING,SPHERICAL,22222E/C3(SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.41 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.42 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.43 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.44 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.45 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.46 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.47 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 17-Dec-25 04:44 PM | 17-Dec-25 05:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.48 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.49 |  | SHEAR BIOCK- 10x10x50mm | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.50 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.53 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.54 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.55 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.56 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.59 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.60 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.61 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.62 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.63 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.64 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.65 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.66 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.67 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.68 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.69 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 65 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.6.2.70 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 12:00 PM | 18-Nov-25 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7 |  | BRIDLE ROLL ASSY.#7 | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 69d10h |  |  | 16-Aug-25 01:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Dec-25 10:36 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
11.7.1 |  | Release of PO | step |  |  |  |  | 11.7.2
11.7.1.1 |  | BRIDLE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:21 AM | 13-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.2 |  | BRIDLE SNUBBER ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:21 AM | 13-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.3 |  | MAIN FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:21 AM | 13-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.4 |  | MOTOR AND GEARBOX FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:21 AM | 13-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.5 |  | BRAKE STAND- 7A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.6 |  | ARM FRAME- 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.7 |  | ARM CLEVIS- RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.8 |  | ARM CLEVIS- LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.9 |  | ARM FRAME- 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.10 |  | ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.11 |  | CYL. CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.12 |  | BRAKE STAND- 7B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.13 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:21 AM | 13-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.14 |  | CYL. CLEVIS PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.15 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.16 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.17 |  | ARM PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.18 |  | LOCKING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.19 |  | PIN HOLDER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.20 |  | ADJUSTING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.21 |  | SPACER- 01 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.22 |  | SPACER- 02 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.23 |  | SPACER- 03 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.24 |  | SPACER- 04 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.25 |  | SPACER- 05 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.26 |  | SPACER- 06 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Dec-25 04:02 PM | 18-Dec-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.27 |  | GEAR BOX SHIM-7A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:21 AM | 13-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.28 |  | GEAR BOX SHIM-7B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:21 AM | 13-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.29 |  | MOTOR SHIM- 7A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:21 AM | 13-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.30 |  | MOTOR SHIM-7B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:21 AM | 13-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.31 |  | COUPLING- 7A, FULL GEAR, AFG-106 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:24 AM | 13-Dec-25 11:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.32 |  | COUPLING- 7B, FULL GEAR, AFG-106 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:24 AM | 13-Dec-25 11:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.33 |  | COUPLING- 7A,HALF GEAR, AHG-103 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:24 AM | 13-Dec-25 11:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.34 |  | COUPLING- 7B,HALF GEAR, AHG-103 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:24 AM | 13-Dec-25 11:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.35 |  | BRIDLE- 7A, GEARBOX RATIO- 13.922, MECH (P) 75KW | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:24 AM | 13-Dec-25 11:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.36 |  | BRIDLE- 7B, GEARBOX RATIO- 14.133, MECH (P) 45KW | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:24 AM | 13-Dec-25 11:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.37 |  | 75KW, 6 POLE, 1000 RPM,FOOT MOUNTING, FRAME SIZE-ND315S, MAKE- CG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:24 AM | 13-Dec-25 11:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.38 |  | 45KW, 6 POLE, 1000 RPM,FOOT MOUNTING, FRAME SIZE-ND280S, MAKE- CG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:24 AM | 13-Dec-25 11:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.39 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 12:08 PM | 19-Dec-25 01:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.40 |  | BEARING,SPHERICAL,22222E/C3(SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.41 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.42 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.43 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.44 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.45 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.46 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.47 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.48 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.49 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.50 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.53 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.54 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.55 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.56 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.59 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.60 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.61 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.62 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.63 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.64 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.65 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.66 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.67 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.68 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.69 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.70 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.71 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.1.72 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2 |  | Ready for Assy | step |  |  |  | 11.7.1
11.7.2.1 |  | BRIDLE ROLL | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:21 AM | 13-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.2 |  | BRIDLE SNUBBER ROLL | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:21 AM | 13-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.3 |  | MAIN FRAME | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:21 AM | 13-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.4 |  | MOTOR AND GEARBOX FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 68d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:21 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.5 |  | BRAKE STAND- 7A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.6 |  | ARM FRAME- 1 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.7 |  | ARM CLEVIS- RH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.8 |  | ARM CLEVIS- LH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.9 |  | ARM FRAME- 2 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.10 |  | ARM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.11 |  | CYL. CLEVIS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.12 |  | BRAKE STAND- 7B | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.13 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 4d12h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:21 AM | 18-Dec-25 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.14 |  | CYL. CLEVIS PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.15 |  | TIE ROD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.16 |  | KEEPER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.17 |  | ARM PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.18 |  | LOCKING PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.19 |  | PIN HOLDER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.20 |  | ADJUSTING PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.21 |  | SPACER- 01 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.22 |  | SPACER- 02 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.23 |  | SPACER- 03 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.24 |  | SPACER- 04 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.25 |  | SPACER- 05 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.26 |  | SPACER- 06 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Dec-25 04:02 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.27 |  | GEAR BOX SHIM-7A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:21 AM | 13-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.28 |  | GEAR BOX SHIM-7B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:21 AM | 13-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.29 |  | MOTOR SHIM- 7A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:21 AM | 13-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.30 |  | MOTOR SHIM-7B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:21 AM | 13-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.31 |  | COUPLING- 7A, FULL GEAR, AFG-106 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:24 AM | 13-Dec-25 11:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.32 |  | COUPLING- 7B, FULL GEAR, AFG-106 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:24 AM | 13-Dec-25 11:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.33 |  | COUPLING- 7A,HALF GEAR, AHG-103 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:24 AM | 13-Dec-25 11:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.34 |  | COUPLING- 7B,HALF GEAR, AHG-103 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:24 AM | 13-Dec-25 11:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.35 |  | BRIDLE- 7A, GEARBOX RATIO- 13.922, MECH (P) 75KW | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:24 AM | 13-Dec-25 11:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.36 |  | BRIDLE- 7B, GEARBOX RATIO- 14.133, MECH (P) 45KW | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:24 AM | 13-Dec-25 11:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.37 |  | 75KW, 6 POLE, 1000 RPM,FOOT MOUNTING, FRAME SIZE-ND315S, MAKE- CG | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 68d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:24 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.38 |  | 45KW, 6 POLE, 1000 RPM,FOOT MOUNTING, FRAME SIZE-ND280S, MAKE- CG | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 68d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:24 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.39 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 12:08 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.7.2.40 |  | BEARING,SPHERICAL,22222E/C3(SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.41 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.42 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.43 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.44 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.45 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.46 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.47 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.48 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.49 |  | SHEAR BIOCK- 10x10x50mm | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.50 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.53 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.54 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.55 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.56 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.59 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.60 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.61 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.62 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.63 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.64 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.65 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.66 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.67 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.68 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.69 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 70 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.70 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.71 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.7.2.72 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:26 AM | 13-Dec-25 11:26 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8 |  | BRIDLE ROLL ASSY.#8 | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 69d10h |  |  | 16-Aug-25 01:00 AM | 25-Dec-25 02:00 PM |  |  | 12-Dec-25 10:37 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
11.8.1 |  | Release of PO | step |  |  |  |  | 11.8.2
11.8.1.1 |  | BRIDLE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:33 AM | 13-Dec-25 11:33 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.2 |  | BRIDLE SNUBBER ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 11:56 AM | 19-Dec-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.3 |  | MAIN FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:33 AM | 13-Dec-25 11:33 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.4 |  | MOTOR AND GEARBOX FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:33 AM | 13-Dec-25 11:33 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.5 |  | BRAKE STAND- 8B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.6 |  | ARM FRAME- 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.7 |  | ARM CLEVIS- RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.8 |  | ARM CLEVIS- LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.9 |  | ARM FRAME- 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.10 |  | ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.11 |  | CYL. CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.12 |  | BRAKE STAND- 8A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.13 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:33 AM | 13-Dec-25 11:33 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.14 |  | CYL. CLEVIS PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.15 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.16 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.17 |  | ARM PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.18 |  | LOCKING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.19 |  | PIN HOLDER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.20 |  | ADJUSTING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.21 |  | COUPLING- 8A, FULL GEAR, AFG-105 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:40 AM | 13-Dec-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.22 |  | COUPLING- 8B, FULL GEAR, AFG-105 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:40 AM | 13-Dec-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.23 |  | COUPLING- 8A, HALF GEAR, AHG-102 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:40 AM | 13-Dec-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.24 |  | COUPLING- 8B,HALF GEAR, AHG-102 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:40 AM | 13-Dec-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.25 |  | SPACER- 01 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.26 |  | SPACER- 02 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.27 |  | SPACER- 03 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.28 |  | SPACER- 04 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.29 |  | SPACER- 05 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.30 |  | GEAR BOX SHIM- 8A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:41 AM | 13-Dec-25 11:41 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.31 |  | GEAR BOX SHIM- 8B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:41 AM | 13-Dec-25 11:41 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.32 |  | MOTOR SHIM- 8A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:41 AM | 13-Dec-25 11:41 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.33 |  | MOTOR SHIM- 8B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:41 AM | 13-Dec-25 11:41 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.34 |  | BRIDLE 8A, GEARBOX RATIO- 14.175, MECH (P) 30KW | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.35 |  | BRIDLE- 8B, GEARBOX RATIO- 13.806, MECH (P) 22KW | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.36 |  | 30KW, 6 POLE, 1000 RPM,FOOT MOUNTING FRAME SIZE-ND225M | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.37 |  | 22KW, 6 POLE, 1000 RPM,FOOT MOUNTING FRAME SIZE-ND200L | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.38 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 09:34 AM | 19-Dec-25 10:34 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.39 |  | BEARING,SPHERICAL,22222E/C3(SPHERI CAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.40 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.41 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.42 |  | LOCATING RING-FRB 13.5/200, MAKE- SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.43 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.44 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.45 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.46 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.47 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.48 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.49 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.52 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.53 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.54 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.55 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.59 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.60 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.61 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.62 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.63 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.64 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.65 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.1.66 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2 |  | Ready for Assy | step |  |  |  | 11.8.1
11.8.2.1 |  | BRIDLE ROLL | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:33 AM | 13-Dec-25 11:33 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.2 |  | BRIDLE SNUBBER ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 11:56 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.3 |  | MAIN FRAME | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:33 AM | 13-Dec-25 11:33 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.4 |  | MOTOR AND GEARBOX FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 68d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:33 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.5 |  | BRAKE STAND- 8B | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.6 |  | ARM FRAME- 1 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.7 |  | ARM CLEVIS- RH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.8 |  | ARM CLEVIS- LH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.9 |  | ARM FRAME- 2 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.10 |  | ARM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.11 |  | CYL. CLEVIS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.12 |  | BRAKE STAND- 8A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.13 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:33 AM | 19-Dec-25 01:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.14 |  | CYL. CLEVIS PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.15 |  | TIE ROD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.16 |  | KEEPER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.17 |  | ARM PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.18 |  | LOCKING PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.19 |  | PIN HOLDER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.20 |  | ADJUSTING PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.21 |  | COUPLING- 8A, FULL GEAR, AFG-105 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:40 AM | 13-Dec-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.22 |  | COUPLING- 8B, FULL GEAR, AFG-105 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:40 AM | 13-Dec-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.23 |  | COUPLING- 8A, HALF GEAR, AHG-102 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:40 AM | 13-Dec-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.24 |  | COUPLING- 8B,HALF GEAR, AHG-102 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:40 AM | 13-Dec-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.25 |  | SPACER- 01 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.26 |  | SPACER- 02 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.27 |  | SPACER- 03 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.28 |  | SPACER- 04 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.29 |  | SPACER- 05 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.30 |  | GEAR BOX SHIM- 8A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:41 AM | 13-Dec-25 11:41 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.31 |  | GEAR BOX SHIM- 8B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:41 AM | 13-Dec-25 11:41 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.32 |  | MOTOR SHIM- 8A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:41 AM | 13-Dec-25 11:41 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.33 |  | MOTOR SHIM- 8B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:41 AM | 13-Dec-25 11:41 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.34 |  | BRIDLE 8A, GEARBOX RATIO- 14.175, MECH (P) 30KW | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.35 |  | BRIDLE- 8B, GEARBOX RATIO- 13.806, MECH (P) 22KW | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.36 |  | 30KW, 6 POLE, 1000 RPM,FOOT MOUNTING FRAME SIZE-ND225M | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 68d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.37 |  | 22KW, 6 POLE, 1000 RPM,FOOT MOUNTING FRAME SIZE-ND200L | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 68d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.38 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 09:34 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.8.2.39 |  | BEARING,SPHERICAL,22222E/C3(SPHERI CAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.40 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.41 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.42 |  | LOCATING RING-FRB 13.5/200, MAKE- SKF | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.43 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.44 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.45 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.46 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:42 AM | 13-Dec-25 11:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.47 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.48 |  | SHEAR BIOCK- 10x10x50mm | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.49 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.52 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.53 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.54 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.55 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.59 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.60 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.61 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.62 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.63 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.64 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.65 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.8.2.66 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:43 AM | 13-Dec-25 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9 |  | BRIDLE ROLL ASSY.#9 | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 97d13h |  |  | 16-Aug-25 01:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:00 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
11.9.1 |  | Release of PO | step |  |  |  |  | 11.9.2
11.9.1.1 |  | BRIDLE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:02 PM | 11-Nov-25 08:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.2 |  | BRIDLE SNUBBER ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:57 AM | 18-Nov-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.3 |  | MAIN FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:02 PM | 11-Nov-25 08:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.4 |  | MOTOR AND GEARBOX FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 21d8h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 09-Dec-25 10:50 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.5 |  | ARM FRAME- 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 18-Nov-25 11:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.6 |  | ARM CLEVIS- RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 18-Nov-25 11:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.7 |  | ARM CLEVIS- LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 18-Nov-25 11:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.8 |  | ARM FRAME- 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 18-Nov-25 11:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.9 |  | ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 18-Nov-25 11:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.10 |  | CYL. CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 18-Nov-25 11:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.11 |  | BRAKE STAND | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 18-Nov-25 11:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.12 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.13 |  | CYL. CLEVIS PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 18-Nov-25 11:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.14 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 18-Nov-25 11:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.15 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 18-Nov-25 11:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.16 |  | ARM PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 18-Nov-25 11:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.17 |  | LOCKING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 18-Nov-25 11:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.18 |  | PIN HOLDER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 18-Nov-25 11:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.19 |  | ADJUSTING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 18-Nov-25 11:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.20 |  | COUPLING, FULL GEAR, AFG-105 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:02 PM | 11-Nov-25 08:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.21 |  | SPACER- 01 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 18-Nov-25 11:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.22 |  | COUPLING,HALF GEAR, AHG-102 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:02 PM | 11-Nov-25 08:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.23 |  | SPACER- 02 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d5h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 18-Nov-25 11:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.24 |  | GEAR BOX SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 21d8h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 09-Dec-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.25 |  | MOTOR SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 21d8h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 15-Nov-25 02:50 PM | 09-Dec-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.26 |  | BRIDLE- 9B, GEARBOX RATIO- 14.4, MECH (P) 15KW @1500RPM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:02 PM | 11-Nov-25 08:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.27 |  | BRIDLE- 9A, GEARBOX RATIO- 14.4, MECH (P) 15KW @1500RPM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:02 PM | 11-Nov-25 08:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.28 |  | 15KW, 4 POLE, 1500 RPM,FOOT MOUNTING, FRAME SIZE-ND160L, MAKE- CG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.29 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 18-Nov-25 11:53 AM | 18-Nov-25 12:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.30 |  | BEARING,SPHERICAL,22222E/C3(SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:02 PM | 11-Nov-25 08:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.31 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:02 PM | 11-Nov-25 08:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.32 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:02 PM | 11-Nov-25 08:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.33 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:02 PM | 11-Nov-25 08:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.34 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:02 PM | 11-Nov-25 08:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.35 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:02 PM | 11-Nov-25 08:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.36 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:02 PM | 11-Nov-25 08:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.37 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 07:02 PM | 11-Nov-25 08:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.38 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.39 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.40 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.43 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.44 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.45 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.46 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.50 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.51 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.52 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.54 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.55 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.1.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2 |  | Ready for Assy | step |  |  |  | 11.9.1
11.9.2.1 |  | BRIDLE ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:02 PM | 09-Dec-25 10:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.2 |  | BRIDLE SNUBBER ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 28d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:57 AM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.3 |  | MAIN FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:02 PM | 09-Dec-25 10:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.4 |  | MOTOR AND GEARBOX FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 93d17h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.9.2.5 |  | ARM FRAME- 2 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.6 |  | ARM CLEVIS- RH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.7 |  | ARM CLEVIS- LH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.8 |  | ARM FRAME- 1 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.9 |  | ARM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.10 |  | CYL. CLEVIS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.11 |  | BRAKE STAND | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.12 |  | BUSH | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.13 |  | CYL. CLEVIS PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.14 |  | TIE ROD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.15 |  | KEEPER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.16 |  | ARM PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.17 |  | LOCKING PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.18 |  | PIN HOLDER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.19 |  | ADJUSTING PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.20 |  | COUPLING, FULL GEAR, AFG-105 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:02 PM | 09-Dec-25 10:59 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.21 |  | SPACER- 01 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.22 |  | COUPLING,HALF GEAR, AHG-102 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:02 PM | 09-Dec-25 10:59 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.23 |  | SPACER- 02 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d15h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.24 |  | GEAR BOX SHIM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 21d8h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 09-Dec-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.25 |  | MOTOR SHIM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 21d8h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 15-Nov-25 02:50 PM | 09-Dec-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.26 |  | BRIDLE- 9B, GEARBOX RATIO- 14.4, MECH (P) 15KW @1500RPM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:02 PM | 15-Nov-25 02:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.27 |  | BRIDLE- 9A, GEARBOX RATIO- 14.4, MECH (P) 15KW @1500RPM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 3d14h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:02 PM | 15-Nov-25 02:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.28 |  | 15KW, 4 POLE, 1500 RPM,FOOT MOUNTING, FRAME SIZE-ND160L, MAKE- CG | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:51 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.9.2.29 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 28d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 18-Nov-25 11:53 AM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.30 |  | BEARING,SPHERICAL,22222E/C3(SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:02 PM | 09-Dec-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.31 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 34d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:02 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.32 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 34d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:02 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.33 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 34d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:02 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.34 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 34d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:02 PM | 19-Dec-25 10:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.35 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:02 PM | 09-Dec-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.36 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:02 PM | 09-Dec-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.37 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:02 PM | 09-Dec-25 10:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.38 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.39 |  | SHEAR BIOCK- 10x10x50mm | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.40 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.43 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.44 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.45 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.46 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.50 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.51 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.52 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.54 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.55 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.9.2.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 09-Dec-25 10:56 AM | 09-Dec-25 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10 |  | BRIDLE ROLL ASSY.#10 | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 97d14h |  |  | 16-Aug-25 01:00 AM | 25-Dec-25 02:00 PM |  |  | 11-Nov-25 07:00 PM | 26-Feb-26 05:03 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
11.10.1 |  | Release of PO | step |  |  |  |  | 11.10.2
11.10.1.1 |  | BRIDLE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:44 AM | 13-Dec-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.2 |  | BRIDLE SNUBBER ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 11:56 AM | 19-Dec-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.3 |  | MAIN FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:44 AM | 13-Dec-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.4 |  | MOTOR AND GEARBOX FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:44 AM | 13-Dec-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.5 |  | ARM FRAME- 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.6 |  | CYL. CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.7 |  | ARM FRAME- 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.8 |  | ARM CLEVIS- RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.9 |  | ARM CLEVIS- LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.10 |  | ARM FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.11 |  | BRAKE STAND- 10A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.12 |  | BRAKE STAND- 10B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.13 |  | CHAIN COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 26-Feb-26 04:03 PM | 26-Feb-26 05:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.1.14 |  | DUPLEX CHAIN (12B2), ROLLER DIA 12.07mm, PITCH 0.75'' (1150mm LONG), (60 NOS. LINKS), MAKE- RENOLD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 12:52 PM | 19-Dec-25 01:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.15 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.16 |  | CYL. CLEVIS PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:04 AM | 19-Dec-25 11:04 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.17 |  | SPACER- 01 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:04 AM | 19-Dec-25 11:04 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.18 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:04 AM | 19-Dec-25 11:04 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.19 |  | ARM PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:04 AM | 19-Dec-25 11:04 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.20 |  | LOCKING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:04 AM | 19-Dec-25 11:04 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.21 |  | PIN HOLDER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:04 AM | 19-Dec-25 11:04 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.22 |  | ADJUSTING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:04 AM | 19-Dec-25 11:04 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.23 |  | COUPLING- 10A, FULL GEAR, AFG-105 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.24 |  | COUPLING- 10B, FULL GEAR, AFG-105 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.25 |  | COUPLING- 10A,HALF GEAR, AHG-102 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.26 |  | COUPLING- 10B,HALF GEAR, AHG-102 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.27 |  | GEAR BOX SHIM- 10A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.28 |  | GEAR BOX SHIM- 10B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.29 |  | MOTOR SHIM- 10A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.30 |  | MOTOR SHIM- 10B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.31 |  | SPACER- 02 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.32 |  | SPACER- 03 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.33 |  | END PLATE (ROLL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.34 |  | END PLATE (GEAREDMOTOR) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.35 |  | GEAR BOX SPROCKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.36 |  | ROLL SPROCKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.37 |  | SPACER - 04 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.38 |  | SPACER- 05 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.39 |  | BASE PLATE (MAIN FRAME) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 26-Feb-26 04:03 PM | 26-Feb-26 05:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.1.40 |  | BASE PLATE (GEARBOX FRAME) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 26-Feb-26 04:03 PM | 26-Feb-26 05:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.1.41 |  | GEARED MOTOR- 1.5KW,1500RPM,4 POLE, RATIO- 25.51:1, MODEL-M062222, MAKE- PBL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 11:51 AM | 19-Dec-25 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.42 |  | BRIDLE 10A, GEARBOX RATIO- 11.333, MECH (P) 22KW | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.43 |  | BRIDLE- 10B, GEARBOX RATIO- 11.059, MECH (P) 30KW | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.44 |  | 22KW, 4 POLE, 1500 RPM,FOOT MOUNTING, FRAME SIZE- ND180L, MAKE- CG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.45 |  | 30KW, 4 POLE, 1500 RPM,FOOT MOUNTING, FRAME SIZE-ND200L, MAKE- CG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.46 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.47 |  | BEARING,SPHERICAL,22222E/C3(SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.48 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.49 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.50 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.51 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.52 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.53 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.54 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.55 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.56 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.57 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.59 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.60 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.61 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.62 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.63 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.64 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.65 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.66 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.67 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.68 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.69 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.70 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.71 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.72 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.73 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.74 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.75 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.76 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.77 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M36 x 110 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.78 |  | Spring Lock Washer IS 3063 - 36-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.1.79 |  | Plain Washer (Type A) IS 2016 - 39 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2 |  | Ready for Assy | step |  |  |  | 11.10.1
11.10.2.1 |  | BRIDLE ROLL | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:44 AM | 13-Dec-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.2 |  | BRIDLE SNUBBER ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 11:56 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.3 |  | MAIN FRAME | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:44 AM | 13-Dec-25 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.4 |  | MOTOR AND GEARBOX FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 68d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:44 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.5 |  | ARM FRAME- 2 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.6 |  | CYL. CLEVIS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.7 |  | ARM FRAME- 1 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.8 |  | ARM CLEVIS- RH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.9 |  | ARM CLEVIS- LH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.10 |  | ARM FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.11 |  | BRAKE STAND- 10A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.12 |  | BRAKE STAND- 10B | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.13 |  | CHAIN COVER | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 26-Feb-26 04:03 PM | 26-Feb-26 05:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.14 |  | DUPLEX CHAIN (12B2), ROLLER DIA 12.07mm, PITCH 0.75'' (1150mm LONG), (60 NOS. LINKS), MAKE- RENOLD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d2h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 12:52 PM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.15 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 19-Dec-25 01:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.16 |  | CYL. CLEVIS PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:04 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.17 |  | SPACER- 01 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:04 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.18 |  | KEEPER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:04 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.19 |  | ARM PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:04 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.20 |  | LOCKING PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:04 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.21 |  | PIN HOLDER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:04 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.22 |  | ADJUSTING PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:04 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.23 |  | COUPLING- 10A, FULL GEAR, AFG-105 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.24 |  | COUPLING- 10B, FULL GEAR, AFG-105 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.25 |  | COUPLING- 10A,HALF GEAR, AHG-102 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.26 |  | COUPLING- 10B,HALF GEAR, AHG-102 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.27 |  | GEAR BOX SHIM- 10A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.28 |  | GEAR BOX SHIM- 10B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.29 |  | MOTOR SHIM- 10A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.30 |  | MOTOR SHIM- 10B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 19-Dec-25 11:00 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.31 |  | SPACER- 02 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.32 |  | SPACER- 03 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.33 |  | END PLATE (ROLL) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.34 |  | END PLATE (GEAREDMOTOR) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.35 |  | GEAR BOX SPROCKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.36 |  | ROLL SPROCKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.37 |  | SPACER - 04 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.38 |  | SPACER- 05 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.39 |  | BASE PLATE (MAIN FRAME) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 26-Feb-26 04:03 PM | 26-Feb-26 05:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.40 |  | BASE PLATE (GEARBOX FRAME) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 26-Feb-26 04:03 PM | 26-Feb-26 05:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.41 |  | GEARED MOTOR- 1.5KW,1500RPM,4 POLE, RATIO- 25.51:1, MODEL-M062222, MAKE- PBL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 11:51 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.42 |  | BRIDLE 10A, GEARBOX RATIO- 11.333, MECH (P) 22KW | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.43 |  | BRIDLE- 10B, GEARBOX RATIO- 11.059, MECH (P) 30KW | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.44 |  | 22KW, 4 POLE, 1500 RPM,FOOT MOUNTING, FRAME SIZE- ND180L, MAKE- CG | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 68d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.45 |  | 30KW, 4 POLE, 1500 RPM,FOOT MOUNTING, FRAME SIZE-ND200L, MAKE- CG | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 68d10h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.46 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 63d3h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 19-Dec-25 10:00 AM | 26-Feb-26 04:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
11.10.2.47 |  | BEARING,SPHERICAL,22222E/C3(SPHERICAL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.48 |  | BEARING HOUSING-FSNL 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 19-Dec-25 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.49 |  | END COVER-ASNH 522-619, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 19-Dec-25 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.50 |  | LOCATING RING-FRB 13.5/200, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 19-Dec-25 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.51 |  | OIL SEAL-TSN 222 A, MAKE-SKF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 5d9h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 19-Dec-25 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.52 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.53 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.54 |  | BRAKE PNEUMATIC- KA-PF-320 (KATEEL) | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:48 AM | 13-Dec-25 11:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.55 |  | Retaining Ring (Normal) External IS 3075(Part1) - 30 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.56 |  | SHEAR BIOCK- 10x10x50mm | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.57 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.58 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.59 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.60 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.61 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.62 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.63 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.64 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.65 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 100 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.66 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.67 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.68 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.69 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.70 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.71 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.72 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.73 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.74 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.75 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.76 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.77 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M36 x 110 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.78 |  | Spring Lock Washer IS 3063 - 36-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
11.10.2.79 |  | Plain Washer (Type A) IS 2016 - 39 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 27-Aug-25 05:00 AM | 25-Dec-25 02:00 PM |  |  | 13-Dec-25 10:49 AM | 13-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12 | 60 | Category 2 - UNCOILER ASSY (2QTYS) - Ordering & Manufacturing | TASK |  | 120d | 120d | 21 | 64 | IP | NO | 001-023 |  |  |  |  | 1d |  | 128d6h |  |  | 18-Aug-25 02:00 PM | 27-Dec-25 02:00 PM | 24-Mar-26 01:00 AM | 25-Mar-26 01:00 AM | 03-Nov-25 01:07 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
12.1 |  | UNCOILER MANDREL ASSY. (2QTYS) | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 105d7h |  |  | 18-Aug-25 02:00 PM | 27-Dec-25 02:00 PM |  |  | 03-Nov-25 01:07 PM | 26-Feb-26 03:52 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
12.1.1 |  | Release of PO | step |  |  |  |  | 12.1.2
12.1.1.1 |  | AIA1800826-OIL SEAL- ID190XOD220X15 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 03-Nov-25 01:08 PM | 13-Jan-26 09:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.2 |  | 22234_CC_W33-SPHERICAL ROLLER BEARING-ID170X OD310X82 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 64d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 03-Nov-25 01:08 PM | 13-Jan-26 09:57 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.3 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 20d3h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 13-Dec-25 03:34 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.4 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 20d3h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 13-Dec-25 03:34 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.5 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 20d3h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 13-Dec-25 03:34 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.6 |  | OBBS SHAFT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 20d3h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 13-Dec-25 03:34 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.7 |  | BEARING HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 20d3h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 13-Dec-25 03:34 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.8 |  | DUO FLOW HYD. ROTATING UNION, ROTOR THREAD 1-1/4" BSP, INLET PORT THREAD 1/2" BSP, MAKE- DEUBLIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 47d17h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 13-Jan-26 10:05 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.9 |  | PULL ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 20d3h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 13-Dec-25 03:34 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.10 |  | RETAINER 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 20d3h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 13-Dec-25 03:34 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.11 |  | CONNECTOR | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 20d3h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 13-Dec-25 03:34 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.12 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 34d3h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 29-Dec-25 12:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.13 |  | MANDREL SHAFT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 12d11h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 05-Dec-25 10:54 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.14 |  | CYL. BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 20d3h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 13-Dec-25 03:34 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.15 |  | HYD. CYL. BORE-220, ROD-110, STROKE- 175MM,FF | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d14h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 25-Dec-25 09:38 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.16 |  | MANDREL DRUM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 12d11h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 05-Dec-25 10:42 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.17 |  | GREASE NIPPLE 1/4" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.18 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.20 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.22 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.23 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.24 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 120 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.25 |  | Hexagon Nut Style 1 IS 1364-Part3 - M16-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.26 |  | Hexagon Nut Style 1 IS 1364-Part3 - M24-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.27 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.28 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.29 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.30 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.31 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.32 |  | Socket Head Cap Screw IS 2269 - M16 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.33 |  | Socket Head Cap Screw IS 2269 - M20 x 110 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.34 |  | Socket Head Cap Screw IS 2269 - M24 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.35 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.36 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.37 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.38 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.39 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.1.40 |  | Socket Countersunk Head Cap Screw IS 6761 - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d15h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 21-Nov-25 03:34 PM | 01-Dec-25 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2 |  | Ready for Assy | step |  |  |  | 12.1.1
12.1.2.1 |  | AIA1800826-OIL SEAL- ID190XOD220X15 THK. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 75d6h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:20 PM | 02-Feb-26 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.2 |  | 22234_CC_W33-SPHERICAL ROLLER BEARING-ID170X OD310X82 THK. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 60d2h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:20 PM | 16-Jan-26 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.3 |  | RETAINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d4h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:34 PM | 02-Feb-26 04:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.4 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d4h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:34 PM | 02-Feb-26 04:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.5 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d4h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:34 PM | 02-Feb-26 04:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.6 |  | OBBS SHAFT | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d4h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:34 PM | 02-Feb-26 04:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.7 |  | BEARING HOUSING | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d4h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:34 PM | 02-Feb-26 04:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.8 |  | DUO FLOW HYD. ROTATING UNION, ROTOR THREAD 1-1/4" BSP, INLET PORT THREAD 1/2" BSP, MAKE- DEUBLIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 04:59 PM | 26-Feb-26 03:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.9 |  | PULL ROD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d4h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:34 PM | 02-Feb-26 04:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.10 |  | RETAINER 2 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d4h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:34 PM | 02-Feb-26 04:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.11 |  | CONNECTOR | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d4h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:34 PM | 02-Feb-26 04:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.12 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 12:27 PM | 02-Feb-26 02:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.13 |  | MANDREL SHAFT | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d14h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:34 PM | 16-Jan-26 11:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.14 |  | CYL. BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d4h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:34 PM | 02-Feb-26 04:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.15 |  | HYD. CYL. BORE-220, ROD-110, STROKE- 175MM,FF | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d14h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 09:38 AM | 26-Feb-26 03:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.16 |  | MANDREL DRUM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 16-Jan-26 12:13 PM | 16-Jan-26 01:13 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.17 |  | GREASE NIPPLE 1/4" BSP | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.18 |  | GREASE NIPPLE 1/8" BSP | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.20 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.22 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.23 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.24 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 120 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.25 |  | Hexagon Nut Style 1 IS 1364-Part3 - M16-D-N | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.26 |  | Hexagon Nut Style 1 IS 1364-Part3 - M24-D-N | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.27 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.28 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.29 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.30 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.31 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.32 |  | Socket Head Cap Screw IS 2269 - M16 x 65 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.33 |  | Socket Head Cap Screw IS 2269 - M20 x 110 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.34 |  | Socket Head Cap Screw IS 2269 - M24 x 90 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.35 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.36 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.37 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.38 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.39 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.1.2.40 |  | Socket Countersunk Head Cap Screw IS 6761 - M12 x 45 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:21 AM | 29-Dec-25 11:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2 |  | UNCOILER GEAR BOX ASSY. (2QTYS) | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 108d16h |  |  | 18-Aug-25 02:00 PM | 27-Dec-25 02:00 PM |  |  | 03-Nov-25 01:07 PM | 02-Mar-26 05:34 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
12.2.1 |  | Release of PO | step |  |  |  |  | 12.2.2
12.2.1.1 |  | FIXED FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:23 PM | 11-Nov-25 08:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.2 |  | SLIDING FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 21d4h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Nov-25 10:31 AM | 05-Dec-25 12:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.3 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 04:15 PM | 13-Dec-25 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.4 |  | HYD. CYLINDER, STK-300, ROD-Ø90 PISTON-Ø180 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:20 PM | 05-Dec-25 01:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.5 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 04:15 PM | 13-Dec-25 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.6 |  | DISC BRAKE STAND | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:20 PM | 05-Dec-25 01:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.7 |  | MOTOR BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Jan-26 03:06 PM | 05-Jan-26 04:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.8 |  | ROTARY UNION SUPPORT ASSY. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 04:15 PM | 13-Dec-25 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.9 |  | GEARBOX: RPM- 750-1500, G.R.-13.65:1, INPUT POWER- 45KW | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:20 PM | 05-Dec-25 01:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.10 |  | AHG-105 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 02:36 PM | 29-Dec-25 03:36 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.11 |  | GEAR BOX SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 04:15 PM | 13-Dec-25 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.12 |  | MOTOR SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.13 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 04:15 PM | 13-Dec-25 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.14 |  | CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 04:15 PM | 13-Dec-25 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.15 |  | VERTICAL LINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 12:43 PM | 29-Dec-25 01:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.16 |  | LOCK PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 04:15 PM | 13-Dec-25 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.17 |  | VERTICAL LINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 12:43 PM | 29-Dec-25 01:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.18 |  | HORIZONTAL LINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 12:56 PM | 29-Dec-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.19 |  | HOR. LINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 12:56 PM | 29-Dec-25 01:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.20 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 04:15 PM | 13-Dec-25 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.21 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 04:15 PM | 13-Dec-25 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.22 |  | MOTOR SPACER OD Ø95.0 x ID Ø75.0 x 30.0 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 04:15 PM | 13-Dec-25 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.23 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 04:15 PM | 13-Dec-25 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.24 |  | 80X115X16 THKL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 04:15 PM | 13-Dec-25 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.25 |  | BRAKE PNEUMATIC- KC-PF-400 (KATEEL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 02:55 PM | 29-Dec-25 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.26 |  | 45 KW MOTOR-8 POLE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:20 PM | 05-Dec-25 01:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.27 |  | DOWEL PIN Ø10X33.5MM LONG. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.28 |  | 15x15x50 MM LONG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.29 |  | SHEAR BLOCK- 15X15X80MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.30 |  | STOPPER 25 X 25 X 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.31 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.32 |  | Spring Lock Washer IS 3063 - 30-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 110 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.34 |  | Socket Countersunk Head Cap Screw IS 6761 - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.35 |  | Plain Washer (Type A) IS 2016 - 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.36 |  | Spring Lock Washer IS 3063 - 16-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.37 |  | Hexagon nut IS 1363- Part2 - M16-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 130 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.40 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.41 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.43 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.45 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.47 |  | Plain Washer (Type A) IS 2016 - 39 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.48 |  | Spring Lock Washer IS 3063 - 36-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M36 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.50 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.51 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.53 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.54 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.56 |  | Spring Lock Washer IS 3063 - 12-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.58 |  | Spring Lock Washer IS 3063 - 10-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.59 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.60 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.61 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.1.62 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2 |  | Ready for Assy | step |  |  |  | 12.2.1
12.2.2.1 |  | FIXED FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d13h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 16-Jan-26 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.2 |  | SLIDING FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d13h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 16-Jan-26 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.3 |  | BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 02-Feb-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.4 |  | HYD. CYLINDER, STK-300, ROD-Ø90 PISTON-Ø180 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d13h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 16-Jan-26 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.5 |  | BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 02-Feb-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.6 |  | DISC BRAKE STAND | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d13h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 16-Jan-26 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.7 |  | MOTOR BASE FRAME | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 05-Jan-26 03:06 PM | 05-Jan-26 04:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.8 |  | ROTARY UNION SUPPORT ASSY. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 02-Feb-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.9 |  | GEARBOX: RPM- 750-1500, G.R.-13.65:1, INPUT POWER- 45KW | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 69d8h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 27-Feb-26 06:17 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.10 |  | AHG-105 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 16d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 02:36 PM | 16-Jan-26 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.11 |  | GEAR BOX SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 02-Feb-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.12 |  | MOTOR SHIM | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.13 |  | PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 02-Feb-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.14 |  | CLEVIS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 02-Feb-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.15 |  | VERTICAL LINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 16d15h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 12:43 PM | 16-Jan-26 01:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.16 |  | LOCK PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 02-Feb-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.17 |  | VERTICAL LINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 16d15h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 12:43 PM | 16-Jan-26 01:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.18 |  | HORIZONTAL LINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 16d14h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 12:56 PM | 16-Jan-26 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.19 |  | HOR. LINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 16d15h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 12:56 PM | 16-Jan-26 01:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.20 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 02-Feb-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.21 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 02-Feb-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.22 |  | MOTOR SPACER OD Ø95.0 x ID Ø75.0 x 30.0 THK. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 02-Feb-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.23 |  | PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 02-Feb-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.24 |  | 80X115X16 THKL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 04:15 PM | 02-Feb-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.25 |  | BRAKE PNEUMATIC- KC-PF-400 (KATEEL) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 54d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 02:55 PM | 26-Feb-26 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.26 |  | 45 KW MOTOR-8 POLE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 54d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 02:56 PM | 26-Feb-26 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.27 |  | DOWEL PIN Ø10X33.5MM LONG. | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.28 |  | 15x15x50 MM LONG | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.29 |  | SHEAR BLOCK- 15X15X80MM | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.30 |  | STOPPER 25 X 25 X 100 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.31 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.32 |  | Spring Lock Washer IS 3063 - 30-B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 110 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.34 |  | Socket Countersunk Head Cap Screw IS 6761 - M12 x 35 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.35 |  | Plain Washer (Type A) IS 2016 - 20 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.36 |  | Spring Lock Washer IS 3063 - 16-B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.37 |  | Hexagon nut IS 1363- Part2 - M16-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 130 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 80 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.40 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.41 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.43 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.45 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 70 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.47 |  | Plain Washer (Type A) IS 2016 - 39 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.48 |  | Spring Lock Washer IS 3063 - 36-B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M36 x 100 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.50 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.51 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.53 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.54 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.56 |  | Spring Lock Washer IS 3063 - 12-B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.58 |  | Spring Lock Washer IS 3063 - 10-B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.59 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 25 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.60 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.61 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.2.2.62 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:06 PM | 29-Dec-25 02:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3 |  | UNCOILER SNUBBER ROLL ASSY.#1 (2QTYS) | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 79d13h |  |  | 18-Aug-25 02:00 PM | 27-Dec-25 02:00 PM |  |  | 01-Dec-25 04:06 PM | 26-Feb-26 04:52 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
12.3.1 |  | Release of PO | step |  |  |  |  | 12.3.2
12.3.1.1 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 12:31 PM | 29-Dec-25 01:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.2 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 12:31 PM | 29-Dec-25 01:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.3 |  | CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 03:57 PM | 13-Dec-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.4 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 03:57 PM | 13-Dec-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.5 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 03:57 PM | 13-Dec-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.6 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 03:57 PM | 13-Dec-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.7 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 03:57 PM | 13-Dec-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.8 |  | HYD . MOTOR OMP 250(1X) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Jan-26 11:07 AM | 13-Jan-26 12:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.9 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 03:57 PM | 13-Dec-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.10 |  | BEARING COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 03:57 PM | 13-Dec-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.11 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 03:57 PM | 13-Dec-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.12 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 03:57 PM | 13-Dec-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.13 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 03:57 PM | 13-Dec-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.14 |  | CHAIN COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 26-Feb-26 03:52 PM | 26-Feb-26 04:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.3.1.15 |  | MOTOR SPROCKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 03:57 PM | 13-Dec-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.16 |  | ROLL SPROCKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 03:57 PM | 13-Dec-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.17 |  | RIB | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 03:57 PM | 13-Dec-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.18 |  | CYL. CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 03:57 PM | 13-Dec-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.19 |  | SNUBBER ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:42 PM | 29-Dec-25 04:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.20 |  | SHAFT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 09:44 AM | 29-Dec-25 10:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.21 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:42 PM | 29-Dec-25 04:42 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.22 |  | LEVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 09:44 AM | 29-Dec-25 10:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.23 |  | HYD , CYL BORE DIA -80,ROD DIA-45,STROKE 450 MM REAR PIVOT MOUNTING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 09:40 AM | 25-Dec-25 10:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.24 |  | SNUBBER ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:08 PM | 29-Dec-25 04:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.25 |  | BRG BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 03:57 PM | 13-Dec-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.26 |  | DUPLEX CHAIN PITCH 3/4'' (1000 LONG) MAKE RENOLD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Jan-26 09:59 AM | 13-Jan-26 10:59 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.27 |  | MOTOR HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Jan-26 09:59 AM | 13-Jan-26 10:59 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.28 |  | SNUBBER LOCKING BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Jan-26 11:18 AM | 13-Jan-26 12:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.29 |  | SAFETY PIN WITH CHAIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Dec-25 03:57 PM | 13-Dec-25 04:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.30 |  | OIL SEAL-50ID x 70OD x 8THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Jan-26 09:59 AM | 13-Jan-26 10:59 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.31 |  | BEARING,SPHERICAL,22208 E(SPHERICAL ROLLER BRG D 40IDx80ODx23THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Jan-26 09:59 AM | 13-Jan-26 10:59 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.32 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.33 |  | Spring Lock Washer IS 3063 - 16-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.34 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.35 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.36 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.37 |  | Spring Lock Washer IS 3063 - 20-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.39 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.40 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.42 |  | Spring Lock Washer IS 3063 - 8-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.43 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.44 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.45 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.46 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.48 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.49 |  | Spring Lock Washer IS 3063 - 12-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.54 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.1.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 05-Dec-25 12:21 PM | 05-Dec-25 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2 |  | Ready for Assy | step |  |  |  | 12.3.1
12.3.2.1 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 12:31 PM | 02-Feb-26 02:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.2 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 12:31 PM | 02-Feb-26 02:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.3 |  | CLEVIS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:57 PM | 02-Feb-26 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.4 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:57 PM | 02-Feb-26 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.5 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:57 PM | 02-Feb-26 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.6 |  | PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 68d5h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:57 PM | 26-Feb-26 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.3.2.7 |  | PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:57 PM | 02-Feb-26 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.8 |  | HYD . MOTOR OMP 250(1X) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 40d10h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Jan-26 11:07 AM | 26-Feb-26 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.3.2.9 |  | RETAINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:57 PM | 02-Feb-26 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.10 |  | BEARING COVER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:57 PM | 02-Feb-26 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.11 |  | RETAINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:57 PM | 02-Feb-26 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.12 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:57 PM | 02-Feb-26 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.13 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:57 PM | 02-Feb-26 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.14 |  | CHAIN COVER | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 26-Feb-26 03:52 PM | 26-Feb-26 04:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.3.2.15 |  | MOTOR SPROCKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:57 PM | 02-Feb-26 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.16 |  | ROLL SPROCKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:57 PM | 02-Feb-26 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.17 |  | RIB | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:57 PM | 02-Feb-26 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.18 |  | CYL. CLEVIS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:57 PM | 02-Feb-26 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.19 |  | SNUBBER ARM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 54d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:42 PM | 26-Feb-26 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.3.2.20 |  | SHAFT | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 54d7h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 09:44 AM | 26-Feb-26 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.3.2.21 |  | BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 54d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:42 PM | 26-Feb-26 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.3.2.22 |  | LEVER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 54d7h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 09:44 AM | 26-Feb-26 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.3.2.23 |  | HYD , CYL BORE DIA -80,ROD DIA-45,STROKE 450 MM REAR PIVOT MOUNTING | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d14h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 09:40 AM | 26-Feb-26 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.3.2.24 |  | SNUBBER ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 54d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:08 PM | 26-Feb-26 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.3.2.25 |  | BRG BLOCK | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:57 PM | 02-Feb-26 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.26 |  | DUPLEX CHAIN PITCH 3/4'' (1000 LONG) MAKE RENOLD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 26-Feb-26 03:52 PM | 26-Feb-26 04:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.3.2.27 |  | MOTOR HOUSING | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 26-Feb-26 03:52 PM | 26-Feb-26 04:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.3.2.28 |  | SNUBBER LOCKING BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 40d10h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Jan-26 11:18 AM | 26-Feb-26 03:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.3.2.29 |  | SAFETY PIN WITH CHAIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 46d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Dec-25 03:57 PM | 02-Feb-26 04:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.30 |  | OIL SEAL-50ID x 70OD x 8THK | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 02-Feb-26 12:57 PM | 02-Feb-26 01:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.31 |  | BEARING,SPHERICAL,22208 E(SPHERICAL ROLLER BRG D 40IDx80ODx23THK. mm) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 16-Jan-26 11:54 AM | 16-Jan-26 12:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.32 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.33 |  | Spring Lock Washer IS 3063 - 16-B | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.34 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.35 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.36 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.37 |  | Spring Lock Washer IS 3063 - 20-B | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 60 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.39 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.40 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.42 |  | Spring Lock Washer IS 3063 - 8-B | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.43 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 20 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.44 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.45 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.46 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.48 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.49 |  | Spring Lock Washer IS 3063 - 12-B | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 25 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 25 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.54 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 25 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.3.2.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 25 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:08 PM | 29-Dec-25 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4 |  | UNCOILER OBBS ASSY. (2QTYS) | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 97d12h |  |  | 18-Aug-25 02:00 PM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:06 PM | 26-Feb-26 03:53 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
12.4.1 |  | Release of PO | step |  |  |  |  | 12.4.2
12.4.1.1 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 14-Nov-25 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.2 |  | O.B.B.S ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 18-Nov-25 10:31 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.3 |  | PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 18-Nov-25 10:31 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.4 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 14-Nov-25 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.5 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 14-Nov-25 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.6 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 14-Nov-25 05:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.7 |  | CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 18-Nov-25 10:31 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.8 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 18-Nov-25 10:31 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.9 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 18-Nov-25 10:31 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.10 |  | SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d8h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 29-Dec-25 01:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.11 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d10h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 15-Dec-25 09:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.12 |  | ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d10h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 15-Dec-25 09:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.13 |  | ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d10h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 15-Dec-25 09:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.14 |  | ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d10h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 15-Dec-25 09:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.15 |  | MOUNTING BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 30d10h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 15-Dec-25 09:53 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.16 |  | HYD.CYL.BORE-Ø100,ROD-Ø56,STK-500mm,CT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 14-Nov-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.17 |  | MOUNTING BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d10h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 29-Dec-25 03:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.18 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 18-Nov-25 10:31 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.19 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 18-Nov-25 10:31 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.20 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 18-Nov-25 10:31 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.21 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 18-Nov-25 10:31 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.22 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 18-Nov-25 10:31 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.23 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 11-Nov-25 08:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.24 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 11-Nov-25 08:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.25 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 11-Nov-25 08:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.26 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 11-Nov-25 08:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.27 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 11-Nov-25 08:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.28 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 11-Nov-25 08:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.29 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 11-Nov-25 08:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.30 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 11-Nov-25 08:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.31 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 11-Nov-25 08:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.1.32 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 11-Nov-25 07:07 PM | 11-Nov-25 08:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2 |  | Ready for Assy | step |  |  |  | 12.4.1
12.4.2.1 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d10h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 29-Dec-25 03:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.2 |  | O.B.B.S ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d9h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 29-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.3 |  | PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d9h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 29-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.4 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d9h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 29-Dec-25 03:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.5 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d9h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 29-Dec-25 03:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.6 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d9h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 29-Dec-25 03:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.7 |  | CLEVIS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d9h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 29-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.8 |  | PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d9h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 29-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.9 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d9h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 29-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.10 |  | SHIM | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 43d7h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 29-Dec-25 01:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.11 |  | BASE FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 26-Feb-26 03:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.4.2.12 |  | ARM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 26-Feb-26 03:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.4.2.13 |  | ARM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 26-Feb-26 03:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.4.2.14 |  | ARM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 26-Feb-26 03:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.4.2.15 |  | MOUNTING BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 26-Feb-26 03:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.4.2.16 |  | HYD.CYL.BORE-Ø100,ROD-Ø56,STK-500mm,CT | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 26-Feb-26 03:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.4.2.17 |  | MOUNTING BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 26-Feb-26 03:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
12.4.2.18 |  | BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d9h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 29-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.19 |  | BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d9h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 29-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.20 |  | BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d9h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 29-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.21 |  | PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d9h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 29-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.22 |  | PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 43d9h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 29-Dec-25 03:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.23 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 14-Nov-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.24 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 14-Nov-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.25 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 60 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 14-Nov-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.26 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 14-Nov-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.27 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 14-Nov-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.28 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 14-Nov-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.29 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 14-Nov-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.30 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 14-Nov-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.31 |  | Spring Lock Washer IS 6735 - 12 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 14-Nov-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
12.4.2.32 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 11-Nov-25 07:26 PM | 14-Nov-25 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13 | 63 | Category 2 - RECOILER ASSY - Ordering & Manufacturing | TASK |  | 120d | 120d | 22 | 91 | IP | NO | 002-004 |  |  |  |  | 120d | 120d | 247d6h |  |  | 18-Aug-25 02:00 PM | 27-Dec-25 02:00 PM | 24-Mar-26 02:25 AM | 02-Aug-26 09:25 AM | 03-Nov-25 01:08 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
13.1 |  | RECOILER MANDREL ASSY. | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 105d7h |  |  | 18-Aug-25 02:00 PM | 27-Dec-25 02:00 PM |  |  | 03-Nov-25 01:08 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
13.1.1 |  | Release of PO | step |  |  |  |  | 13.1.2
13.1.1.1 |  | AIA1800826-OIL SEAL- ID190XOD220X15 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Jan-26 10:01 AM | 13-Jan-26 11:01 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.2 |  | 22234_CC_W33-SPHERICAL ROLLER BEARING-ID170XOD310X82 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Jan-26 10:01 AM | 13-Jan-26 11:01 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.3 |  | OBBS SHAFT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 11:37 AM | 25-Dec-25 12:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.4 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 11:37 AM | 25-Dec-25 12:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.5 |  | LOCKING PLATE 90X35X12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 11:57 AM | 25-Dec-25 12:57 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.6 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:07 PM | 25-Dec-25 01:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.7 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:07 PM | 25-Dec-25 01:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.8 |  | PULL ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:45 PM | 29-Dec-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.9 |  | BEARING HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:07 PM | 25-Dec-25 01:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.10 |  | CONNECTOR | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:07 PM | 25-Dec-25 01:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.11 |  | ROTORY UNION | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Jan-26 10:06 AM | 13-Jan-26 11:06 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.12 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 12:37 PM | 29-Dec-25 01:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.13 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:47 PM | 29-Dec-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.14 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:47 PM | 29-Dec-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.15 |  | ROT. HYD. CYL. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 09:36 AM | 25-Dec-25 10:36 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.16 |  | MANDREL DRUM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:47 PM | 29-Dec-25 04:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.17 |  | MANDREL SHAFT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Jan-26 10:06 AM | 13-Jan-26 11:06 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.18 |  | GREASE NIPPLE 1/4" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.19 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.20 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.22 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.23 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.24 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.25 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 120 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.26 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 120 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.27 |  | Hexagon Nut Style 1 IS 1364-Part3 - M16-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.28 |  | Hexagon Nut Style 1 IS 1364-Part3 - M24-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.29 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.30 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.31 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.32 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.33 |  | Plain Washer (Type A) IS 2016 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.34 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.35 |  | Socket Head Cap Screw IS 2269 - M20 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.36 |  | Socket Head Cap Screw IS 2269 - M24 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.37 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.38 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.39 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.40 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.41 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.1.42 |  | Socket Countersunk Head Cap Screw IS 6761 - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2 |  | Ready for Assy | step |  |  |  | 13.1.1
13.1.2.1 |  | AIA1800826-OIL SEAL- ID190XOD220X15 THK. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 02-Feb-26 12:58 PM | 02-Feb-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.2 |  | 22234_CC_W33-SPHERICAL ROLLER BEARING-ID170XOD310X82 THK. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 16-Jan-26 12:11 PM | 16-Jan-26 01:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.3 |  | OBBS SHAFT | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d9h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 11:37 AM | 02-Feb-26 02:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.4 |  | RETAINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d9h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 11:37 AM | 02-Feb-26 02:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.5 |  | LOCKING PLATE 90X35X12 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 11:57 AM | 02-Feb-26 05:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.6 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:07 PM | 02-Feb-26 05:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.7 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:07 PM | 02-Feb-26 05:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.8 |  | PULL ROD | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:45 PM | 29-Dec-25 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.9 |  | BEARING HOUSING | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:07 PM | 02-Feb-26 05:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.10 |  | CONNECTOR | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:07 PM | 02-Feb-26 05:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.11 |  | ROTORY UNION | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:04 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.1.2.12 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d2h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 12:37 PM | 02-Feb-26 02:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.13 |  | RETAINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:47 PM | 02-Feb-26 05:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.14 |  | BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 32d1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:47 PM | 02-Feb-26 05:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.15 |  | ROT. HYD. CYL. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d14h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 09:36 AM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.1.2.16 |  | MANDREL DRUM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 16d11h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:47 PM | 16-Jan-26 12:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.17 |  | MANDREL SHAFT | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:04 PM | 22-Jan-26 06:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.18 |  | GREASE NIPPLE 1/4" BSP | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.19 |  | GREASE NIPPLE 1/8" BSP | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.20 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.22 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.23 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.24 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.25 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 120 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.26 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 120 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.27 |  | Hexagon Nut Style 1 IS 1364-Part3 - M16-D-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.28 |  | Hexagon Nut Style 1 IS 1364-Part3 - M24-D-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.29 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.30 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.31 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.32 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.33 |  | Plain Washer (Type A) IS 2016 - 24 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.34 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.35 |  | Socket Head Cap Screw IS 2269 - M20 x 100 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.36 |  | Socket Head Cap Screw IS 2269 - M24 x 100 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.37 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.38 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.39 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.40 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.41 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.1.2.42 |  | Socket Countersunk Head Cap Screw IS 6761 - M12 x 45 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 10:27 AM | 29-Dec-25 11:27 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2 |  | RECOILER GEAR BOX ASSY. | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 105d8h |  |  | 18-Aug-25 02:00 PM | 27-Dec-25 02:00 PM |  |  | 03-Nov-25 01:09 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
13.2.1 |  | Release of PO | step |  |  |  |  | 13.2.2
13.2.1.1 |  | FIXED FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:52 PM | 29-Dec-25 04:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.2 |  | SLIDING FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:52 PM | 29-Dec-25 04:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.3 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:04 PM | 25-Dec-25 01:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.4 |  | HYD. CYLINDER, STK-300, ROD-Ø90 PISTON-Ø180 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 09:37 AM | 25-Dec-25 10:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.5 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:04 PM | 25-Dec-25 01:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.6 |  | DISC BRAKE STAND | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.7 |  | MOTOR BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:52 PM | 29-Dec-25 04:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.8 |  | ROTARY UNION SUPPORT ASSY. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:04 PM | 25-Dec-25 01:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.9 |  | GEARBOX INPUT RPM- 750-1500, G.R.- 13.65:1, INPUT POWER - 132KW | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 22-Jan-26 05:08 PM | 22-Jan-26 06:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.10 |  | AHG-105 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 02:43 PM | 29-Dec-25 03:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.11 |  | GEAR BOX SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:04 PM | 25-Dec-25 01:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.12 |  | MOTOR SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:53 PM | 29-Dec-25 04:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.13 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:04 PM | 25-Dec-25 01:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.14 |  | CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:04 PM | 25-Dec-25 01:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.15 |  | VERTICAL LINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:01 PM | 29-Dec-25 02:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.16 |  | LOCK PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:04 PM | 25-Dec-25 01:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.17 |  | VERTICAL LINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:01 PM | 29-Dec-25 02:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.18 |  | HORIZONTAL LINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:01 PM | 29-Dec-25 02:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.19 |  | HOR. LINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 01:01 PM | 29-Dec-25 02:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.20 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:04 PM | 25-Dec-25 01:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.21 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:04 PM | 25-Dec-25 01:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.22 |  | MOTOR SPACER OD Ø120.0 x ID Ø100.0 x 100.0 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:04 PM | 25-Dec-25 01:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.23 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:04 PM | 25-Dec-25 01:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.24 |  | 80X115X16 THKL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:04 PM | 25-Dec-25 01:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.25 |  | BRAKE PNEUMATIC- KC-PF-400 (KATEEL) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 07-Jan-26 12:00 PM | 07-Jan-26 01:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.26 |  | 132 KW MOTOR-8 POLE (CG POWER AND INDUSTRIAL SOLUTION LIMITED) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 22-Jan-26 05:08 PM | 22-Jan-26 06:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.27 |  | DOWEL PIN Ø10X33.5MM LONG. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.28 |  | 15x15x50 MM LONG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.29 |  | SHEAR BLOCK- 15X15X80MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.30 |  | STOPPER 25 X 25 X 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.31 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.32 |  | Spring Lock Washer IS 3063 - 30-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 110 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.34 |  | Socket Countersunk Head Cap Screw IS 6761 - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.35 |  | Plain Washer (Type A) IS 2016 - 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.36 |  | Spring Lock Washer IS 3063 - 16-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.37 |  | Hexagon nut IS 1363- Part2 - M16-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 130 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.40 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.41 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.43 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.45 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.47 |  | Plain Washer (Type A) IS 2016 - 39 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.48 |  | Spring Lock Washer IS 3063 - 36-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M36 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.50 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.51 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.53 |  | Spring Lock Washer IS 3063 - 12-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.54 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.55 |  | Spring Lock Washer IS 3063 - 10-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.57 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.58 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.59 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.60 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.61 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.1.62 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2 |  | Ready for Assy | step |  |  |  | 13.2.1
13.2.2.1 |  | FIXED FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 22d5h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:52 PM | 22-Jan-26 05:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.2 |  | SLIDING FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 22d5h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:52 PM | 22-Jan-26 05:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.3 |  | BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d13h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:04 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.2.2.4 |  | HYD. CYLINDER, STK-300, ROD-Ø90 PISTON-Ø180 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d14h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 09:37 AM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.2.2.5 |  | BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d13h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:04 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.2.2.6 |  | DISC BRAKE STAND | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 22d5h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 22-Jan-26 05:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.7 |  | MOTOR BASE FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 22d5h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:52 PM | 22-Jan-26 05:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.8 |  | ROTARY UNION SUPPORT ASSY. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d13h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:04 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.2.2.9 |  | GEARBOX INPUT RPM- 750-1500, G.R.- 13.65:1, INPUT POWER - 132KW | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:08 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.2.2.10 |  | AHG-105 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 16d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 02:43 PM | 16-Jan-26 12:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.11 |  | GEAR BOX SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d13h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:04 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.2.2.12 |  | MOTOR SHIM | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:53 PM | 29-Dec-25 04:53 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.13 |  | PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d13h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:04 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.2.2.14 |  | CLEVIS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d13h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:04 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.2.2.15 |  | VERTICAL LINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 16d14h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:01 PM | 16-Jan-26 12:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.16 |  | LOCK PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d13h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:04 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.2.2.17 |  | VERTICAL LINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 16d14h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:01 PM | 16-Jan-26 12:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.18 |  | HORIZONTAL LINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 16d14h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:01 PM | 16-Jan-26 12:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.19 |  | HOR. LINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 16d14h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 01:01 PM | 16-Jan-26 12:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.20 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d13h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:04 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.2.2.21 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d13h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:04 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.2.2.22 |  | MOTOR SPACER OD Ø120.0 x ID Ø100.0 x 100.0 THK. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d13h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:04 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.2.2.23 |  | PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d13h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:04 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.2.2.24 |  | 80X115X16 THKL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d13h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:04 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.2.2.25 |  | BRAKE PNEUMATIC- KC-PF-400 (KATEEL) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 26-Feb-26 03:55 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.2.2.26 |  | 132 KW MOTOR-8 POLE (CG POWER AND INDUSTRIAL SOLUTION LIMITED) | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 26-Feb-26 03:55 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.2.2.27 |  | DOWEL PIN Ø10X33.5MM LONG. | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.28 |  | 15x15x50 MM LONG | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.29 |  | SHEAR BLOCK- 15X15X80MM | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.30 |  | STOPPER 25 X 25 X 100 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.31 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.32 |  | Spring Lock Washer IS 3063 - 30-B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 110 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.34 |  | Socket Countersunk Head Cap Screw IS 6761 - M12 x 35 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.35 |  | Plain Washer (Type A) IS 2016 - 20 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.36 |  | Spring Lock Washer IS 3063 - 16-B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.37 |  | Hexagon nut IS 1363- Part2 - M16-N | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 130 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 80 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.40 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.41 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.43 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.45 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M30 x 70 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.47 |  | Plain Washer (Type A) IS 2016 - 39 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.48 |  | Spring Lock Washer IS 3063 - 36-B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M36 x 100 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.50 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.51 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.53 |  | Spring Lock Washer IS 3063 - 12-B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.54 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.55 |  | Spring Lock Washer IS 3063 - 10-B | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 25 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.57 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.58 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.59 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.60 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.61 |  | Spring Lock Washer IS 6735 - 24 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.2.2.62 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 29-Dec-25 03:55 PM | 29-Dec-25 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3 |  | RECOILER PUSHER PLATE ASSY. | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 69d9h |  |  | 18-Aug-25 02:00 PM | 27-Dec-25 02:00 PM |  |  | 12-Dec-25 10:07 AM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
13.3.1 |  | Release of PO | step |  |  |  |  | 13.3.2
13.3.1.1 |  | PUSHER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 22-Jan-26 05:10 PM | 22-Jan-26 06:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.2 |  | CYL CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:11 PM | 25-Dec-25 01:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.3 |  | HYD. CYLINDER BORE DIA-100,PISTON DIA-56,STROKE-1550,CT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 09:37 AM | 25-Dec-25 10:37 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.4 |  | BUSH BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:11 PM | 25-Dec-25 01:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.5 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:11 PM | 25-Dec-25 01:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.6 |  | GUIDE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Jan-26 03:45 PM | 13-Jan-26 04:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.7 |  | COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:11 PM | 25-Dec-25 01:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.8 |  | BUSH BLOCK - 02 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 25-Dec-25 12:11 PM | 25-Dec-25 01:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.9 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Jan-26 03:44 PM | 13-Jan-26 04:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.10 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 13-Jan-26 03:44 PM | 13-Jan-26 04:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.11 |  | COVER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 22-Jan-26 05:10 PM | 22-Jan-26 06:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.12 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.13 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.14 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.15 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.17 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.18 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.20 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.22 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.23 |  | Plain Washer (Type A) IS 2016 - 6.6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.24 |  | Spring Lock Washer IS 3063 - 16-B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.25 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.26 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.27 |  | Socket Set Screw - Cone Point IS 6094 - M6 x 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.1.28 |  | Spring Lock Washer IS 6735 - 6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 12-Dec-25 10:35 AM | 12-Dec-25 11:35 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.2 |  | Ready for Assy | step |  |  |  | 13.3.1
13.3.2.1 |  | PUSHER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.2 |  | CYL CLEVIS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:11 PM | 02-Feb-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.2.3 |  | HYD. CYLINDER BORE DIA-100,PISTON DIA-56,STROKE-1550,CT | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d14h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 09:37 AM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.4 |  | BUSH BLOCK | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:11 PM | 02-Feb-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.2.5 |  | BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:11 PM | 02-Feb-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.2.6 |  | GUIDE ROD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 40d7h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Jan-26 03:45 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.7 |  | COVER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:11 PM | 02-Feb-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.2.8 |  | BUSH BLOCK - 02 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 35d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 25-Dec-25 12:11 PM | 02-Feb-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.3.2.9 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 40d7h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Jan-26 03:44 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.10 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 40d7h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 13-Jan-26 03:44 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.11 |  | COVER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.12 |  | GREASE NIPPLE 1/8" BSP | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.13 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.14 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.15 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 80 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.17 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.18 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 25 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.20 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.22 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 16 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.23 |  | Plain Washer (Type A) IS 2016 - 6.6 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.24 |  | Spring Lock Washer IS 3063 - 16-B | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.25 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.26 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.27 |  | Socket Set Screw - Cone Point IS 6094 - M6 x 16 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.3.2.28 |  | Spring Lock Washer IS 6735 - 6 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 31d16h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 22-Jan-26 05:10 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.4 |  | RECOILER EXIT OBBS ASSY. | Subtask |  | 120d | 120d |  |  | CO | YES | [7 empty] | 94d15h |  |  | 18-Aug-25 02:00 PM | 27-Dec-25 02:00 PM |  |  | 14-Nov-25 05:00 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
13.4.1 |  | Release of PO | step |  |  |  |  | 13.4.2
13.4.1.1 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.2 |  | O.B.B.S ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 18-Nov-25 10:32 AM | 18-Nov-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.3 |  | PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 18-Nov-25 10:32 AM | 18-Nov-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.4 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 14-Nov-25 05:00 PM | 14-Nov-25 06:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.5 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 14-Nov-25 05:00 PM | 14-Nov-25 06:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.6 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 14-Nov-25 05:00 PM | 14-Nov-25 06:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.7 |  | CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 18-Nov-25 10:32 AM | 18-Nov-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.8 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 18-Nov-25 10:32 AM | 18-Nov-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.9 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 18-Nov-25 10:32 AM | 18-Nov-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.10 |  | SHIM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 18-Nov-25 10:32 AM | 18-Nov-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.11 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 26-Feb-26 03:55 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.4.1.12 |  | ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 26-Feb-26 03:55 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.4.1.13 |  | ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 26-Feb-26 03:55 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.4.1.14 |  | ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 26-Feb-26 03:55 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.4.1.15 |  | MOUNTING BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 26-Feb-26 03:55 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.4.1.16 |  | HYD.CYL.BORE- Ø100,ROD- Ø56,STK- 500mm,CT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 14-Nov-25 05:03 PM | 14-Nov-25 06:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.17 |  | MOUNTING BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 26-Feb-26 03:55 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.4.1.18 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 18-Nov-25 10:32 AM | 18-Nov-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.19 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 18-Nov-25 10:32 AM | 18-Nov-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.20 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 18-Nov-25 10:32 AM | 18-Nov-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.21 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 18-Nov-25 10:32 AM | 18-Nov-25 11:32 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.22 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 26-Feb-26 03:55 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.4.1.23 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.24 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.25 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.26 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.27 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.28 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.29 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.30 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.31 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.1.32 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Aug-25 02:00 PM | 29-Aug-25 05:00 AM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2 |  | Ready for Assy | step |  |  |  | 13.4.1
13.4.2.1 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d5h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 14-Nov-25 05:01 PM | 16-Jan-26 12:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.2 |  | O.B.B.S ROLL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 54d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 18-Nov-25 10:32 AM | 16-Jan-26 12:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.3 |  | PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 54d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 18-Nov-25 10:32 AM | 16-Jan-26 12:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.4 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d5h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 14-Nov-25 05:00 PM | 16-Jan-26 12:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.5 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d5h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 14-Nov-25 05:00 PM | 16-Jan-26 12:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.6 |  | BUSH | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 57d5h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 14-Nov-25 05:00 PM | 16-Jan-26 12:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.7 |  | CLEVIS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 54d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 18-Nov-25 10:32 AM | 16-Jan-26 12:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.8 |  | PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 54d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 18-Nov-25 10:32 AM | 16-Jan-26 12:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.9 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 54d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 18-Nov-25 10:32 AM | 16-Jan-26 12:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.10 |  | SHIM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 91d12h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 18-Nov-25 10:32 AM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.4.2.11 |  | BASE FRAME | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 26-Feb-26 03:55 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.4.2.12 |  | ARM | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 26-Feb-26 03:55 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.4.2.13 |  | ARM | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 26-Feb-26 03:55 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.4.2.14 |  | ARM | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 26-Feb-26 03:55 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.4.2.15 |  | MOUNTING BRACKET | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 26-Feb-26 03:55 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.4.2.16 |  | HYD.CYL.BORE- Ø100,ROD- Ø56,STK- 500mm,CT | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 94d14h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 14-Nov-25 05:03 PM | 26-Feb-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.4.2.17 |  | MOUNTING BRACKET | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 26-Feb-26 03:55 PM | 26-Feb-26 04:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
13.4.2.18 |  | BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 54d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 18-Nov-25 10:32 AM | 16-Jan-26 12:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.19 |  | BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 54d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 18-Nov-25 10:32 AM | 16-Jan-26 12:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.20 |  | BRACKET | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 54d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 18-Nov-25 10:32 AM | 16-Jan-26 12:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.21 |  | PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 54d3h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 18-Nov-25 10:32 AM | 16-Jan-26 12:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.22 |  | PIN | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 16-Jan-26 12:59 PM | 16-Jan-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.23 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.24 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.25 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 60 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.26 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.27 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.28 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.29 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.30 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.31 |  | Spring Lock Washer IS 6735 - 12 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.4.2.32 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 29-Aug-25 05:00 AM | 27-Dec-25 02:00 PM |  |  | 14-Nov-25 05:01 PM | 14-Nov-25 06:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
13.5 |  | RECOILER BELT WRAPPPER ASSY. | Subtask |  | 120d |  |  |  | NS | YES | [5 empty] | 120d |  |  |  |  | 18-Aug-25 02:00 PM | 27-Dec-25 02:00 PM | 24-Mar-26 02:25 AM | 02-Aug-26 09:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
14 | 75 | Category 2 - SQUEEZE ROLL ASSY. - Ordering & Manufacturing | TASK |  | 90d | 90d | 31 | 89 | IP | NO | 013-006 |  |  |  |  | 90d | 90d | 217d13h |  |  | 15-Aug-25 01:00 AM | 21-Nov-25 01:00 PM | 26-Mar-26 02:25 AM | 02-Jul-26 02:25 PM | 03-Nov-25 01:12 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
14.1 |  | SINGLE SQUEEZE ROLL ASSY. (8 Qty's) | Subtask |  | 90d | 90d |  |  | IP | YES | [5 empty] | 1d |  | 128d13h |  |  | 15-Aug-25 01:00 AM | 21-Nov-25 01:00 PM |  | 27-Mar-26 02:25 AM | 03-Nov-25 01:12 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
14.1.1 |  | Release of PO | step |  |  |  |  | 14.1.2
14.1.1.1 |  | GUIDE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d8h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 21-Nov-25 01:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.2 |  | GUIDE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d8h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 21-Nov-25 01:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.3 |  | BASE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d8h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 21-Nov-25 01:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.4 |  | MOUNTING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d8h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 21-Nov-25 01:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.5 |  | GUIDE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d8h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 21-Nov-25 01:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.6 |  | LEAD SCREW | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d8h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 21-Nov-25 01:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.7 |  | GUIDE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d8h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 21-Nov-25 01:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.8 |  | ADAPTOR | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d8h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 21-Nov-25 01:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.9 |  | TOP SQUEEZE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.10 |  | BOTTOM SQUEEZE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.11 |  | TIE BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d8h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 21-Nov-25 01:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.12 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d8h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.13 |  | HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d8h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.14 |  | ROLL COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d8h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 21-Nov-25 01:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.15 |  | PNEU. CYL. BORE-100,ROD- 25,STK-80 MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 03-Nov-25 01:13 PM | 03-Nov-25 02:13 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.16 |  | Bearing Unit-Take up, Make- SKF/EQ,Shaft Dia-60mm,Model No. UCT 212,Housing- T 212/Y,Bearing- UC 212 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d8h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:04 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.17 |  | STOPPER 10X10X40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.18 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.19 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.20 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M30-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.21 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.22 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.23 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.24 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.25 |  | Plain Washer (Type B) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.26 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.27 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.28 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.29 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.30 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.31 |  | Spring Lock Washer IS 6735 - 10 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.1.32 |  | Plain Washer (Type B) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2 |  | Ready for Assy | step |  |  |  | 14.1.1
14.1.2.1 |  | GUIDE PLATE | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d8h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.2 |  | GUIDE PLATE | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d8h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.3 |  | BASE PLATE | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d8h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.4 |  | MOUNTING PLATE | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d8h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.5 |  | GUIDE PLATE | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d8h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.6 |  | LEAD SCREW | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d8h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.7 |  | GUIDE PLATE | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d8h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.8 |  | ADAPTOR | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d8h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.9 |  | TOP SQUEEZE ROLL | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d8h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.10 |  | BOTTOM SQUEEZE ROLL | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d8h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.11 |  | TIE BRACKET | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d8h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.12 |  | BASE FRAME | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 100d8h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.13 |  | HOUSING | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 100d8h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.14 |  | ROLL COVER | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d8h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.15 |  | PNEU. CYL. BORE-100,ROD- 25,STK-80 MM | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d8h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.16 |  | Bearing Unit-Take up, Make- SKF/EQ,Shaft Dia-60mm,Model No. UCT 212,Housing- T 212/Y,Bearing- UC 212 | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 100d8h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:04 PM | 02-Mar-26 04:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.17 |  | STOPPER 10X10X40 | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.18 |  | SHEAR BIOCK- 10x10x50mm | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.19 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.20 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M30-N | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.21 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.22 |  | Spring Lock Washer IS 6735 - 16 | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.23 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.24 |  | Spring Lock Washer IS 6735 - 12 | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.25 |  | Plain Washer (Type B) IS 2016 - 14 | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.26 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.27 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.28 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.29 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.30 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.31 |  | Spring Lock Washer IS 6735 - 10 | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.1.2.32 |  | Plain Washer (Type B) IS 2016 - 11 | date |  | 80d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 12-Nov-25 01:03 PM | 12-Nov-25 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.2 |  | VERTICAL SQUEEZE ROLL ASSY.@CAG | Subtask |  | 90d |  |  |  | NS | YES | [5 empty] | 90d |  |  |  |  | 15-Aug-25 01:00 AM | 21-Nov-25 01:00 PM | 26-Mar-26 02:25 AM | 02-Jul-26 02:25 PM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
14.3 |  | DOUBLE SQUEEZE ROLL ASSY. @ CHROMATIC TANK | Subtask |  | 90d |  |  |  | NS | YES | [5 empty] | 90d |  |  |  |  | 15-Aug-25 01:00 AM | 21-Nov-25 01:00 PM | 26-Mar-26 02:25 AM | 02-Jul-26 02:25 PM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
14.4 |  | PORTER BAR @ CLANING SECTION SQZ ROLL REMOVAL | Subtask |  | 90d | 90d |  |  | IP | YES | [5 empty] | 80d | 80d | 80d1h |  |  | 15-Aug-25 01:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 23-Mar-26 09:47 AM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
14.4.1 |  | Release of PO | step |  |  |  |  | 14.4.2
14.4.1.1 |  | Porter Bar | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 23-Mar-26 09:48 AM | 23-Mar-26 10:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.4.1.2 |  | PLATE 550.0X400.0X25.0 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 23-Mar-26 09:48 AM | 23-Mar-26 10:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.4.1.3 |  | STUD 350.0MM LONG,M20.0 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 23-Mar-26 09:48 AM | 23-Mar-26 10:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.4.1.4 |  | 2-Leg Chain Sling | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 23-Mar-26 09:48 AM | 23-Mar-26 10:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.4.1.5 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N, CL-8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 23-Mar-26 09:48 AM | 23-Mar-26 10:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.4.1.6 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 23-Mar-26 09:48 AM | 23-Mar-26 10:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.4.1.7 |  | Socket Set Screw - Full Dog Point IS 6094 - M8 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 23-Mar-26 09:48 AM | 23-Mar-26 10:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.4.2 |  | Ready for Assy | step |  |  |  | 14.4.1
14.4.2.1 |  | Porter Bar | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 80d |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 23-Mar-26 09:48 AM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.4.2.2 |  | PLATE 550.0X400.0X25.0 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 80d |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 23-Mar-26 09:48 AM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.4.2.3 |  | STUD 350.0MM LONG,M20.0 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 80d |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 23-Mar-26 09:48 AM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.4.2.4 |  | 2-Leg Chain Sling | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 80d |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 23-Mar-26 09:48 AM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.4.2.5 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N, CL-8 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 80d |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 23-Mar-26 09:48 AM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.4.2.6 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 80d |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 23-Mar-26 09:48 AM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.4.2.7 |  | Socket Set Screw - Full Dog Point IS 6094 - M8 x 40 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 80d |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 23-Mar-26 09:48 AM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
14.5 |  | SINGLE SQUEEZE ROLL TRAY ASSY. #2 | Subtask |  | 90d | 90d |  |  | IP | YES | [5 empty] | 80d | 80d | 134d9h |  |  | 15-Aug-25 01:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 22-Jan-26 11:00 AM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
14.5.1 |  | Release of PO | step |  |  |  |  | 14.5.2
14.5.1.1 |  | TRAY | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:39 PM | 02-Mar-26 05:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.5.2 |  | Ready for Assy | step |  |  |  | 14.5.1
14.5.2.1 |  | TRAY | date |  | 80d |  |  |  | NS | YES | [5 empty] | 80d |  |  |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM | 26-Mar-26 02:25 AM | 22-Jun-26 01:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.6 |  | SINGLE SQUEEZE ROLL TRAY ASSY. #1 ( REQUIRED QTY:- 06 ) | Subtask |  | 90d | 90d |  |  | IP | YES | [5 empty] | 80d | 80d | 134d9h |  |  | 15-Aug-25 01:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 22-Jan-26 11:00 AM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
14.6.1 |  | Release of PO | step |  |  |  |  | 14.6.2
14.6.1.1 |  | TRAY | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:39 PM | 02-Mar-26 05:39 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.6.2 |  | Ready for Assy | step |  |  |  | 14.6.1
14.6.2.1 |  | TRAY | date |  | 80d |  |  |  | NS | YES | [5 empty] | 80d |  |  |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM | 26-Mar-26 02:25 AM | 22-Jun-26 01:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7 |  | SINGLE SQUEEZE ROLL .RINSING TANK ASSY.(2QTY) | Subtask |  | 90d | 90d |  |  | IP | YES | [5 empty] | 1d |  | 55d9h |  |  | 15-Aug-25 01:00 AM | 21-Nov-25 01:00 PM |  | 27-Mar-26 02:25 AM | 22-Jan-26 11:00 AM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
14.7.1 |  | Release of PO | step |  |  |  |  | 14.7.2
14.7.1.1 |  | GUIDE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.2 |  | GUIDE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.3 |  | BASE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.4 |  | MOUNTING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.5 |  | GUIDE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.6 |  | LEAD SCREW | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.7 |  | GUIDE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.8 |  | ADAPTOR | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.9 |  | TOP SQUEEZE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.10 |  | BOTTOM SQUEEZE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.11 |  | TIE BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.12 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.13 |  | HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.14 |  | ROLL COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.15 |  | PNEU. CYL. BORE-100,ROD- 25,STK-80 MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.16 |  | Bearing Unit-Take up, Make- SKF/EQ,Shaft Dia-60mm,Model No. UCT 212,Housing- T 212/Y,Bearing- UC 212 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.17 |  | STOPPER 10X10X40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.18 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.19 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.20 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M30-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.21 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.22 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.23 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.24 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.25 |  | Plain Washer (Type B) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.26 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.27 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.28 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.29 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.30 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.31 |  | Spring Lock Washer IS 6735 - 10 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.1.32 |  | Plain Washer (Type B) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:41 PM | 02-Mar-26 05:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2 |  | Ready for Assy | step |  |  |  | 14.7.1
14.7.2.1 |  | GUIDE PLATE | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.2 |  | GUIDE PLATE | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.3 |  | BASE PLATE | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.4 |  | MOUNTING PLATE | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.5 |  | GUIDE PLATE | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.6 |  | LEAD SCREW | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.7 |  | GUIDE PLATE | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.8 |  | ADAPTOR | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.9 |  | TOP SQUEEZE ROLL | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.10 |  | BOTTOM SQUEEZE ROLL | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.11 |  | TIE BRACKET | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.12 |  | BASE FRAME | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 05-Mar-26 01:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.13 |  | HOUSING | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 05-Mar-26 01:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.14 |  | ROLL COVER | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.15 |  | PNEU. CYL. BORE-100,ROD- 25,STK-80 MM | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.16 |  | Bearing Unit-Take up, Make- SKF/EQ,Shaft Dia-60mm,Model No. UCT 212,Housing- T 212/Y,Bearing- UC 212 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.17 |  | STOPPER 10X10X40 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.18 |  | SHEAR BIOCK- 10x10x50mm | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.19 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.20 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M30-N | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.21 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.22 |  | Spring Lock Washer IS 6735 - 16 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.23 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.24 |  | Spring Lock Washer IS 6735 - 12 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.25 |  | Plain Washer (Type B) IS 2016 - 14 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.26 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.27 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.28 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.29 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.30 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.31 |  | Spring Lock Washer IS 6735 - 10 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.7.2.32 |  | Plain Washer (Type B) IS 2016 - 11 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 03-Mar-26 02:40 PM | 03-Mar-26 03:40 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8 |  | VERTICAL DOUBLE SQUEEZE ROLL ASSY. (Qty 2) | Subtask |  | 90d | 90d |  |  | IP | YES | [5 empty] | 90d | 90d | 108d17h |  |  | 15-Aug-25 01:00 AM | 21-Nov-25 01:00 PM |  | 02-Jul-26 02:25 PM | 02-Mar-26 04:35 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
14.8.1 |  | Release of PO | step |  |  |  |  | 14.8.2
14.8.1.1 |  | TOP SQUEEZE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.2 |  | BOTTOM SQUEEZE ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.3 |  | LEVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.4 |  | Foot Mounting | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.5 |  | OPEN | date |  | 10d |  |  |  | IP | YES | [5 empty] | 10d |  | 28d17h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  | 06-Apr-26 06:25 AM | 02-Mar-26 04:45 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.6 |  | LEVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.7 |  | ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.8 |  | ARM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.9 |  | TIE ROD & PIPE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.10 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.11 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.12 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.13 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.14 |  | PLATE-700.0x250.0x25.0 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.15 |  | CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.16 |  | COVER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.17 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.18 |  | BOTTOM PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.19 |  | PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.20 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.21 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.22 |  | PLATE-700x250x25THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.23 |  | (SQUARE) TUBE 80X80X6.3THK.1455.0 LONG. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 16h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 03-Mar-26 02:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.24 |  | PNU. CYL BOTTOM FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.25 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.26 |  | RIB | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.27 |  | RIB | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.28 |  | COVER PLATE - 2020x1505x2THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.29 |  | TOP PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.30 |  | BOTTOM PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.31 |  | LIFTING LUG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.32 |  | BOTTOM PLATE 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.33 |  | PLATE | date |  | 10d |  |  |  | IP | YES | [5 empty] | 10d |  | 28d17h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  | 06-Apr-26 06:25 AM | 02-Mar-26 04:45 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.34 |  | UCP 216-PILLOW BLOCK BALL BEARING-ID80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.35 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.37 |  | Spring Lock Washer IS 6735 - 10 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.38 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.40 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.41 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.42 |  | Hexagon Nut Style 1 IS 1364- Part3 - M30-W-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.43 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.44 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.45 |  | Hexagon Nut Style 1 IS 1364- Part3 - M24-W-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.46 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.47 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.49 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.52 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.53 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.54 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.55 |  | Plain Washer (Type A) IS 2016 - 7.6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.56 |  | Spring Lock Washer IS 3063 - 6- A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.58 |  | Retaining Ring (Normal) External IS 3075(Part1) - 19 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.59 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.60 |  | Plain Washer (Type A) IS 2016 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.61 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.1.62 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 15-Aug-25 01:00 AM | 26-Aug-25 05:00 AM |  |  | 02-Mar-26 04:45 PM | 02-Mar-26 05:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2 |  | Ready for Assy | step |  |  |  | 14.8.1
14.8.2.1 |  | TOP SQUEEZE ROLL | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.2 |  | BOTTOM SQUEEZE ROLL | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.3 |  | LEVER | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.4 |  | Foot Mounting | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.5 |  | OPEN | date |  | 80d |  |  |  | IP | NO | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 02-Jul-26 02:25 PM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.6 |  | LEVER | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.7 |  | ARM | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.8 |  | ARM | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.9 |  | TIE ROD & PIPE | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.10 |  | END PLATE | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.11 |  | SPACER | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.12 |  | SPACER | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.13 |  | SPACER | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.14 |  | PLATE-700.0x250.0x25.0 THK. | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.15 |  | CLEVIS | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.16 |  | COVER PLATE | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.17 |  | PIN | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.18 |  | BOTTOM PLATE | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.19 |  | PLATE | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.20 |  | PIN | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.21 |  | PIN | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.22 |  | PLATE-700x250x25THK. | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.23 |  | (SQUARE) TUBE 80X80X6.3THK.1455.0 LONG. | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d15h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 02-Mar-26 04:46 PM | 05-Mar-26 01:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.24 |  | PNU. CYL BOTTOM FRAME | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.25 |  | PIN | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.26 |  | RIB | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.27 |  | RIB | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.28 |  | COVER PLATE - 2020x1505x2THK. | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.29 |  | TOP PLATE | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.30 |  | BOTTOM PLATE | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.31 |  | LIFTING LUG | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.32 |  | BOTTOM PLATE 2 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.33 |  | PLATE | date |  | 80d |  |  |  | IP | NO | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 02-Jul-26 02:25 PM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.34 |  | UCP 216-PILLOW BLOCK BALL BEARING-ID80 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d15h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  |  | 02-Mar-26 04:46 PM | 05-Mar-26 01:21 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.35 |  | GREASE NIPPLE 1/8" BSP | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 35 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.37 |  | Spring Lock Washer IS 6735 - 10 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.38 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.40 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.41 |  | Spring Lock Washer IS 3063 - 30-A | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.42 |  | Hexagon Nut Style 1 IS 1364- Part3 - M30-W-N | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.43 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.44 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.45 |  | Hexagon Nut Style 1 IS 1364- Part3 - M24-W-N | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.46 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.47 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.49 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 25 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 25 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.52 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.53 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.54 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.55 |  | Plain Washer (Type A) IS 2016 - 7.6 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.56 |  | Spring Lock Washer IS 3063 - 6- A | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.57 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 25 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.58 |  | Retaining Ring (Normal) External IS 3075(Part1) - 19 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.59 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 60 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.60 |  | Plain Washer (Type A) IS 2016 - 24 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.61 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
14.8.2.62 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 80 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 80d |  | 98d17h |  |  | 26-Aug-25 05:00 AM | 21-Nov-25 01:00 PM |  | 22-Jun-26 01:25 AM | 02-Mar-26 04:46 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
15 | 57 | Category 1 - TENSIOMETER ASSY - Ordering & Manufacturing | TASK |  | 60d | 60d | 28 | 81 | IP | NO | 006-014 |  |  |  |  | 60d | 60d | 187d6h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 27-Mar-26 02:25 AM | 01-Jun-26 04:25 AM | 03-Nov-25 01:15 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
15.1 |  | TENSIOMETER ASSY.#1 BEFORE FURNACE ENTRY | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 50d | 50d | 177d6h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 20-May-26 08:25 PM | 03-Nov-25 01:15 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
15.1.1 |  | Release of PO | step |  |  |  |  | 15.1.2
15.1.1.1 |  | LOAD CELL: SIZE-BZV-F 04E1-12,5k-T, MAKE- HAEHNE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 06-Mar-26 10:43 AM | 06-Mar-26 11:43 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.2 |  | TOP PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.3 |  | HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.4 |  | TENSIOMETER ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.5 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.6 |  | 60X80X10_OILSEAL_AIA0600804 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.7 |  | GREASE NIPPLE 1/4" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.8 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.9 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.10 |  | Socket Head Cap Screw IS 2269 - M12 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.11 |  | Socket Head Cap Screw IS 2269 - M12 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.12 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.13 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.14 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.15 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.16 |  | Retaining Ring (Normal) External IS 3075(Part1) - 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.17 |  | 22212_E-SPH.ROLLER BRG-ID60XOD110X28 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.1.18 |  | Socket Head Cap Screw IS 2269 - M16 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 05:19 PM | 02-Mar-26 06:19 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2 |  | Ready for Assy | step |  |  |  | 15.1.1
15.1.2.1 |  | LOAD CELL: SIZE-BZV-F 04E1-12,5k-T, MAKE- HAEHNE | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 27-Mar-26 02:25 AM | 20-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.2 |  | TOP PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 03-Mar-26 01:07 PM | 05-Mar-26 12:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.3 |  | HOUSING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 03-Mar-26 01:07 PM | 05-Mar-26 12:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.4 |  | TENSIOMETER ROLL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 06-Mar-26 01:14 PM | 06-Mar-26 02:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.5 |  | BASE FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 03-Mar-26 01:11 PM | 03-Mar-26 02:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.6 |  | 60X80X10_OILSEAL_AIA0600804 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 03-Mar-26 01:12 PM | 03-Mar-26 02:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.7 |  | GREASE NIPPLE 1/4" BSP | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 06-Mar-26 01:16 PM | 06-Mar-26 02:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.8 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 90 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 06-Mar-26 01:16 PM | 06-Mar-26 02:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.9 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 06-Mar-26 01:16 PM | 06-Mar-26 02:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.10 |  | Socket Head Cap Screw IS 2269 - M12 x 30 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 06-Mar-26 01:16 PM | 06-Mar-26 02:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.11 |  | Socket Head Cap Screw IS 2269 - M12 x 60 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 06-Mar-26 01:16 PM | 06-Mar-26 02:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.12 |  | Spring Lock Washer IS 6735 - 16 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 06-Mar-26 01:16 PM | 06-Mar-26 02:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.13 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 06-Mar-26 01:16 PM | 06-Mar-26 02:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.14 |  | Spring Lock Washer IS 6735 - 24 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 06-Mar-26 01:16 PM | 06-Mar-26 02:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.15 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 60 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 06-Mar-26 01:16 PM | 06-Mar-26 02:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.16 |  | Retaining Ring (Normal) External IS 3075(Part1) - 60 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 06-Mar-26 01:16 PM | 06-Mar-26 02:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.17 |  | 22212_E-SPH.ROLLER BRG-ID60XOD110X28 THK. | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 03-Mar-26 02:18 PM | 03-Mar-26 03:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.1.2.18 |  | Socket Head Cap Screw IS 2269 - M16 x 100 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 06-Mar-26 01:16 PM | 06-Mar-26 02:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
15.2 |  | TENSIOMETER ASSY.#2 AFTER CAG | Subtask |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 27-Mar-26 02:25 AM | 01-Jun-26 04:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
16 | 18 | Category 1 - STEERING ROLL ASSY. - Engg | TASK |  | 4d | 4d |  | 3 | CO | YES | [7 empty] | 1h |  |  | 17-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  |  | 03-Nov-25 04:30 PM | 03-Nov-25 05:30 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
16.1 |  | STEERING ROLL ASSY | Subtask |  | 4d | 4d |  |  | CO | NO | [7 empty] | 1h |  |  | 17-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  |  | 03-Nov-25 04:30 PM | 03-Nov-25 05:30 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
16.1.1 |  | Completion | step
16.1.1.1 |  | SINGLE STEERING ROLL ASSY. | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 17-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  |  | 03-Nov-25 04:30 PM | 03-Nov-25 05:30 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
16.1.1.2 |  | DOUBLE STEERING ROLL ASSY. @ CAG | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 17-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  |  | 03-Nov-25 04:30 PM | 03-Nov-25 05:30 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
16.1.1.3 |  | DOUBLE STEERING ROLL ASSY. BEFORE EXIT ACC ASSY. | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 17-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  |  | 03-Nov-25 04:30 PM | 03-Nov-25 05:30 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
17 | 6 | Category 1 - COIL CAR ASSY @ UNCOILER - Engg | TASK |  | 4d | 4d |  | 4 | CO | YES | [7 empty] | 2h |  |  | 17-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  |  | 03-Nov-25 04:30 PM | 03-Nov-25 05:31 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
17.1 |  | COIL CAR ASSY @ UNCOILER | Subtask |  | 4d | 4d |  |  | CO | YES | [7 empty] | 1h |  |  | 17-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  |  | 03-Nov-25 04:31 PM | 03-Nov-25 05:31 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
17.1.1 |  | Completion | step
17.1.1.1 |  | COIL CAR ASSY. @ UNCOILER | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 17-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  |  | 03-Nov-25 04:31 PM | 03-Nov-25 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
17.1.1.2 |  | DRAG CHAIN ASSY. @ UNCOILER | date |  | 3d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 17-Oct-25 12:00 PM | 21-Oct-25 03:00 AM |  |  | 03-Nov-25 04:31 PM | 03-Nov-25 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
17.1.1.3 |  | COIL SADDLE ASSY. @ UNCOILER | date |  | 3d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 17-Oct-25 12:00 PM | 21-Oct-25 03:00 AM |  |  | 03-Nov-25 04:31 PM | 03-Nov-25 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
18 | 15 | Category 1 - TABLE - Ordering & Manufacturing | TASK |  | 60d | 120d | 33 | 92 | IP | NO | 006-003 |  |  |  |  | 120d | 120d | 245d5h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 03-Aug-26 03:25 PM | 05-Nov-25 02:18 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.1 |  | PEELER TABLE ASSY.#1 | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 50d | 50d | 151d12h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 01-Dec-25 02:53 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.1.1 |  | Release of PO | step |  |  |  |  | 18.1.2
18.1.1.1 |  | HYD. CYL. BORE DIA- 80, ROD DIA-45, STK- 325MM RC | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.2 |  | HYD CYL. BORE-63, ROD-45, STK-400, CT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.3 |  | SLIDING TABLE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.4 |  | SWIVILING TABLE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.5 |  | GUARD FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.6 |  | SUPPORT FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.7 |  | CYLINDER BRACKET - 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.8 |  | CYLINDER BRACKET - 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.9 |  | CYLINDER BRACKET - 3 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.10 |  | BUSH BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.11 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.12 |  | PLATE- 200X200X25 THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.13 |  | PLATE - 200X60X20 THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.14 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.15 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.16 |  | CYL CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.17 |  | PLATE - 780X110X25 THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.18 |  | CYL. PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.19 |  | CLY. CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.20 |  | NYLON PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.21 |  | BUSH BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.22 |  | CLAMP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.23 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.24 |  | KNIFE OPENER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.25 |  | L-PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.26 |  | HORIZONTAL LINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.27 |  | VERTICAL LINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.28 |  | CLAMP PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.29 |  | CYL.BASE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.30 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.31 |  | RIB | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.32 |  | ISMC 200X75X670 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.33 |  | RIB | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.34 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.35 |  | Spring Lock Washer IS 6735 - 10 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.37 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.38 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.40 |  | Socket Countersunk Head Cap Screw IS 6761 - M8 x 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.41 |  | Socket Head Cap Screw IS 2269 - M10 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.42 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.43 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.45 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.46 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.48 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.49 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.50 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.53 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.54 |  | Spring Lock Washer IS 6735 - 8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.1.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:10 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2 |  | Ready for Assy | step |  |  |  | 18.1.1
18.1.2.1 |  | HYD. CYL. BORE DIA- 80, ROD DIA-45, STK- 325MM RC | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d3h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 11-Mar-26 09:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.2 |  | HYD CYL. BORE-63, ROD-45, STK-400, CT | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:10 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.3 |  | SLIDING TABLE | date |  | 50d |  |  |  | IP | YES | [5 empty] | 1d |  | 19d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 23-Mar-26 09:00 PM | 02-Mar-26 04:10 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.4 |  | SWIVILING TABLE | date |  | 50d |  |  |  | IP | YES | [5 empty] | 1d |  | 19d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 23-Mar-26 09:00 PM | 02-Mar-26 04:10 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.5 |  | GUARD FRAME | date |  | 50d |  |  |  | IP | YES | [5 empty] | 1d |  | 19d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 23-Mar-26 09:00 PM | 02-Mar-26 04:10 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.6 |  | SUPPORT FRAME | date |  | 50d |  |  |  | IP | YES | [5 empty] | 1d |  | 19d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 23-Mar-26 09:00 PM | 02-Mar-26 04:10 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.7 |  | CYLINDER BRACKET - 1 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.8 |  | CYLINDER BRACKET - 2 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.9 |  | CYLINDER BRACKET - 3 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.10 |  | BUSH BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.11 |  | BUSH | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:10 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.12 |  | PLATE- 200X200X25 THK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.13 |  | PLATE - 200X60X20 THK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.14 |  | PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.15 |  | KEEPER PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.16 |  | CYL CLEVIS | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.17 |  | PLATE - 780X110X25 THK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.18 |  | CYL. PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.19 |  | CLY. CLEVIS | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.20 |  | NYLON PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 05-Mar-26 01:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.21 |  | BUSH BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.22 |  | CLAMP | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.23 |  | BUSH | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:10 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.24 |  | KNIFE OPENER | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:10 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.25 |  | L-PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.26 |  | HORIZONTAL LINER | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:10 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.27 |  | VERTICAL LINER | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:10 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.28 |  | CLAMP PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.29 |  | CYL.BASE PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.30 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.31 |  | RIB | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.32 |  | ISMC 200X75X670 | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:10 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.33 |  | RIB | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.34 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.35 |  | Spring Lock Washer IS 6735 - 10 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 60 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.37 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.38 |  | Spring Lock Washer IS 6735 - 12 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.40 |  | Socket Countersunk Head Cap Screw IS 6761 - M8 x 20 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.41 |  | Socket Head Cap Screw IS 2269 - M10 x 25 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.42 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.43 |  | Spring Lock Washer IS 6735 - 20 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.45 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.46 |  | Spring Lock Washer IS 6735 - 16 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.48 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 30 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.49 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 20 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.50 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.53 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.54 |  | Spring Lock Washer IS 6735 - 8 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.1.2.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 20 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:10 PM | 17-Mar-26 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2 |  | PEELER TABLE ASSY.#2 | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 50d | 50d | 72d3h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 26-Feb-26 12:05 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.2.1 |  | Release of PO | step |  |  |  |  | 18.2.2
18.2.1.1 |  | HYD. CYL. BORE DIA-80, ROD DIA-45, STK-425MM RC | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.2 |  | HYD CYL. BORE-63, ROD- 45, STK-325, CT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.3 |  | SLIDING TABLE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.4 |  | SWIVILING TABLE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.5 |  | GUARD FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.6 |  | SUPPORT FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.7 |  | CYLINDER BRACKET - 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.8 |  | CYLINDER BRACKET - 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.9 |  | CYLINDER BRACKET - 3 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.10 |  | BUSH BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.11 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.12 |  | PLATE- 200X350X25 THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.13 |  | PLATE - 200X60X20 THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.14 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.15 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.16 |  | CYL CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.17 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.18 |  | CYL. PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.19 |  | CLY. CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.20 |  | NYLON PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.21 |  | BUSH BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.22 |  | CLAMP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.23 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.24 |  | KNIFE OPENER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.1.25 |  | L-PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.26 |  | HORIZONTAL LINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.27 |  | VERTICAL LINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.28 |  | CLAMP PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.29 |  | CYL.BASE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.30 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.31 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.32 |  | Spring Lock Washer IS 6735 - 10 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.34 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.35 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.37 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.38 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.40 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.41 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.43 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.44 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.45 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.47 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.48 |  | Spring Lock Washer IS 6735 - 8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.50 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.51 |  | Socket Countersunk Head Cap Screw IS 6761 - M8 x 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.52 |  | Socket Head Cap Screw IS 2269 - M10 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.53 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.54 |  | Plain Washer (Type B) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.1.56 |  | SHEAR BLOCK- 10X10X50MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:11 PM | 02-Mar-26 05:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2 |  | Ready for Assy | step |  |  |  | 18.2.1
18.2.2.1 |  | HYD. CYL. BORE DIA-80, ROD DIA-45, STK-425MM RC | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.2 |  | HYD CYL. BORE-63, ROD- 45, STK-325, CT | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:11 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.3 |  | SLIDING TABLE | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:11 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.4 |  | SWIVILING TABLE | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:11 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.5 |  | GUARD FRAME | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:11 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.6 |  | SUPPORT FRAME | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:11 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.7 |  | CYLINDER BRACKET - 1 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.8 |  | CYLINDER BRACKET - 2 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.9 |  | CYLINDER BRACKET - 3 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.10 |  | BUSH BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.11 |  | BUSH | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:11 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.12 |  | PLATE- 200X350X25 THK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.13 |  | PLATE - 200X60X20 THK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.14 |  | PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.15 |  | KEEPER PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.16 |  | CYL CLEVIS | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.17 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.18 |  | CYL. PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.19 |  | CLY. CLEVIS | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.20 |  | NYLON PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 05-Mar-26 01:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.21 |  | BUSH BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.22 |  | CLAMP | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.23 |  | BUSH | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:11 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.24 |  | KNIFE OPENER | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:11 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.2.2.25 |  | L-PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.26 |  | HORIZONTAL LINER | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:11 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.27 |  | VERTICAL LINER | date |  | 50d |  |  |  | IP | YES | [5 empty] | 50d |  | 68d10h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 02-Mar-26 04:11 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.28 |  | CLAMP PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.29 |  | CYL.BASE PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.30 |  | GREASE NIPPLE 1/8" BSP | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.31 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.32 |  | Spring Lock Washer IS 6735 - 10 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 60 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.34 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.35 |  | Spring Lock Washer IS 6735 - 12 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.37 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.38 |  | Spring Lock Washer IS 6735 - 20 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.40 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.41 |  | Spring Lock Washer IS 6735 - 16 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.43 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 30 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.44 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 20 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.45 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.47 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.48 |  | Spring Lock Washer IS 6735 - 8 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 20 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.50 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 25 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.51 |  | Socket Countersunk Head Cap Screw IS 6761 - M8 x 20 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.52 |  | Socket Head Cap Screw IS 2269 - M10 x 25 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.53 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.54 |  | Plain Washer (Type B) IS 2016 - 22 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.2.2.56 |  | SHEAR BLOCK- 10X10X50MM | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 13d11h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 02-Mar-26 04:11 PM | 17-Mar-26 12:52 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3 |  | ENTRY SCRAP DOWN TABLE ASSY#1 | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 1d |  | 126d5h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 26-Mar-26 02:25 AM | 05-Nov-25 02:18 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.3.1 |  | Release of PO | step |  |  |  |  | 18.3.2
18.3.1.1 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:20 PM | 05-Nov-25 03:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.2 |  | END PLATE Ø30 X 10MM THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:20 PM | 05-Nov-25 03:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.3 |  | PLATE 240 X 100 X 20MM THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:20 PM | 05-Nov-25 03:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.4 |  | CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:20 PM | 05-Nov-25 03:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.5 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:20 PM | 05-Nov-25 03:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.6 |  | PLATE 310X180X20THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:20 PM | 05-Nov-25 03:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.7 |  | BAKELITE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d4h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 10:40 AM | 03-Mar-26 10:11 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.8 |  | TABLE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d4h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 10:40 AM | 03-Mar-26 10:11 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.9 |  | CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:20 PM | 05-Nov-25 03:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.10 |  | SUPPORT FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:20 PM | 05-Nov-25 03:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.11 |  | AS PER DRAWING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:20 PM | 05-Nov-25 03:20 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.12 |  | PNU. CYLINDER BORE DIA-100,ROD- DIA-25,STROKE-80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d4h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 10:40 AM | 03-Mar-26 10:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.13 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d4h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 10:40 AM | 03-Mar-26 10:22 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.14 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 10:40 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.15 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 10:40 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.16 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 10:40 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.17 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 10:40 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.18 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 10:40 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.19 |  | Spring Lock Washer IS 6735 - 8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 10:40 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.20 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 10:40 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.1.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 10:40 AM | 12-Nov-25 11:40 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2 |  | Ready for Assy | step |  |  |  | 18.3.1
18.3.2.1 |  | PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:20 PM | 03-Mar-26 10:11 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.2 |  | END PLATE Ø30 X 10MM THK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:20 PM | 03-Mar-26 10:11 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.3 |  | PLATE 240 X 100 X 20MM THK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:20 PM | 03-Mar-26 10:11 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.4 |  | CLEVIS | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:20 PM | 03-Mar-26 10:11 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.5 |  | PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:20 PM | 03-Mar-26 10:11 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.6 |  | PLATE 310X180X20THK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:20 PM | 03-Mar-26 10:11 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.7 |  | BAKELITE PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d4h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 10:40 AM | 03-Mar-26 10:11 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.8 |  | TABLE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d4h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 10:40 AM | 03-Mar-26 10:11 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.9 |  | CLEVIS | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:20 PM | 03-Mar-26 10:18 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.10 |  | SUPPORT FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:20 PM | 03-Mar-26 10:18 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.11 |  | AS PER DRAWING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:20 PM | 03-Mar-26 10:18 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.12 |  | PNU. CYLINDER BORE DIA-100,ROD- DIA-25,STROKE-80 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d4h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 10:40 AM | 03-Mar-26 10:21 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.13 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d4h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 10:40 AM | 03-Mar-26 10:22 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.14 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 10:40 AM | 05-Mar-26 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.15 |  | Spring Lock Washer IS 6735 - 16 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 10:40 AM | 05-Mar-26 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.16 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 10:40 AM | 05-Mar-26 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.17 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 20 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 10:40 AM | 05-Mar-26 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.18 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 10:40 AM | 05-Mar-26 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.19 |  | Spring Lock Washer IS 6735 - 8 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 10:40 AM | 05-Mar-26 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.20 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 10:40 AM | 05-Mar-26 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.3.2.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 10:40 AM | 05-Mar-26 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4 |  | ENTRY SCRAP DOWN TABLE ASSY#2 | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 1d |  | 126d4h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 26-Mar-26 02:25 AM | 05-Nov-25 02:31 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.4.1 |  | Release of PO | step |  |  |  |  | 18.4.2
18.4.1.1 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:31 PM | 05-Nov-25 03:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.2 |  | END PLATE Ø30 X 10MM THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:31 PM | 05-Nov-25 03:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.3 |  | PLATE 240 X 100 X 20MM THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:31 PM | 05-Nov-25 03:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.4 |  | CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:31 PM | 05-Nov-25 03:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.5 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:31 PM | 05-Nov-25 03:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.6 |  | PLATE 310X180X20THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:31 PM | 05-Nov-25 03:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.7 |  | BAKELITE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d4h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 11:00 AM | 03-Mar-26 10:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.8 |  | TABLE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d4h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 11:00 AM | 03-Mar-26 10:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.9 |  | CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:31 PM | 05-Nov-25 03:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.10 |  | SUPPORT FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:31 PM | 05-Nov-25 03:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.11 |  | AS PER DRAWING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 05-Nov-25 02:31 PM | 05-Nov-25 03:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.12 |  | PNU. CYLINDER BORE DIA-100,ROD- DIA-25,STROKE-80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d4h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 11:00 AM | 03-Mar-26 10:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.13 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d4h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 11:00 AM | 03-Mar-26 10:24 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.14 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 11:00 AM | 12-Nov-25 12:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.15 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 11:00 AM | 12-Nov-25 12:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.16 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 11:00 AM | 12-Nov-25 12:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.17 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 11:00 AM | 12-Nov-25 12:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.18 |  | Spring Lock Washer IS 6735 - 8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 11:00 AM | 12-Nov-25 12:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.19 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 11:00 AM | 12-Nov-25 12:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.20 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 11:00 AM | 12-Nov-25 12:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.1.21 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 11:00 AM | 12-Nov-25 12:00 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2 |  | Ready for Assy | step |  |  |  | 18.4.1
18.4.2.1 |  | PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:31 PM | 03-Mar-26 10:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.2 |  | END PLATE Ø30 X 10MM THK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:31 PM | 03-Mar-26 10:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.3 |  | PLATE 240 X 100 X 20MM THK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:31 PM | 03-Mar-26 10:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.4 |  | CLEVIS | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:31 PM | 03-Mar-26 10:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.5 |  | PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:31 PM | 03-Mar-26 10:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.6 |  | PLATE 310X180X20THK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:31 PM | 03-Mar-26 10:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.7 |  | BAKELITE PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d4h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 11:00 AM | 03-Mar-26 10:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.8 |  | TABLE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d4h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 11:00 AM | 03-Mar-26 10:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.9 |  | CLEVIS | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:31 PM | 03-Mar-26 10:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.10 |  | SUPPORT FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:31 PM | 03-Mar-26 10:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.11 |  | AS PER DRAWING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 107d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 05-Nov-25 02:31 PM | 03-Mar-26 10:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.12 |  | PNU. CYLINDER BORE DIA-100,ROD- DIA-25,STROKE-80 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d4h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 11:00 AM | 03-Mar-26 10:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.13 |  | UCP 210-PILLOW BLOCK BALL BEARING-ID50 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d4h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 11:00 AM | 03-Mar-26 10:25 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.14 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 11:00 AM | 05-Mar-26 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.15 |  | Spring Lock Washer IS 6735 - 16 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 11:00 AM | 05-Mar-26 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.16 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 11:00 AM | 05-Mar-26 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.17 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 11:00 AM | 05-Mar-26 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.18 |  | Spring Lock Washer IS 6735 - 8 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 11:00 AM | 05-Mar-26 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.19 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 11:00 AM | 05-Mar-26 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.20 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 11:00 AM | 05-Mar-26 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.4.2.21 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d6h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 11:00 AM | 05-Mar-26 01:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5 |  | PASSING TABLE ASSY#1 | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 50d | 50d | 72d2h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 18-May-26 08:25 PM | 26-Feb-26 01:07 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.5.1 |  | Release of PO | step |  |  |  |  | 18.5.2
18.5.1.1 |  | BAKELITE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.1.2 |  | BAKELITE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.1.3 |  | ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.1.4 |  | SHAFT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.1.5 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.1.6 |  | LOCK PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.1.7 |  | PLATE 150.00 X 150.00 X 20.00 MM THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.1.8 |  | BAKELITE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.1.9 |  | TABLE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.1.10 |  | SUPPORT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.1.11 |  | 6305-2Z-BALL BEARING- ID25XOD62X17 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.1.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.1.13 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.1.14 |  | Hexagon nut IS 1363-Part2 - M20-C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.1.15 |  | Hexagon Nut Style 1 IS 1364- Part3 - M20-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.1.16 |  | Plain Washer (Type A) IS 2016 - 6.6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.1.17 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.1.18 |  | Plain Washer (Type B) IS 2016 - 6.6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.1.19 |  | Spring Lock Washer IS 6735 - 6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.1.20 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.1.21 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 17-Mar-26 12:58 PM | 17-Mar-26 01:58 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.2 |  | Ready for Assy | step |  |  |  | 18.5.1
18.5.2.1 |  | BAKELITE PLATE | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 18-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.2.2 |  | BAKELITE PLATE | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 18-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.2.3 |  | ROLL | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 18-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.2.4 |  | SHAFT | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 18-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.2.5 |  | SPACER | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 18-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.2.6 |  | LOCK PLATE | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 18-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.2.7 |  | PLATE 150.00 X 150.00 X 20.00 MM THK | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 18-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.2.8 |  | BAKELITE PLATE | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 18-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.2.9 |  | TABLE | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 18-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.2.10 |  | SUPPORT | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 18-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.2.11 |  | 6305-2Z-BALL BEARING- ID25XOD62X17 THK. | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 17-Mar-26 01:04 PM | 17-Mar-26 02:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.2.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 25 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 17-Mar-26 01:04 PM | 17-Mar-26 02:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.5.2.13 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 17-Mar-26 01:04 PM | 17-Mar-26 02:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.2.14 |  | Hexagon nut IS 1363-Part2 - M20-C | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 17-Mar-26 01:04 PM | 17-Mar-26 02:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.2.15 |  | Hexagon Nut Style 1 IS 1364- Part3 - M20-D-N | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 17-Mar-26 01:04 PM | 17-Mar-26 02:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.2.16 |  | Plain Washer (Type A) IS 2016 - 6.6 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 17-Mar-26 01:04 PM | 17-Mar-26 02:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.2.17 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 17-Mar-26 01:04 PM | 17-Mar-26 02:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.2.18 |  | Plain Washer (Type B) IS 2016 - 6.6 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 17-Mar-26 01:04 PM | 17-Mar-26 02:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.2.19 |  | Spring Lock Washer IS 6735 - 6 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 17-Mar-26 01:04 PM | 17-Mar-26 02:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.2.20 |  | Spring Lock Washer IS 6735 - 20 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 17-Mar-26 01:04 PM | 17-Mar-26 02:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.5.2.21 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 17-Mar-26 01:04 PM | 17-Mar-26 02:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.6 |  | PASSING TABLE ASSY#2 | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 60d | 60d | 82d2h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 29-May-26 01:25 PM | 26-Feb-26 01:07 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.6.1 |  | Release of PO | step |  |  |  |  | 18.6.2
18.6.1.1 |  | BAKELITE PLATE 592.00x300.00 x10.00THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.6.1.2 |  | PLATE 150X120X18.00 THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.6.1.3 |  | TABLE | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.6.1.4 |  | SUPPORT FRAME | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.6.1.5 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.6.1.6 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.6.1.7 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.6.1.8 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.6.2 |  | Ready for Assy | step |  |  |  | 18.6.1
18.6.2.1 |  | BAKELITE PLATE 592.00x300.00 x10.00THK | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.6.2.2 |  | PLATE 150X120X18.00 THK | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.6.2.3 |  | TABLE | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.6.2.4 |  | SUPPORT FRAME | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.6.2.5 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.6.2.6 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.6.2.7 |  | Spring Lock Washer IS 6735 - 16 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.6.2.8 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.7 |  | PASSING TABLE ASSY#3 (BEFORE PINCH ROLL#4) | Subtask |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 29-May-26 01:25 PM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.8 |  | PASSING TABLE ASSY #4 | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 120d | 120d | 141d17h |  |  | 22-Oct-25 03:00 AM | 02-Mar-26 04:00 PM |  | 03-Aug-26 03:25 PM | 26-Feb-26 03:59 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.8.1 |  | Release of PO | step |  |  |  |  | 18.8.2
18.8.1.1 |  | PASSING TABLE-01 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.8.1.2 |  | PASSING TABLE-02 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.8.1.3 |  | PASSING TABLE-03 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.8.1.4 |  | PIPE SIZE-O.D.-80xI.D.- 60x1608 LONG | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.8.1.5 |  | SHAFT | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.8.1.6 |  | SPACER | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.8.1.7 |  | BASE PLATE- 220x220x20thk. | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.8.1.8 |  | 6305-2Z-BALL BEARING- ID25XOD62X17 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 19-Mar-26 12:35 PM | 19-Mar-26 01:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.8.1.9 |  | Hexagon nut IS 1363- Part2 - M20-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 19-Mar-26 12:35 PM | 19-Mar-26 01:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.8.1.10 |  | Hexagon Head Screw (Grade B) IS 1364(Part2) - M16 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 19-Mar-26 12:35 PM | 19-Mar-26 01:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.8.1.11 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 19-Mar-26 12:35 PM | 19-Mar-26 01:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.8.1.12 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 19-Mar-26 12:35 PM | 19-Mar-26 01:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.8.2 |  | Ready for Assy | step |  |  |  | 18.8.1
18.8.2.1 |  | PASSING TABLE-01 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.8.2.2 |  | PASSING TABLE-02 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.8.2.3 |  | PASSING TABLE-03 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.8.2.4 |  | PIPE SIZE-O.D.-80xI.D.- 60x1608 LONG | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.8.2.5 |  | SHAFT | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.8.2.6 |  | SPACER | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.8.2.7 |  | BASE PLATE- 220x220x20thk. | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.8.2.8 |  | 6305-2Z-BALL BEARING- ID25XOD62X17 THK. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 19-Mar-26 12:35 PM | 19-Mar-26 01:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.8.2.9 |  | Hexagon nut IS 1363- Part2 - M20-N | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 19-Mar-26 12:35 PM | 19-Mar-26 01:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.8.2.10 |  | Hexagon Head Screw (Grade B) IS 1364(Part2) - M16 x 40 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 19-Mar-26 12:35 PM | 19-Mar-26 01:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.8.2.11 |  | Spring Lock Washer IS 6735 - 16 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 19-Mar-26 12:35 PM | 19-Mar-26 01:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.8.2.12 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 19-Mar-26 12:35 PM | 19-Mar-26 01:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9 |  | PASSING TABLE ASSY#4 (PINCH ROLL#4 & SEAM WELDER) | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 60d | 60d | 161d12h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 29-May-26 01:25 PM | 01-Dec-25 02:54 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.9.1 |  | Release of PO | step |  |  |  |  | 18.9.2
18.9.1.1 |  | PASSING TABLE-01 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.1.2 |  | PASSING TABLE-02 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.1.3 |  | PASSING TABLE-03 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.1.4 |  | PIPE SIZE-O.D.-80xI.D.- 60x1608 LONG | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.1.5 |  | SHAFT | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.1.6 |  | SPACER | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.1.7 |  | BASE PLATE- 220x220x20thk. | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.1.8 |  | 6305-2Z-BALL BEARING- ID25XOD62X17 THK. | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.1.9 |  | Hexagon nut IS 1363- Part2 - M20-N | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.1.10 |  | Hexagon Head Screw (Grade B) IS 1364(Part2) - M16 x 40 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.1.11 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.1.12 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.2 |  | Ready for Assy | step |  |  |  | 18.9.1
18.9.2.1 |  | PASSING TABLE-01 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.2.2 |  | PASSING TABLE-02 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.2.3 |  | PASSING TABLE-03 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.2.4 |  | PIPE SIZE-O.D.-80xI.D.- 60x1608 LONG | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.2.5 |  | SHAFT | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.2.6 |  | SPACER | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.2.7 |  | BASE PLATE- 220x220x20thk. | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.2.8 |  | 6305-2Z-BALL BEARING- ID25XOD62X17 THK. | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.2.9 |  | Hexagon nut IS 1363- Part2 - M20-N | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.2.10 |  | Hexagon Head Screw (Grade B) IS 1364(Part2) - M16 x 40 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.2.11 |  | Spring Lock Washer IS 6735 - 16 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.9.2.12 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10 |  | PASSING TABLE ASSY#5 (SEAM WELDER & PINCH ROLL#5) | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 60d | 60d | 81d17h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 29-May-26 01:25 PM | 26-Feb-26 03:59 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.10.1 |  | Release of PO | step |  |  |  |  | 18.10.2
18.10.1.1 |  | NYLON PAD | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.1.2 |  | PLATE 200 X 120 X 16 MM THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.1.3 |  | RIB 80 X 60 X 12 MM THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.1.4 |  | RIB 130 X 60 X 12 MM THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.1.5 |  | TABLE | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.1.6 |  | COLUMN | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.1.7 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 35 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.1.8 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.1.9 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.2 |  | Ready for Assy | step |  |  |  | 18.10.1
18.10.2.1 |  | NYLON PAD | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.2.2 |  | PLATE 200 X 120 X 16 MM THK | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.2.3 |  | RIB 80 X 60 X 12 MM THK | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.2.4 |  | RIB 130 X 60 X 12 MM THK | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.2.5 |  | TABLE | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.2.6 |  | COLUMN | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.2.7 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 35 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.2.8 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.10.2.9 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.11 |  | PASSING TABLE ASSY#5 (BEFORE ENTRY FURNACE) | Subtask |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 29-May-26 01:25 PM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.12 |  | PASSING TABLE ASSY#6 (COOLING AFTER GALVANIZING) | Subtask |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 29-May-26 01:25 PM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.13 |  | PASSING TABLE ASSY#7 (STRIP HEATER ASSY.) | Subtask |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 29-May-26 01:25 PM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.14 |  | PASSING TABLE ASSY#7 (BEFORE ENTRY FURNACE) | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 120d | 120d | 141d17h |  |  | 22-Oct-25 03:00 AM | 02-Mar-26 04:00 PM |  | 03-Aug-26 03:25 PM | 26-Feb-26 04:00 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.14.1 |  | Release of PO | step |  |  |  |  | 18.14.2
18.14.1.1 |  | BAKELITE PLATE | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.1.2 |  | PLATE 250 X 180 X 30 MM THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.1.3 |  | TABLE-1 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.1.4 |  | COLUMN | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.1.5 |  | SUPPORT COLUMN | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.1.6 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 80 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.1.7 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.1.8 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 45 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.1.9 |  | Hexagon Nut Style 2 IS 1364- Part6 - M16-D-C | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.1.10 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.1.11 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.1.12 |  | Plain Washer (Type B) IS 2016 - 22 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.1.13 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.1.14 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.1.15 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.2 |  | Ready for Assy | step |  |  |  | 18.14.1
18.14.2.1 |  | BAKELITE PLATE | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.2.2 |  | PLATE 250 X 180 X 30 MM THK | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.2.3 |  | TABLE-1 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.2.4 |  | COLUMN | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.2.5 |  | SUPPORT COLUMN | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.2.6 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 80 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.2.7 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.2.8 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 45 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.2.9 |  | Hexagon Nut Style 2 IS 1364- Part6 - M16-D-C | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.2.10 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.2.11 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.2.12 |  | Plain Washer (Type B) IS 2016 - 22 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.2.13 |  | Spring Lock Washer IS 6735 - 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.2.14 |  | Spring Lock Washer IS 6735 - 20 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.14.2.15 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.15 |  | PASSING TABLE ASSY#10 (ON TURN UP ROLL) | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 120d | 120d | 141d17h |  |  | 22-Oct-25 03:00 AM | 02-Mar-26 04:00 PM |  | 03-Aug-26 03:25 PM | 26-Feb-26 04:00 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.15.1 |  | Release of PO | step |  |  |  |  | 18.15.2
18.15.1.1 |  | TABLE | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.15.1.2 |  | 115 X 150 X 20 MM THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.15.1.3 |  | NYLON PAD | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.15.1.4 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.15.1.5 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.15.1.6 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.15.1.7 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.15.2 |  | Ready for Assy | step |  |  |  | 18.15.1
18.15.2.1 |  | TABLE | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.15.2.2 |  | 115 X 150 X 20 MM THK | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.15.2.3 |  | NYLON PAD | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.15.2.4 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.15.2.5 |  | Spring Lock Washer IS 6735 - 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.15.2.6 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.15.2.7 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16 |  | PASSING TABLE ASSY#11 (COOLING AFTER GALVANIZING) | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 120d | 120d | 141d17h |  |  | 22-Oct-25 03:00 AM | 02-Mar-26 04:00 PM |  | 03-Aug-26 03:25 PM | 26-Feb-26 04:00 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.16.1 |  | Release of PO | step |  |  |  |  | 18.16.2
18.16.1.1 |  | TABLE FAB | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.1.2 |  | COLUMN FAB | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.1.3 |  | COLUMN FAB | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.1.4 |  | PLATE 250 X 180 X 30 MM THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.1.5 |  | NYLON PAD | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.1.6 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 45 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.1.7 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.1.8 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.1.9 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.1.10 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 80 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.1.11 |  | Hexagon Nut Style 2 IS 1364- Part6 - M16-D-C | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.1.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.1.13 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.16.1.14 |  | Plain Washer (Type B) IS 2016 - 22 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.16.1.15 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.16.2 |  | Ready for Assy | step |  |  |  | 18.16.1
18.16.2.1 |  | TABLE FAB | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.2.2 |  | COLUMN FAB | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.2.3 |  | COLUMN FAB | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.2.4 |  | PLATE 250 X 180 X 30 MM THK | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.2.5 |  | NYLON PAD | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.2.6 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 45 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.2.7 |  | Spring Lock Washer IS 6735 - 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.2.8 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.2.9 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.2.10 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 80 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.2.11 |  | Hexagon Nut Style 2 IS 1364- Part6 - M16-D-C | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.2.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.16.2.13 |  | Spring Lock Washer IS 6735 - 20 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.16.2.14 |  | Plain Washer (Type B) IS 2016 - 22 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.16.2.15 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.17 |  | PASSING TABLE ASSY#12 (ON TURN DOWN ROLL) | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 120d | 120d | 141d17h |  |  | 22-Oct-25 03:00 AM | 02-Mar-26 04:00 PM |  | 03-Aug-26 03:25 PM | 26-Feb-26 04:00 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.17.1 |  | Release of PO | step |  |  |  |  | 18.17.2
18.17.1.1 |  | TABLE | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.17.1.2 |  | 115 X 150 X 20 MM THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.17.1.3 |  | NYLON PAD | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.17.1.4 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.17.1.5 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.17.1.6 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.17.1.7 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.17.2 |  | Ready for Assy | step |  |  |  | 18.17.1
18.17.2.1 |  | TABLE | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.17.2.2 |  | 115 X 150 X 20 MM THK | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.17.2.3 |  | NYLON PAD | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.17.2.4 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.17.2.5 |  | Spring Lock Washer IS 6735 - 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.17.2.6 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.17.2.7 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18 |  | PASSING TABLE ASSY#13 (BETWEEN DEFLECTOR #9 & DEFLECTOR #10 | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 120d | 120d | 141d17h |  |  | 22-Oct-25 03:00 AM | 02-Mar-26 04:00 PM |  | 03-Aug-26 03:25 PM | 26-Feb-26 03:59 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.18.1 |  | Release of PO | step |  |  |  |  | 18.18.2
18.18.1.1 |  | TABLE FAB | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.1.2 |  | COLUMN FAB | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.1.3 |  | COLUMN FAB | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.1.4 |  | PLATE 250 X 180 X 30 MM THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.1.5 |  | NYLON PAD | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.1.6 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 45 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.1.7 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.1.8 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.1.9 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.1.10 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 80 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.1.11 |  | Hexagon Nut Style 2 IS 1364- Part6 - M16-D-C | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.1.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.1.13 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.1.14 |  | Plain Washer (Type B) IS 2016 - 22 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.1.15 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.2 |  | Ready for Assy | step |  |  |  | 18.18.1
18.18.2.1 |  | TABLE FAB | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.2.2 |  | COLUMN FAB | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.2.3 |  | COLUMN FAB | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.2.4 |  | PLATE 250 X 180 X 30 MM THK | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.2.5 |  | NYLON PAD | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.2.6 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 45 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.2.7 |  | Spring Lock Washer IS 6735 - 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.2.8 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.2.9 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.2.10 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 80 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.2.11 |  | Hexagon Nut Style 2 IS 1364- Part6 - M16-D-C | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.2.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.2.13 |  | Spring Lock Washer IS 6735 - 20 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.2.14 |  | Plain Washer (Type B) IS 2016 - 22 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.18.2.15 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19 |  | PASSING TABLE ASSY#14 (BETWEEN CHILL ROLL# 1 & 2) | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 120d | 120d | 141d17h |  |  | 22-Oct-25 03:00 AM | 02-Mar-26 04:00 PM |  | 03-Aug-26 03:25 PM | 26-Feb-26 03:59 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.19.1 |  | Release of PO | step |  |  |  |  | 18.19.2
18.19.1.1 |  | BAKELITE PLATE | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.1.2 |  | PLATE 250 X 180 X 30 MM THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.1.3 |  | TABLE-1 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.1.4 |  | COLUMN | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.1.5 |  | SUPPORT COLUMN | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.1.6 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 80 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.1.7 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.1.8 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 45 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.1.9 |  | Hexagon Nut Style 2 IS 1364- Part6 - M16-D-C | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.1.10 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.1.11 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.1.12 |  | Plain Washer (Type B) IS 2016 - 22 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.1.13 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.1.14 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.1.15 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.2 |  | Ready for Assy | step |  |  |  | 18.19.1
18.19.2.1 |  | BAKELITE PLATE | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.2.2 |  | PLATE 250 X 180 X 30 MM THK | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.2.3 |  | TABLE-1 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.2.4 |  | COLUMN | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.2.5 |  | SUPPORT COLUMN | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.2.6 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 80 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.2.7 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.2.8 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 45 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.2.9 |  | Hexagon Nut Style 2 IS 1364- Part6 - M16-D-C | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.2.10 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.2.11 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.2.12 |  | Plain Washer (Type B) IS 2016 - 22 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.2.13 |  | Spring Lock Washer IS 6735 - 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.2.14 |  | Spring Lock Washer IS 6735 - 20 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.19.2.15 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20 |  | PASSING TABLE ASSY#16 (AFTER BRIDLE ASSY.#10) | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 120d | 120d | 141d17h |  |  | 22-Oct-25 03:00 AM | 02-Mar-26 04:00 PM |  | 03-Aug-26 03:25 PM | 26-Feb-26 03:59 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.20.1 |  | Release of PO | step |  |  |  |  | 18.20.2
18.20.1.1 |  | TABLE | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.1.2 |  | COLUMN FRAME #1 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.1.3 |  | COLUMN FRAME #2 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.1.4 |  | PLATE - 250X150X25 THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.1.5 |  | BAKELITE | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.1.6 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 80 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.1.7 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.1.8 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.1.9 |  | Hexagon Nut Style 2 IS 1364-Part6 - M16-D-C | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.1.10 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.1.11 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.1.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.2 |  | Ready for Assy | step |  |  |  | 18.20.1
18.20.2.1 |  | TABLE | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.2.2 |  | COLUMN FRAME #1 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.2.3 |  | COLUMN FRAME #2 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.2.4 |  | PLATE - 250X150X25 THK | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.2.5 |  | BAKELITE | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.2.6 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 80 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.2.7 |  | Spring Lock Washer IS 6735 - 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.2.8 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.2.9 |  | Hexagon Nut Style 2 IS 1364-Part6 - M16-D-C | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.2.10 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.2.11 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.20.2.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.21 |  | PASSING TABLE ASSY#18 (AFTER EXIT SHEAR) | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 120d | 120d | 141d17h |  |  | 22-Oct-25 03:00 AM | 02-Mar-26 04:00 PM |  | 03-Aug-26 03:25 PM | 26-Feb-26 03:59 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.21.1 |  | Release of PO | step |  |  |  |  | 18.21.2
18.21.1.1 |  | TABLE | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.21.1.2 |  | BAKELITE PLATE 430.0X250.0X10.0 MM THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.21.1.3 |  | PLATE 100X120X20.0 THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.21.1.4 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.21.1.5 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.21.1.6 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.21.1.7 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.21.2 |  | Ready for Assy | step |  |  |  | 18.21.1
18.21.2.1 |  | TABLE | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.21.2.2 |  | BAKELITE PLATE 430.0X250.0X10.0 MM THK | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.21.2.3 |  | PLATE 100X120X20.0 THK | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.21.2.4 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.21.2.5 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.21.2.6 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.21.2.7 |  | Spring Lock Washer IS 6735 - 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.22 |  | ENTRY SCRAP TRAY ASSY | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 120d | 120d | 141d17h |  |  | 22-Oct-25 03:00 AM | 02-Mar-26 04:00 PM |  | 03-Aug-26 03:25 PM | 26-Feb-26 03:59 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.22.1 |  | Release of PO | step |  |  |  |  | 18.22.2
18.22.1.1 |  | TRAY | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 14-Mar-26 04:51 PM | 14-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.22.1.2 |  | ISA 75.0 X 75.0 X 10.0MM THK ( 1820.0MM LONG ) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 14-Mar-26 04:51 PM | 14-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.22.1.3 |  | ISA 50 X 50 X 6MM THK (150MM LONG) | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.22.1.4 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 35 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.22.1.5 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.22.1.6 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.22.1.7 |  | Hexagon nut IS 1363-Part2 - M10-C | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.22.2 |  | Ready for Assy | step |  |  |  | 18.22.1
18.22.2.1 |  | TRAY | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.22.2.2 |  | ISA 75.0 X 75.0 X 10.0MM THK ( 1820.0MM LONG ) | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.22.2.3 |  | ISA 50 X 50 X 6MM THK (150MM LONG) | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.22.2.4 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 35 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.22.2.5 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.22.2.6 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.22.2.7 |  | Hexagon nut IS 1363-Part2 - M10-C | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23 |  | EXIT THREADING TABLE | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 120d | 120d | 141d17h |  |  | 22-Oct-25 03:00 AM | 02-Mar-26 04:00 PM |  | 03-Aug-26 03:25 PM | 26-Feb-26 03:59 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.23.1 |  | Release of PO | step |  |  |  |  | 18.23.2
18.23.1.1 |  | PAD | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.2 |  | PLATE 165x185x20 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.3 |  | END PLATE | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.4 |  | PIN | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.5 |  | PAD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.6 |  | CYL.PIN | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.7 |  | CLAMP | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.8 |  | BUSH BLOCK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.9 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.10 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.11 |  | CYL CLEVIS | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.12 |  | CYL. CLEVIS | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.13 |  | L-PLATE | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.14 |  | HORIZONTAL LINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.15 |  | VERTICAL LINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.16 |  | CLAMP PLATE | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.17 |  | WELDED PLATE | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.18 |  | HYD. CYL. BORE DIA-80, ROD DIA-45, STK-500MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.19 |  | HYD CYL. BORE-63, ROD-45, STK-550, | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.20 |  | TABLE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.1.21 |  | SLIDING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.22 |  | GUARD PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.23 |  | CYL. BRACKET | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.24 |  | BUSH HOUSING | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.25 |  | CLEVIS | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.26 |  | BRACKET | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.27 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.28 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.29 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.30 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.31 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.32 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.34 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.35 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.36 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.37 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.38 |  | Plain Washer (Type B) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.39 |  | Socket Head Cap Screw IS 2269 - M10 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.40 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.41 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.42 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.43 |  | Spring Lock Washer IS 6735 - 10 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.44 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.45 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.46 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.1.47 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:23 PM | 02-Mar-26 05:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2 |  | Ready for Assy | step |  |  |  | 18.23.1
18.23.2.1 |  | PAD | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.2 |  | PLATE 165x185x20 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.3 |  | END PLATE | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.4 |  | PIN | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.5 |  | PAD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 05-Mar-26 01:08 PM | 05-Mar-26 02:08 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.6 |  | CYL.PIN | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.7 |  | CLAMP | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.8 |  | BUSH BLOCK | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.9 |  | BUSH | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.10 |  | BUSH | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.11 |  | CYL CLEVIS | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.12 |  | CYL. CLEVIS | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.13 |  | L-PLATE | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.14 |  | HORIZONTAL LINER | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.15 |  | VERTICAL LINER | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.16 |  | CLAMP PLATE | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.17 |  | WELDED PLATE | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.18 |  | HYD. CYL. BORE DIA-80, ROD DIA-45, STK-500MM | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.19 |  | HYD CYL. BORE-63, ROD-45, STK-550, | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.20 |  | TABLE | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.23.2.21 |  | SLIDING PLATE | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.22 |  | GUARD PLATE | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.23 |  | CYL. BRACKET | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.24 |  | BUSH HOUSING | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.25 |  | CLEVIS | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.26 |  | BRACKET | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 04-Apr-26 03:25 PM | 03-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.27 |  | GREASE NIPPLE 1/8" BSP | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.28 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.29 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 35 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.30 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.31 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 25 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.32 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 60 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.34 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.35 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.36 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.37 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.38 |  | Plain Washer (Type B) IS 2016 - 11 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.39 |  | Socket Head Cap Screw IS 2269 - M10 x 25 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.40 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.41 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.42 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.43 |  | Spring Lock Washer IS 6735 - 10 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.44 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.45 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 20 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.46 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 25 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.23.2.47 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 30 | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24 |  | ENTRY SCRAP TROLLY ASSY. | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 110d | 110d | 131d17h |  |  | 22-Oct-25 03:00 AM | 02-Mar-26 04:00 PM |  | 23-Jul-26 09:25 AM | 26-Feb-26 03:59 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
18.24.1 |  | Release of PO | step |  |  |  |  | 18.24.2
18.24.1.1 |  | TROLLEY | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.24.1.2 |  | BOTTOM FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.24.1.3 |  | BRACKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.24.1.4 |  | BRG.BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.24.1.5 |  | CHAIN COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.24.1.6 |  | BRG.BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.24.1.7 |  | CABLE REEL DRUM FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.24.1.8 |  | SIMPLEX CHAIN PITCH 1'' 1500MM LONG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.9 |  | PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.10 |  | WHEEL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.11 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.12 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.13 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.14 |  | SQUARE BAR 40 X 40 X 8500MM LONG | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.15 |  | SHAFT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.16 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.17 |  | WHEEL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.18 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.19 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.20 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.21 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.22 |  | SPROCKETS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.23 |  | SPROCKETS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.24 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.25 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.26 |  | PLATE 150 X 150 X 16MM THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.27 |  | KEY-45X18X11MM THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.28 |  | 1.5 KW GEARED MOTOR, GEAR RATIO-100, 4 POLE ,MAKE BY-NORD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.29 |  | 6208_2Z-DEEP GROOVE BALL BEARING-ID40XOD80X18 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.30 |  | SPH. ROLLER BEARING ID -55, OD-120, THK. -29 MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.31 |  | 105x70x10THK OIL SEAL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.32 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.33 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.34 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.35 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.36 |  | Spring Lock Washer IS 6735 - 10 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.37 |  | Spring Lock Washer IS 3063 - 12- B | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.39 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.40 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.42 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.43 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.45 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.46 |  | Spring Lock Washer IS 6735 - 8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.47 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.50 |  | Hexagon Nut Style 1 IS 1364-Part3 - M8-D-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.52 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.1.53 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 02-Mar-26 04:14 PM | 02-Mar-26 05:14 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2 |  | Ready for Assy | step |  |  |  | 18.24.1
18.24.2.1 |  | TROLLEY | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.24.2.2 |  | BOTTOM FRAME | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 7d12h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:43 PM | 17-Mar-26 05:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.24.2.3 |  | BRACKET | date |  | 110d |  |  |  | IP | YES | [5 empty] | 110d |  | 122d6h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  | 23-Jul-26 09:25 AM | 09-Mar-26 12:43 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.24.2.4 |  | BRG.BLOCK | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.24.2.5 |  | CHAIN COVER | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.24.2.6 |  | BRG.BLOCK | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.24.2.7 |  | CABLE REEL DRUM FRAME | date |  | 110d |  |  |  | IP | YES | [5 empty] | 110d |  | 122d6h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  | 23-Jul-26 09:25 AM | 09-Mar-26 12:44 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
18.24.2.8 |  | SIMPLEX CHAIN PITCH 1'' 1500MM LONG | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:50 PM | 09-Mar-26 01:50 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.9 |  | PIN | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.10 |  | WHEEL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.11 |  | KEEPER PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.12 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.13 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.14 |  | SQUARE BAR 40 X 40 X 8500MM LONG | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.15 |  | SHAFT | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.16 |  | RETAINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.17 |  | WHEEL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.18 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.19 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.20 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.21 |  | RETAINER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.22 |  | SPROCKETS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.23 |  | SPROCKETS | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.24 |  | END PLATE | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.25 |  | SPACER | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:45 PM | 09-Mar-26 01:45 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.26 |  | PLATE 150 X 150 X 16MM THK | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.27 |  | KEY-45X18X11MM THK | date |  | 110d |  |  |  | NS | YES | [5 empty] | 110d |  |  |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM | 25-Mar-26 02:25 AM | 23-Jul-26 09:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.28 |  | 1.5 KW GEARED MOTOR, GEAR RATIO-100, 4 POLE ,MAKE BY-NORD | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 17-Mar-26 05:09 PM | 17-Mar-26 06:09 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.29 |  | 6208_2Z-DEEP GROOVE BALL BEARING-ID40XOD80X18 THK. | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:47 PM | 09-Mar-26 01:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.30 |  | SPH. ROLLER BEARING ID -55, OD-120, THK. -29 MM | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:47 PM | 09-Mar-26 01:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.31 |  | 105x70x10THK OIL SEAL | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.32 |  | GREASE NIPPLE 1/8" BSP | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.33 |  | SHEAR BIOCK- 10x10x50mm | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.34 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 20 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.35 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 25 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.36 |  | Spring Lock Washer IS 6735 - 10 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.37 |  | Spring Lock Washer IS 3063 - 12- B | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.39 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.40 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 40 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 40 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.42 |  | Spring Lock Washer IS 6735 - 16 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.43 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.45 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 16 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.46 |  | Spring Lock Washer IS 6735 - 8 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.47 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.50 |  | Hexagon Nut Style 1 IS 1364-Part3 - M8-D-N | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 60 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.52 |  | Spring Lock Washer IS 6735 - 20 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
18.24.2.53 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 110d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 02-Mar-26 04:00 PM |  |  | 09-Mar-26 12:49 PM | 09-Mar-26 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19 | 51 | Category 2 - BRUSHING ROLL ASSY - Ordering & Manufacturing | TASK |  | 90d | 90d | 25 | 80 | IP | YES | 012-015 |  |  |  |  | 63d8h | 63d8h | 188d17h |  |  | 16-Aug-25 01:00 AM | 22-Nov-25 01:00 PM |  | 31-May-26 02:56 PM | 05-Nov-25 04:23 PM |  |  |  | FAST |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
19.1 |  | BRUSHING ROLL ASSY.#01 (4 ASSY QTY) | Subtask |  | 90d | 90d |  |  | IP | YES | [5 empty] | 61d7h | 61d7h | 186d16h |  |  | 16-Aug-25 01:00 AM | 22-Nov-25 01:00 PM |  | 29-May-26 07:16 AM | 05-Nov-25 04:23 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
19.1.1 |  | Release of PO | step |  |  |  |  | 19.1.2
19.1.1.1 |  | Chock | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.2 |  | Bearing Cover 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.3 |  | Bearing cover 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.4 |  | Clamp | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.5 |  | Spacer | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.6 |  | Splash Ring | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.7 |  | Connecting Rod | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.8 |  | Lock Nut | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.9 |  | Lead Screw | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.10 |  | Hand Wheel | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.11 |  | Screw Adaptor 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.12 |  | Guide Plate 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.13 |  | Guide Plate 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.14 |  | Spacer | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.15 |  | Spacer | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.16 |  | Adaptor Motor Side | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.17 |  | Adaptor Roll Side | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.18 |  | Adaptor GM Side | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.19 |  | MOTOR 11 KW X 8 POLE X 750 RPM X FOOT MOUNTED | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 74d10h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:31 PM | 02-Feb-26 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.20 |  | 2.2 KW Gear Ratio 5.65 X 1500 RPM X Motor Size 100 L | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 74d10h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:31 PM | 02-Feb-26 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.21 |  | MOTOR 2.2 KW X 4 POLE X 1500 RPM X FRAME SIZE 100L | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 74d10h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:31 PM | 02-Feb-26 10:58 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.22 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.23 |  | ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.24 |  | BACKUP ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 12:05 PM | 11-Nov-25 01:05 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.25 |  | BASE FRAME 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:31 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.26 |  | SIDE FRAME 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:31 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.27 |  | TOP FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.28 |  | Coupling | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:31 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.29 |  | Screw Jack | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 62d15h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:31 PM | 20-Jan-26 12:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.30 |  | ROLL SEGMENT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:24 PM | 05-Nov-25 05:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.31 |  | STAND | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.32 |  | Propeller Shaft | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.33 |  | Propeller Shaft | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.34 |  | 22215_E-SPHERICAL ROLLER BEARING- ID75XOD130X31 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.35 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.36 |  | Lock Nut,Thread Size- M100x2,Make- SKF/EQ,Model No-KM20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.37 |  | Parallel Key, Type- A,IS:2048,Size:W5 x H5 x L30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.38 |  | Lock Nut,Thread Size- M75x2,Make- SKF/EQ,Model No-KM15 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.39 |  | Lock Washer, Make- SKF/EQ., Model No.MB15 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.40 |  | Lock Washer, Make- SKF/EQ., Model No.MB20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.41 |  | Rotary Radial Oil Seal-110 X 85 X 12 mm, Type-B, IS:5129 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 12-Nov-25 03:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 12-Nov-25 03:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.43 |  | Grease Nipple,Size-1/8" BSP(M) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 12-Nov-25 03:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 12-Nov-25 03:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.45 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 12-Nov-25 03:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 12-Nov-25 03:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 12-Nov-25 03:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 12-Nov-25 03:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 12-Nov-25 03:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 12-Nov-25 03:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.51 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 12-Nov-25 03:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.52 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 12-Nov-25 03:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.53 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 12-Nov-25 03:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.54 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 12-Nov-25 03:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.1.55 |  | Spring Lock Washer IS 6735 - 8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:32 PM | 12-Nov-25 03:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2 |  | Ready for Assy | step |  |  |  | 19.1.1
19.1.2.1 |  | Chock | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 70d2h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 21-Jan-26 01:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.2 |  | Bearing Cover 1 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 70d2h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 21-Jan-26 01:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.3 |  | Bearing cover 2 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 70d2h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 21-Jan-26 01:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.4 |  | Clamp | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 70d2h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 21-Jan-26 01:16 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.5 |  | Spacer | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.6 |  | Splash Ring | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.7 |  | Connecting Rod | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.8 |  | Lock Nut | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.9 |  | Lead Screw | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.10 |  | Hand Wheel | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.11 |  | Screw Adaptor 1 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.12 |  | Guide Plate 1 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.13 |  | Guide Plate 2 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.14 |  | Spacer | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.15 |  | Spacer | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.16 |  | Adaptor Motor Side | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.17 |  | Adaptor Roll Side | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.18 |  | Adaptor GM Side | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.19 |  | MOTOR 11 KW X 8 POLE X 750 RPM X FOOT MOUNTED | date |  | 80d |  |  |  | IP | YES | [5 empty] | 35d17h |  | 155d4h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  | 01-May-26 09:42 AM | 12-Nov-25 02:32 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.20 |  | 2.2 KW Gear Ratio 5.65 X 1500 RPM X Motor Size 100 L | date |  | 80d |  |  |  | IP | YES | [5 empty] | 35d17h |  | 155d4h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  | 01-May-26 09:42 AM | 12-Nov-25 02:32 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.21 |  | MOTOR 2.2 KW X 4 POLE X 1500 RPM X FRAME SIZE 100L | date |  | 80d |  |  |  | IP | YES | [5 empty] | 35d17h |  | 155d4h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  | 01-May-26 09:42 AM | 12-Nov-25 02:32 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.22 |  | SPACER | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.23 |  | ROLL | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.24 |  | BACKUP ROLL | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 104d6h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 11-Nov-25 12:05 PM | 05-Mar-26 02:04 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.25 |  | BASE FRAME 1 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.26 |  | SIDE FRAME 1 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.27 |  | TOP FRAME | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.28 |  | Coupling | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 103d4h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 05-Mar-26 02:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.29 |  | Screw Jack | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.30 |  | ROLL SEGMENT | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 125d10h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:24 PM | 23-Mar-26 09:51 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.31 |  | STAND | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 113d16h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 17-Mar-26 11:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.32 |  | Propeller Shaft | date |  | 80d |  |  |  | IP | YES | [5 empty] | 61d7h |  | 180d11h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  | 29-May-26 07:16 AM | 12-Nov-25 02:32 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.33 |  | Propeller Shaft | date |  | 80d |  |  |  | IP | YES | [5 empty] | 61d7h |  | 180d11h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  | 29-May-26 07:16 AM | 12-Nov-25 02:32 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.34 |  | 22215_E-SPHERICAL ROLLER BEARING- ID75XOD130X31 THK. | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d9h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 09-Mar-26 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.35 |  | SHEAR BIOCK- 10x10x50mm | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.36 |  | Lock Nut,Thread Size- M100x2,Make- SKF/EQ,Model No-KM20 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 104d2h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 06-Mar-26 12:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.37 |  | Parallel Key, Type- A,IS:2048,Size:W5 x H5 x L30 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 61d7h |  | 180d11h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  | 29-May-26 07:16 AM | 12-Nov-25 02:32 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.38 |  | Lock Nut,Thread Size- M75x2,Make- SKF/EQ,Model No-KM15 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 104d2h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 06-Mar-26 12:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.39 |  | Lock Washer, Make- SKF/EQ., Model No.MB15 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 104d2h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 06-Mar-26 12:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.40 |  | Lock Washer, Make- SKF/EQ., Model No.MB20 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 104d2h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 06-Mar-26 12:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.41 |  | Rotary Radial Oil Seal-110 X 85 X 12 mm, Type-B, IS:5129 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 113d16h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 17-Mar-26 12:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.43 |  | Grease Nipple,Size-1/8" BSP(M) | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.45 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 60 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 25 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.51 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.52 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.53 |  | Spring Lock Washer IS 6735 - 12 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.54 |  | Spring Lock Washer IS 6735 - 16 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.1.2.55 |  | Spring Lock Washer IS 6735 - 8 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:32 PM | 02-Mar-26 05:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2 |  | BRUSHING ROLL ASSY.#02 (4 ASSY QTY) | Subtask |  | 90d | 90d |  |  | IP | YES | [5 empty] | 63d8h | 63d8h | 188d17h |  |  | 16-Aug-25 01:00 AM | 22-Nov-25 01:00 PM |  | 31-May-26 02:56 PM | 05-Nov-25 04:24 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
19.2.1 |  | Release of PO | step |  |  |  |  | 19.2.2
19.2.1.1 |  | Chock | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.2 |  | Bearing Cover 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.3 |  | Bearing cover 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.4 |  | Clamp | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.5 |  | Spacer | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.6 |  | Splash Ring | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.7 |  | Connecting Rod | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.8 |  | Lock Nut | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.9 |  | Lead Screw | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.10 |  | Hand Wheel | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.11 |  | Screw Adaptor 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.12 |  | Guide Plate 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.13 |  | Guide Plate 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.14 |  | Spacer | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.15 |  | Spacer | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.16 |  | Adaptor Motor Side | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.17 |  | Adaptor Roll Side | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.18 |  | Adaptor GM Side | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.19 |  | MOTOR 11 KW X 8 POLE X 750 RPM X FOOT MOUNTED | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d13h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 28-Feb-26 10:11 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.20 |  | 2.2 KW Gear Ratio 5.65 X 1500 RPM X Motor Size 100 L | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d13h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 28-Feb-26 10:11 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.21 |  | MOTOR 2.2 KW X 4 POLE X 1500 RPM X FRAME SIZE 100L | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d13h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 28-Feb-26 10:11 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.22 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.23 |  | ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.24 |  | BACKUP ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 11-Nov-25 12:06 PM | 11-Nov-25 01:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.25 |  | BASE FRAME 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d13h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 28-Feb-26 10:11 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.26 |  | SIDE FRAME 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d13h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 28-Feb-26 10:11 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.27 |  | TOP FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.28 |  | Coupling | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d13h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 28-Feb-26 10:11 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.29 |  | Screw Jack | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 62d15h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 20-Jan-26 12:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.30 |  | ROLL SEGMNET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 05-Nov-25 04:26 PM | 05-Nov-25 05:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.31 |  | STAND | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 62d15h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 20-Jan-26 01:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.32 |  | Propeller Shaft | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.33 |  | Propeller Shaft | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.34 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.35 |  | STOPPER 15.0x15.0x60.0 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.36 |  | 22215_E-SPHERICAL ROLLER BEARING-ID75XOD130X31 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.37 |  | Parallel Key, Type- A,IS:2048,Size:W5 x H5 x L30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.38 |  | Lock Nut,Thread Size- M100x2,Make-SKF/EQ,Model No- KM20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.39 |  | Lock Nut,Thread Size-M75x2,Make- SKF/EQ,Model No-KM15 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.40 |  | Lock Washer, Make-SKF/EQ., Model No.MB15 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.41 |  | Lock Washer, Make-SKF/EQ., Model No.MB20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.42 |  | Rotary Radial Oil Seal-110 X 85 X 12 mm, Type-B, IS:5129 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.43 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.44 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.45 |  | Spring Lock Washer IS 6735 - 8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.46 |  | Grease Nipple,Size-1/8" BSP(M) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.54 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.57 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.1.58 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 16-Aug-25 01:00 AM | 27-Aug-25 05:00 AM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2 |  | Ready for Assy | step |  |  |  | 19.2.1
19.2.2.1 |  | Chock | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.2 |  | Bearing Cover 1 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.3 |  | Bearing cover 2 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.4 |  | Clamp | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.5 |  | Spacer | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.6 |  | Splash Ring | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.7 |  | Connecting Rod | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.8 |  | Lock Nut | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.9 |  | Lead Screw | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.10 |  | Hand Wheel | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.11 |  | Screw Adaptor 1 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.12 |  | Guide Plate 1 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.13 |  | Guide Plate 2 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.14 |  | Spacer | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.15 |  | Spacer | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.16 |  | Adaptor Motor Side | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.17 |  | Adaptor Roll Side | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.18 |  | Adaptor GM Side | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.19 |  | MOTOR 11 KW X 8 POLE X 750 RPM X FOOT MOUNTED | date |  | 80d |  |  |  | IP | YES | [5 empty] | 62d8h |  | 181d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  | 30-May-26 08:24 AM | 12-Nov-25 02:34 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.20 |  | 2.2 KW Gear Ratio 5.65 X 1500 RPM X Motor Size 100 L | date |  | 80d |  |  |  | IP | YES | [5 empty] | 62d8h |  | 181d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  | 30-May-26 08:24 AM | 12-Nov-25 02:34 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.21 |  | MOTOR 2.2 KW X 4 POLE X 1500 RPM X FRAME SIZE 100L | date |  | 80d |  |  |  | IP | YES | [5 empty] | 62d8h |  | 181d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  | 30-May-26 08:24 AM | 12-Nov-25 02:34 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.22 |  | SPACER | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.23 |  | ROLL | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.24 |  | BACKUP ROLL | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 105d5h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 11-Nov-25 12:06 PM | 06-Mar-26 01:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.25 |  | BASE FRAME 1 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 62d8h |  | 181d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  | 30-May-26 08:24 AM | 12-Nov-25 02:34 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.26 |  | SIDE FRAME 1 | date |  | 80d |  |  |  | IP | YES | [5 empty] | 62d8h |  | 181d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  | 30-May-26 08:24 AM | 12-Nov-25 02:34 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.27 |  | TOP FRAME | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.28 |  | Coupling | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 113d17h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 17-Mar-26 12:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.29 |  | Screw Jack | date |  | 80d |  |  |  | IP | YES | [5 empty] | 27d9h |  | 146d13h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  | 22-Apr-26 08:12 AM | 12-Nov-25 02:34 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.30 |  | ROLL SEGMNET | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 125d10h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 05-Nov-25 04:26 PM | 23-Mar-26 09:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.31 |  | STAND | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 113d17h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 17-Mar-26 12:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.32 |  | Propeller Shaft | date |  | 80d |  |  |  | IP | YES | [5 empty] | 63d8h |  | 182d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  | 31-May-26 02:56 PM | 12-Nov-25 02:34 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.33 |  | Propeller Shaft | date |  | 80d |  |  |  | IP | YES | [5 empty] | 63d8h |  | 182d12h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  | 31-May-26 02:56 PM | 12-Nov-25 02:34 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.34 |  | SHEAR BIOCK- 10x10x50mm | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.35 |  | STOPPER 15.0x15.0x60.0 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.36 |  | 22215_E-SPHERICAL ROLLER BEARING-ID75XOD130X31 THK. | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 106d9h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 09-Mar-26 11:56 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.37 |  | Parallel Key, Type- A,IS:2048,Size:W5 x H5 x L30 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 104d6h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 06-Mar-26 04:07 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.38 |  | Lock Nut,Thread Size- M100x2,Make-SKF/EQ,Model No- KM20 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 104d6h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 06-Mar-26 04:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.39 |  | Lock Nut,Thread Size-M75x2,Make- SKF/EQ,Model No-KM15 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 104d6h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 06-Mar-26 04:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.40 |  | Lock Washer, Make-SKF/EQ., Model No.MB15 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 104d6h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 06-Mar-26 04:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.41 |  | Lock Washer, Make-SKF/EQ., Model No.MB20 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 104d6h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 06-Mar-26 04:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.42 |  | Rotary Radial Oil Seal-110 X 85 X 12 mm, Type-B, IS:5129 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 104d6h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 06-Mar-26 04:06 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.43 |  | Spring Lock Washer IS 6735 - 12 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.44 |  | Spring Lock Washer IS 6735 - 16 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.45 |  | Spring Lock Washer IS 6735 - 8 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.46 |  | Grease Nipple,Size-1/8" BSP(M) | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 40 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 70 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.54 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 20 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 25 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.57 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
19.2.2.58 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 80d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d7h |  |  | 27-Aug-25 05:00 AM | 22-Nov-25 01:00 PM |  |  | 12-Nov-25 02:34 PM | 02-Mar-26 05:15 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
20 | 71 | Category 2 - BRIDLE ROLL ASSY - Engg | TASK |  | 4d | 4d |  | 11 | CO | YES | [7 empty] | 28d |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 07-Nov-25 09:36 AM | 08-Dec-25 11:49 AM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
20.1 |  | BRIDLE ROLL ASSY. | Subtask |  | 4d | 4d |  |  | CO | YES | [7 empty] | 28d |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 07-Nov-25 09:36 AM | 08-Dec-25 11:49 AM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
20.1.1 |  | Completion | step
20.1.1.1 |  | BRIDLE ROLL ASSY.#1 | date |  | 4d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 08-Dec-25 10:49 AM | 08-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
20.1.1.2 |  | BRIDLE ROLL ASSY.#2 | date |  | 4d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 07-Nov-25 09:36 AM | 07-Nov-25 10:36 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
20.1.1.3 |  | BRIDLE ROLL ASSY.#3 | date |  | 4d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 07-Nov-25 09:36 AM | 07-Nov-25 10:36 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
20.1.1.4 |  | BRIDLE ROLL ASSY.#4 | date |  | 4d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 11-Nov-25 04:27 PM | 11-Nov-25 05:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
20.1.1.5 |  | BRIDLE ROLL ASSY.#5 | date |  | 4d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 15-Nov-25 09:36 AM | 15-Nov-25 10:36 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
20.1.1.6 |  | BRIDLE ROLL ASSY.#6 (FUTURE PROVISION) | date |  | 4d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 15-Nov-25 09:47 AM | 15-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
20.1.1.7 |  | BRIDLE ROLL ASSY.#7&8 | date |  | 4d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 08-Dec-25 10:49 AM | 08-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
20.1.1.8 |  | BRIDLE ROLL ASSY.#9 | date |  | 4d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 11-Nov-25 04:27 PM | 11-Nov-25 05:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
20.1.1.9 |  | BRIDLE ROLL ASSY.#10 | date |  | 4d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 08-Dec-25 10:49 AM | 08-Dec-25 11:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
21 | 59 | Category 2 - UNCOILER ASSY #1 - Engg | TASK |  | 6d | 6d |  | 12 | IP | YES | 001-023 |  |  |  |  | 17h | 17h | 124d6h |  |  | 12-Aug-25 01:00 AM | 18-Aug-25 02:00 PM |  | 23-Mar-26 09:00 PM | 07-Nov-25 09:40 AM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
21.1 |  | UNCOILER ASSY#1 | Subtask |  | 6d | 6d |  |  | IP | YES | [5 empty] | 17h | 17h | 124d6h |  |  | 12-Aug-25 01:00 AM | 18-Aug-25 02:00 PM |  | 23-Mar-26 09:00 PM | 07-Nov-25 09:40 AM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
21.1.1 |  | Completion | step
21.1.1.1 |  | UNCOILER MANDREL ASSY. | date |  | 5d |  |  |  | IP | YES | [5 empty] | 17h |  | 124d |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM |  | 23-Mar-26 09:00 PM | 07-Nov-25 05:34 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
21.1.1.2 |  | UNCOILER GEAR BOX ASSY. | date |  | 6d |  |  |  | CO | YES | [5 empty] | 0d |  | 7d2h |  |  | 12-Aug-25 01:00 AM | 18-Aug-25 02:00 PM |  |  | 07-Nov-25 05:34 PM | 15-Nov-25 09:49 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
21.1.1.3 |  | UNCOILER SNUBBER ROLL ASSY.#1 | date |  | 5d |  |  |  | IP | YES | [5 empty] | 17h |  | 124d |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM |  | 23-Mar-26 09:00 PM | 07-Nov-25 05:34 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
21.1.1.4 |  | UNCOILER OBBS ASSY. | date |  | 3d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 14-Aug-25 09:00 PM |  |  | 07-Nov-25 09:41 AM | 07-Nov-25 10:41 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
22 | 62 | Category 2 - RECOILER ASSY - Engg | TASK |  | 6d | 6d |  | 13 | IP | YES | 002-004 |  |  |  |  | 1d |  | 124d7h |  |  | 12-Aug-25 01:00 AM | 18-Aug-25 02:00 PM |  | 24-Mar-26 02:25 AM | 07-Nov-25 09:41 AM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
22.1 |  | RECOILER ASSY | Subtask |  | 6d | 6d |  |  | CO | YES | [7 empty] | 101d9h |  |  | 12-Aug-25 01:00 AM | 18-Aug-25 02:00 PM |  |  | 07-Nov-25 09:41 AM | 26-Feb-26 03:54 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
22.1.1 |  | Completion | step
22.1.1.1 |  | RECOILER MANDREL ASSY. | date |  | 5d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d3h |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM |  |  | 07-Nov-25 05:33 PM | 26-Feb-26 03:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
22.1.1.2 |  | RECOILER GEAR BOX ASSY. | date |  | 6d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d3h |  |  | 12-Aug-25 01:00 AM | 18-Aug-25 02:00 PM |  |  | 07-Nov-25 05:33 PM | 26-Feb-26 03:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
22.1.1.3 |  | RECOILER PUSHER PLATE ASSY. | date |  | 5d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d3h |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM |  |  | 07-Nov-25 05:33 PM | 26-Feb-26 03:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
22.1.1.4 |  | RECOILER EXIT OBBS ASSY. | date |  | 3d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 14-Aug-25 09:00 PM |  |  | 07-Nov-25 09:41 AM | 07-Nov-25 10:41 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
22.1.1.5 |  | RECOILER BELT WRAPPPER ASSY. | date |  | 3d |  |  |  | CO | YES | [5 empty] | 0d |  | 101d3h |  |  | 12-Aug-25 01:00 AM | 14-Aug-25 09:00 PM |  |  | 07-Nov-25 05:33 PM | 26-Feb-26 03:54 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
23 | 26 | Category 2 - ENTRY ACCUMULATOR ASSY - Engg | TASK |  | 4d | 4d |  | 6 | CO | YES | [7 empty] | 1h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 07-Nov-25 09:44 AM | 07-Nov-25 10:44 AM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
23.1 |  | ENTRY ACCUMULATOR ASSY. | Subtask |  | 4d | 4d |  |  | CO | YES | [7 empty] | 1h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 07-Nov-25 09:44 AM | 07-Nov-25 10:44 AM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
23.1.1 |  | Completion | step
23.1.1.1 |  | ENTRY ACCUMULATOR ASSY. | date |  | 4d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 07-Nov-25 09:44 AM | 07-Nov-25 10:44 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
24 | 29 | Category 2 - EXIT ACCUMULATOR ASSY. - Engg | TASK |  | 4d | 4d |  | 10 | CO | YES | [7 empty] | 4h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 07-Nov-25 09:45 AM | 07-Nov-25 02:51 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
24.1 |  | EXIT ACCUMULATOR ASSY. | Subtask |  | 4d | 4d |  |  | CO | YES | [7 empty] | 4h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 07-Nov-25 09:45 AM | 07-Nov-25 02:51 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
24.1.1 |  | Completion | step
24.1.1.1 |  | EXIT ACCUMULATOR ASSY. | date |  | 4d |  |  |  | CO | YES | [5 empty] | 0d |  | 4h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 07-Nov-25 09:45 AM | 07-Nov-25 02:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
25 | 50 | Category 2 - BRUSHING ROLL ASSY - Engg | TASK |  | 4d | 4d |  | 19 | CO | YES | [7 empty] | 1h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 07-Nov-25 09:46 AM | 07-Nov-25 10:46 AM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
25.1 |  | BRUSHING ROLL ASSY. | Subtask |  | 4d | 4d |  |  | CO | NO | [7 empty] | 1h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 07-Nov-25 09:46 AM | 07-Nov-25 10:46 AM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
25.1.1 |  | Completion | step
25.1.1.1 |  | BRUSHING ROLL ASSY.#01 | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 07-Nov-25 09:46 AM | 07-Nov-25 10:46 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
25.1.1.2 |  | BRUSHING ROLL ASSY.#02 | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM |  |  | 07-Nov-25 09:46 AM | 07-Nov-25 10:46 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
26 | 38 | Category 1 - DEFLECTOR ROLL ASSY - Engg | TASK |  | 4d | 4d |  | 8 | CO | YES | [7 empty] | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
26.1 |  | DEFLECTOR ROLL ASSY | Subtask |  | 4d | 4d |  |  | CO | NO | [7 empty] | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
26.1.1 |  | Completion | step
26.1.1.1 |  | DEFLECTOR ROLL ASSY. | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
26.1.1.2 |  | DEFLECTOR ROLL FRAME ASSY.#1 (AFTER D.D SHEAR) | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
26.1.1.3 |  | DEFLECTOR ROLL FRAME ASSY.#2 (BEFORE BRIDLE ROLL ASSY.#1) | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
26.1.1.4 |  | DEFLECTOR ROLL FRAME ASSY.#3 (AFTER HOT AIR DRYER) | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
26.1.1.5 |  | DEFLECTOR ROLL FRAME ASSY.#4&5 (AFTER HOT AIR DRYER) | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
26.1.1.6 |  | DEFLECTOR ROLL FRAME ASSY.#6 (BEFORE BRIDLE ROLL ASSY.#2) | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
26.1.1.7 |  | DEFLECTOR ROLL FRAME ASSY.#7 (AFTER ENTRY ACC ASSY.) | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
26.1.1.8 |  | DEFLECTOR ROLL FRAME ASSY.#8 (BEFORE BRIDLE ROLL ASY.#03) | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
26.1.1.9 |  | DEFLECTOR ROLL FRAME ASSY.#9 (AFTER TURN DOWN ROLL ASSY.) | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
26.1.1.10 |  | DEFLECTOR ROLL FRAME ASSY.#10 (BEFORE WATER SPRAY UNIT) | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
26.1.1.11 |  | DEFLECTOR ROLL FRAME ASSY.#11 (BEFORE BRIDLE ROLL ASY.#04) | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
26.1.1.12 |  | DEFLECTOR ROLL FRAME ASSY.#12 (AFTER BRIDLE ROLL ASSY.# 8) | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
26.1.1.13 |  | DEFLECTOR ROLL FRAME ASSY.#13&14 (BEFORE CHEMICAL COATER) | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
26.1.1.14 |  | DEFLECTOR ROLL FRAME ASSY.#15 (BEFORE BRIDLE ROLL ASY.#09) | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
26.1.1.15 |  | DEFLECTOR ROLL FRAME ASSY.#16 (BEFORE LOGO MARKER) | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
26.1.1.16 |  | DEFLECTOR ROLL FRAME ASSY.#17 (BEFORE BRIDLE ROLL ASSY.#10) | date |  | 4d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 11-Oct-25 07:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
27 | 10 | Category 1 - COIL CAR ASSY @ RECOILER - Engg | TASK |  | 3d | 3d |  | 5 | IP | YES | 006-011 |  |  |  |  | 2d | 2d | 125d7h |  |  | 13-Oct-25 12:00 PM | 16-Oct-25 10:00 AM |  | 25-Mar-26 02:25 AM | 07-Nov-25 09:47 AM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
27.1 |  | COIL CAR ASSY @ RECOILER | Subtask |  | 3d | 3d |  |  | IP | YES | [5 empty] | 2d | 2d | 125d7h |  |  | 13-Oct-25 12:00 PM | 16-Oct-25 10:00 AM |  | 25-Mar-26 02:25 AM | 07-Nov-25 09:47 AM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
27.1.1 |  | Completion | step
27.1.1.1 |  | COIL CAR ASSY. @ RECOILER | date |  | 3d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 13-Oct-25 12:00 PM | 16-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
27.1.1.2 |  | DRAG CHAIN ASSY. @ RECOILER | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 13-Oct-25 12:00 PM | 15-Oct-25 10:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
27.1.1.3 |  | COIL SADDLE ASSY. @ RECOILER | date |  | 2d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 13-Oct-25 12:00 PM | 15-Oct-25 10:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
27.1.1.4 |  | PIT COVER-1A @ RECOILER | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 13-Oct-25 12:00 PM | 15-Oct-25 10:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
27.1.1.5 |  | PIT COVER-1B @ RECOILER | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 13-Oct-25 12:00 PM | 15-Oct-25 10:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
28 | 56 | Category 1 - TENSIOMETER ASSY - Engg | TASK |  | 4d | 4d |  | 15 | IP | YES | 006-014 |  |  |  |  | 4d | 4d | 127d7h |  |  | 17-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  | 27-Mar-26 02:25 AM | 07-Nov-25 09:47 AM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
28.1 |  | TENSIOMETER | Subtask |  | 4d | 4d |  |  | IP | YES | [5 empty] | 4d | 4d | 127d7h |  |  | 17-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  | 27-Mar-26 02:25 AM | 07-Nov-25 09:47 AM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
28.1.1 |  | Completion | step
28.1.1.1 |  | TENSIOMETER ASSY.#1 BEFORE FURNACE ENTRY | date |  | 4d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 17-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  |  | 07-Nov-25 09:47 AM | 07-Nov-25 10:47 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
28.1.1.2 |  | TENSIOMETER ASSY.#2 AFTER CAG | date |  | 4d |  |  |  | NS | YES | [5 empty] | 4d |  |  |  |  | 17-Oct-25 12:00 PM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
29 | 22 | Category 1 - PINCH ROLL ASSY. - Engg | TASK |  | 2d | 2d |  | 35 | IP | YES | 006-022 |  |  |  |  | 2d | 2d | 125d7h |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM |  | 25-Mar-26 02:25 AM | 07-Nov-25 09:48 AM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
29.1 |  | PINCH ROLL ASSY | Subtask |  | 2d | 2d |  |  | IP | YES | [5 empty] | 2d | 2d | 125d7h |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM |  | 25-Mar-26 02:25 AM | 07-Nov-25 09:48 AM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
29.1.1 |  | Completion | step
29.1.1.1 |  | ENTRY PINCH ROLL ASSY.#1&2 | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
29.1.1.2 |  | ENTRY PINCH ROLL ASSY.#3 | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
29.1.1.3 |  | ENTRY PINCH ROLL ASSY.#4 | date |  | 2d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM |  |  | 07-Nov-25 09:48 AM | 07-Nov-25 10:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
29.1.1.4 |  | ENTRY PINCH ROLL ASSY.#5 | date |  | 2d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM |  |  | 07-Nov-25 09:48 AM | 07-Nov-25 10:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
29.1.1.5 |  | EXIT PINCH ROLL ASSY. #1 | date |  | 2d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM |  |  | 07-Nov-25 09:48 AM | 07-Nov-25 10:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
29.1.1.6 |  | EXIT PINCH ROLL ASSY. #2 | date |  | 2d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM |  |  | 07-Nov-25 09:48 AM | 07-Nov-25 10:48 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
30 | 91 | Category 2 - COATER STRUCTURE - Engg | TASK |  | 5d | 5d |  | 56 | CO | YES | [7 empty] | 1h |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM |  |  | 07-Nov-25 09:50 AM | 07-Nov-25 10:50 AM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
30.1 |  | COATER STRUCTURE | Subtask |  | 5d | 5d |  |  | CO | NO | [7 empty] | 1h |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM |  |  | 07-Nov-25 09:50 AM | 07-Nov-25 10:50 AM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
30.1.1 |  | Completion | step
30.1.1.1 |  | COATER STRUCTURE | date |  | 5d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM |  |  | 07-Nov-25 09:50 AM | 07-Nov-25 10:50 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
31 | 74 | Category 2 - SQUEEZE ROLL ASSY. - Engg | TASK |  | 3d | 3d |  | 14 | IP | YES | 013-006 |  |  |  |  | 3d | 3d | 126d2h |  |  | 12-Aug-25 01:00 AM | 14-Aug-25 09:00 PM |  | 26-Mar-26 02:25 AM | 07-Nov-25 05:23 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
31.1 |  | SQUEEZE ROLL ASSY. | Subtask |  | 3d | 3d |  |  | IP | YES | [5 empty] | 3d | 3d | 126d2h |  |  | 12-Aug-25 01:00 AM | 14-Aug-25 09:00 PM |  | 26-Mar-26 02:25 AM | 07-Nov-25 05:23 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
31.1.1 |  | Completion | step
31.1.1.1 |  | SINGLE SQUEEZE ROLL ASSY. | date |  | 3d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 12-Aug-25 01:00 AM | 14-Aug-25 09:00 PM |  |  | 07-Nov-25 05:23 PM | 07-Nov-25 06:23 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
31.1.1.2 |  | VERTICAL SQUEEZE ROLL ASSY.@CAG | date |  | 3d |  |  |  | NS | YES | [5 empty] | 3d |  |  |  |  | 12-Aug-25 01:00 AM | 14-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 26-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
31.1.1.3 |  | DOUBLE SQUEEZE ROLL ASSY. @ CHROMATIC TANK | date |  | 3d |  |  |  | NS | YES | [5 empty] | 3d |  |  |  |  | 12-Aug-25 01:00 AM | 14-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 26-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
31.1.1.4 |  | PORTER BAR @ CLANING SECTION SQZ ROLL REMOVAL | date |  | 3d |  |  |  | NS | YES | [5 empty] | 3d |  |  |  |  | 12-Aug-25 01:00 AM | 14-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 26-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
32 | 41 | Category 1 - TURN ROLL ASSY. - Engg | TASK |  | 3d | 3d |  | 43 | CO | YES | [7 empty] | 2h |  |  | 18-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  |  | 07-Nov-25 05:23 PM | 07-Nov-25 06:24 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
32.1 |  | TURN ROLL ASSY. | Subtask |  | 3d | 3d |  |  | CO | YES | [7 empty] | 2h |  |  | 18-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  |  | 07-Nov-25 05:24 PM | 07-Nov-25 06:24 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
32.1.1 |  | Completion | step
32.1.1.1 |  | TURN UP ROLL ASSY. @CAG | date |  | 3d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  |  | 07-Nov-25 05:24 PM | 07-Nov-25 06:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
32.1.1.2 |  | TURN DOWN ROLL ASSY. @CAG | date |  | 3d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 18-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  |  | 07-Nov-25 05:24 PM | 07-Nov-25 06:24 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
33 | 14 | Category 1 - TABLE - Engg | TASK |  | 2d | 2d |  | 18 | IP | YES | 006-003 |  |  |  |  | 2d | 2d | 125d2h |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM |  | 25-Mar-26 02:25 AM | 07-Nov-25 05:25 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
33.1 |  | TABLE | Subtask |  | 2d | 2d |  |  | IP | YES | [5 empty] | 2d | 2d | 125d1h |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM |  | 25-Mar-26 02:25 AM | 07-Nov-25 05:25 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
33.1.1 |  | Completion | step
33.1.1.1 |  | PEELER TABLE ASSY.#1 | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
33.1.1.2 |  | PEELER TABLE ASSY.#2 | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
33.1.1.3 |  | PASSING TABLE ASSY#1 (D.D. SHEAR & PINCH ROLL#2) | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
33.1.1.4 |  | PASSING TABLE ASSY#2 (D.D. SHEAR & PINCH ROLL#3) | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
33.1.1.5 |  | ENTRY SCRAP DOWN TABLE ASSY#1 | date |  | 2d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM |  |  | 07-Nov-25 05:32 PM | 07-Nov-25 06:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
33.1.1.6 |  | ENTRY SCRAP DOWN TABLE ASSY#2 | date |  | 2d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM |  |  | 07-Nov-25 05:32 PM | 07-Nov-25 06:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
33.1.1.7 |  | ENTRY SCRAP TRAY ASSY. | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
33.1.1.8 |  | ENTRY SCRAP TROLLEY ASSY. | date |  | 2d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM |  |  | 07-Nov-25 05:32 PM | 07-Nov-25 06:32 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
33.1.1.9 |  | PASSING TABLE ASSY#3 (BEFORE PINCH ROLL#4) | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
33.1.1.10 |  | PASSING TABLE ASSY#4 (PINCH ROLL#4 & SEAM WELDER) | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
33.1.1.11 |  | PASSING TABLE ASSY#5 (SEAM WELDER & PINCH ROLL#5) | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
33.1.1.12 |  | PASSING TABLE ASSY#5 (BEFORE ENTRY FURNACE) | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
33.1.1.13 |  | PASSING TABLE ASSY#6 (COOLING AFTER GALVANIZING) | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
33.1.1.14 |  | PASSING TABLE ASSY#7 (STRIP HEATER ASSY.) | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
33.1.1.15 |  | EXIT THREADING TABLE ASSY. | date |  | 2d |  |  |  | NS | YES | [5 empty] | 2d |  |  |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
34 | 2 | Category 0 - Engg | TASK |  | 10d |  |  | 73 | IP | YES | 015-021 |  |  |  |  | 10d |  | 133d1h |  |  | 30-Nov-25 11:00 AM | 11-Dec-25 08:00 AM |  | 02-Apr-26 03:25 PM | 07-Nov-25 05:32 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
35 | 23 | Category 1 - PINCH ROLL ASSY. - Ordering & Manufacturing | TASK |  | 60d | 60d | 29 | 67 | CO | NO | [7 empty] | 103d16h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:14 AM | 02-Mar-26 03:38 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
35.1 |  | ENTRY PINCH ROLL ASSY.#1 | Subtask |  | 60d | 60d |  |  | CO | YES | [7 empty] | 40d12h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  |  | 13-Jan-26 09:09 AM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
35.1.1 |  | Release of PO | step |  |  |  |  | 35.1.2
35.1.1.1 |  | TOP PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:37 PM | 16-Jan-26 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.1.2 |  | CARDEN SHAFT COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:37 PM | 16-Jan-26 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.1.3 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:37 PM | 16-Jan-26 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.1.4 |  | COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:37 PM | 16-Jan-26 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.1.5 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:37 PM | 16-Jan-26 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.1.6 |  | GEAR BOX M082232,HOLLOW INPUT SOLID OUTPUT, FRAME 100L, MAKE- PBL GEAR RATIO 32.97 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.1.7 |  | MOTOR 2.2KW, 4POLE, SIZE-M2BAX100LA4 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Jan-26 11:29 AM | 29-Jan-26 12:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.1.8 |  | TOP PINCH ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.1.9 |  | BOTTOM PINCH ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.1.10 |  | HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.1.11 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:37 PM | 16-Jan-26 04:37 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.1.12 |  | CARDAN SHAFT KI FLEX 150 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.1.13 |  | PNU. CYL. BORE- 125,ROD-32,STK-80MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.1.14 |  | TUJ 60 TF - Y BEARING - ID60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 20-Jan-26 12:17 PM | 20-Jan-26 01:17 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.1.15 |  | M27_LOCK NUT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.1.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.1.17 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.1.18 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.1.19 |  | Hexagon nut IS 1363-Part2 - M12-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.1.20 |  | Hexagon nut IS 1363-Part2 - M30-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.1.21 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.1.22 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.1.23 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.1.24 |  | Spring Lock Washer IS 6735 - 12 | date |  | 1d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 23-Oct-25 03:00 AM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.1.2 |  | Ready for Assy | step |  |  |  | 35.1.1
35.1.2.1 |  | TOP PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:37 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.2.2 |  | CARDEN SHAFT COUPLING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:37 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.2.3 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:37 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.2.4 |  | COUPLING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:37 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.2.5 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:37 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.2.6 |  | GEAR BOX M082232,HOLLOW INPUT SOLID OUTPUT, FRAME 100L, MAKE- PBL GEAR RATIO 32.97 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.2.7 |  | MOTOR 2.2KW, 4POLE, SIZE-M2BAX100LA4 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.2.8 |  | TOP PINCH ROLL | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.2.9 |  | BOTTOM PINCH ROLL | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.2.10 |  | HOUSING | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.2.11 |  | TIE ROD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:37 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.2.12 |  | CARDAN SHAFT KI FLEX 150 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.2.13 |  | PNU. CYL. BORE- 125,ROD-32,STK-80MM | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.2.14 |  | TUJ 60 TF - Y BEARING - ID60 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.2.15 |  | M27_LOCK NUT | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.1.2.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.2.17 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.2.18 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.2.19 |  | Hexagon nut IS 1363-Part2 - M12-N | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.2.20 |  | Hexagon nut IS 1363-Part2 - M30-N | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.2.21 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.2.22 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.2.23 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.1.2.24 |  | Spring Lock Washer IS 6735 - 12 | date |  | 1d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 23-Oct-25 03:00 AM | 24-Oct-25 03:00 AM |  |  | 16-Feb-26 11:51 AM | 16-Feb-26 12:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.2 |  | ENTRY PINCH ROLL ASSY.#2 | Subtask |  | 60d | 60d |  |  | CO | YES | [7 empty] | 40d12h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  |  | 13-Jan-26 09:10 AM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
35.2.1 |  | Release of PO | step |  |  |  |  | 35.2.2
35.2.1.1 |  | TOP PINCH ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.1.2 |  | BOTTOM PINCH ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:41 PM | 16-Jan-26 04:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.2.1.3 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:41 PM | 16-Jan-26 04:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.2.1.4 |  | TOP PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:41 PM | 16-Jan-26 04:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.2.1.5 |  | ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:41 PM | 16-Jan-26 04:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.2.1.6 |  | COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:41 PM | 16-Jan-26 04:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.2.1.7 |  | COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:41 PM | 16-Jan-26 04:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.2.1.8 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:41 PM | 16-Jan-26 04:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.2.1.9 |  | GEAR BOX M082232,HOLLOW INPUT SOLID OUTPUT, FRAME 100L, MAKE- PBL GEAR RATIO 32.97 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.1.10 |  | MOTOR 2.2 KWx 1500RPM (FRAME SIZE- 100L) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Jan-26 11:30 AM | 29-Jan-26 12:30 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.2.1.11 |  | HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.1.12 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:41 PM | 16-Jan-26 04:41 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
35.2.1.13 |  | FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.1.14 |  | PNU. CYL. BORE DIA. 125 ROD DIA. 32 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.1.15 |  | CARDAN SHAFT KI FLEX 130 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.1.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.1.17 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.1.18 |  | Hexagon nut IS 1363-Part2 - M12-C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.1.19 |  | Hexagon nut IS 1363-Part2 - M12-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.1.20 |  | Hexagon nut IS 1363-Part2 - M30-C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.1.21 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M20 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.1.22 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.1.23 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M30-C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.1.24 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M36-C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.1.25 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.1.26 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.1.27 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.1.28 |  | Plain Washer (Type A) IS 2016 - 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.1.29 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.1.30 |  | Plain Washer (Type A) IS 2016 - 39 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.1.31 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.1.32 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.1.33 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.1.34 |  | LOCKNUT M27X2P | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.1.35 |  | SHEAR BLOCK- 15X15X80MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.1.36 |  | TUJ 60 TF - Y BEARING - ID60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.2 |  | Ready for Assy | step |  |  |  | 35.2.1
35.2.2.1 |  | TOP PINCH ROLL | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.2 |  | BOTTOM PINCH ROLL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.3 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:41 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.4 |  | TOP PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:41 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.5 |  | ROD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:41 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.6 |  | COUPLING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:41 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.7 |  | COUPLING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:41 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.8 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:41 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.9 |  | GEAR BOX M082232,HOLLOW INPUT SOLID OUTPUT, FRAME 100L, MAKE- PBL GEAR RATIO 32.97 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.10 |  | MOTOR 2.2 KWx 1500RPM (FRAME SIZE- 100L) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Jan-26 11:30 AM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.11 |  | HOUSING | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.12 |  | TIE ROD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:41 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.13 |  | FRAME | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.14 |  | PNU. CYL. BORE DIA. 125 ROD DIA. 32 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.15 |  | CARDAN SHAFT KI FLEX 130 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.17 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 60 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.18 |  | Hexagon nut IS 1363-Part2 - M12-C | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.19 |  | Hexagon nut IS 1363-Part2 - M12-N | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.20 |  | Hexagon nut IS 1363-Part2 - M30-C | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.21 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M20 x 70 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.22 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M24 x 80 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.23 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M30-C | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.24 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M36-C | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  | 0 |  |  | 0
35.2.2.25 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.2.26 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.2.27 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.2.28 |  | Plain Washer (Type A) IS 2016 - 30 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.2.29 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.2.30 |  | Plain Washer (Type A) IS 2016 - 39 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.2.31 |  | Spring Lock Washer IS 6735 - 12 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.2.32 |  | Spring Lock Washer IS 6735 - 20 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.2.33 |  | Spring Lock Washer IS 6735 - 24 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.2.34 |  | LOCKNUT M27X2P | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.2.35 |  | SHEAR BLOCK- 15X15X80MM | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.2.2.36 |  | TUJ 60 TF - Y BEARING - ID60 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3 |  | ENTRY PINCH ROLL ASSY.#3 | Subtask |  | 60d | 60d |  |  | CO | YES | [7 empty] | 46d16h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  |  | 06-Jan-26 02:41 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
35.3.1 |  | Ready for Assy | step |  |  |  |  | 35.3.2
35.3.1.1 |  | TOP PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:51 PM | 16-Jan-26 04:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.3.1.2 |  | CARDEN SHAFT COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:51 PM | 16-Jan-26 04:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.3.1.3 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:51 PM | 16-Jan-26 04:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.3.1.4 |  | COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:51 PM | 16-Jan-26 04:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.3.1.5 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:51 PM | 16-Jan-26 04:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.3.1.6 |  | GEAR BOX M082232,HOLLOW INPUT SOLID OUTPUT, FRAME 100L, MAKE- PBL GEAR RATIO 32.97 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.1.7 |  | MOTOR 2.2KW, 4POLE, SIZE-M2BAX100LA4 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 29-Jan-26 11:31 AM | 29-Jan-26 12:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.3.1.8 |  | TOP PINCH ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.1.9 |  | BOTTOM PINCH ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.1.10 |  | HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.1.11 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 16-Jan-26 03:51 PM | 16-Jan-26 04:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.3.1.12 |  | CARDAN SHAFT KI FLEX 150 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.1.13 |  | PNU. CYL. BORE- 125,ROD-32,STK-80MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 34d3h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 20-Jan-26 12:22 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.1.14 |  | TUJ 60 TF - Y BEARING - ID60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 34d3h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 20-Jan-26 12:22 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.1.15 |  | M27_LOCK NUT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.1.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 06-Jan-26 03:10 PM | 06-Jan-26 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.3.1.17 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 06-Jan-26 03:10 PM | 06-Jan-26 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.3.1.18 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 06-Jan-26 03:10 PM | 06-Jan-26 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.3.1.19 |  | Hexagon nut IS 1363-Part2 - M12-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 06-Jan-26 03:10 PM | 06-Jan-26 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.3.1.20 |  | Hexagon nut IS 1363-Part2 - M30-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 06-Jan-26 03:10 PM | 06-Jan-26 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.3.1.21 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 06-Jan-26 03:10 PM | 06-Jan-26 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.3.1.22 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 06-Jan-26 03:10 PM | 06-Jan-26 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.3.1.23 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 06-Jan-26 03:10 PM | 06-Jan-26 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.3.1.24 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 06-Jan-26 03:10 PM | 06-Jan-26 04:10 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.3.2 |  | Release of PO | step |  |  |  | 35.3.1
35.3.2.1 |  | TOP PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:51 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.2 |  | CARDEN SHAFT COUPLING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:51 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.3 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:51 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.4 |  | COUPLING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:51 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.5 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:51 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.6 |  | GEAR BOX M082232,HOLLOW INPUT SOLID OUTPUT, FRAME 100L, MAKE- PBL GEAR RATIO 32.97 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.7 |  | MOTOR 2.2KW, 4POLE, SIZE-M2BAX100LA4 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 25d15h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 29-Jan-26 11:31 AM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.8 |  | TOP PINCH ROLL | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.9 |  | BOTTOM PINCH ROLL | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.10 |  | HOUSING | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.11 |  | TIE ROD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 37d7h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 16-Jan-26 03:51 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.12 |  | CARDAN SHAFT KI FLEX 150 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.13 |  | PNU. CYL. BORE- 125,ROD-32,STK-80MM | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.14 |  | TUJ 60 TF - Y BEARING - ID60 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.15 |  | M27_LOCK NUT | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.16 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.17 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.18 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.19 |  | Hexagon nut IS 1363-Part2 - M12-N | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.20 |  | Hexagon nut IS 1363-Part2 - M30-N | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.21 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.22 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.23 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.3.2.24 |  | Spring Lock Washer IS 6735 - 12 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 26-Feb-26 04:02 PM | 26-Feb-26 05:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.4 |  | ENTRY PINCH ROLL ASSY.#4 | Subtask |  | 60d | 60d |  |  | CO | YES | [7 empty] | 100d9h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:14 AM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
35.4.1 |  | Release of PO | step |  |  |  |  | 35.4.2
35.4.1.1 |  | TOP PINCH ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 11:56 AM | 11-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.2 |  | BOTTOM PINCH ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:30 PM | 11-Nov-25 07:30 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.3 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 01:02 PM | 21-Nov-25 12:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.4 |  | TOP PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 01:02 PM | 21-Nov-25 12:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.5 |  | ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 01:02 PM | 21-Nov-25 12:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.6 |  | COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 01:02 PM | 21-Nov-25 12:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.7 |  | COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 01:02 PM | 21-Nov-25 12:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.8 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 01:02 PM | 21-Nov-25 12:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.9 |  | GEAR BOX M082232,HOLLOW INPUT SOLID OUTPUT, FRAME 100L, MAKE- PBL GEAR RATIO 32.97 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 87d7h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 01:02 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.10 |  | MOTOR 2.2 KWx 1500RPM (FRAME SIZE- 100L) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 71d4h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 01:02 PM | 29-Jan-26 11:31 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.11 |  | HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:29 PM | 11-Nov-25 07:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.12 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 8d7h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 01:02 PM | 21-Nov-25 12:35 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.13 |  | FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:29 PM | 11-Nov-25 07:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.14 |  | FRAME (GEAR BOX) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:29 PM | 11-Nov-25 07:29 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.15 |  | CARDAN SHAFT KI FLEX 150 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.16 |  | PNEU. CYL. BORE-125,ROD-32,STK-85 MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.17 |  | LOCKNUT M27X2P | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 87d7h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 01:02 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.18 |  | TUJ 60 TF - Y BEARING - ID60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 12-Nov-25 12:49 PM | 12-Nov-25 01:49 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.19 |  | SHEAR BLOCK- 15X15X80MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.20 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.22 |  | Hexagon nut IS 1363-Part2 - M12-C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.23 |  | Hexagon nut IS 1363-Part2 - M12-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.24 |  | Hexagon nut IS 1363-Part2 - M30-C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.25 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M20 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.26 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.27 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.28 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M30-C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.29 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M36-C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.30 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.31 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.32 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.33 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.34 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.35 |  | Plain Washer (Type A) IS 2016 - 39 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.36 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.37 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.38 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.1.39 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2 |  | Ready for Assy | step |  |  |  | 35.4.1
35.4.2.1 |  | TOP PINCH ROLL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 88d8h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 11:56 AM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.2 |  | BOTTOM PINCH ROLL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 88d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:29 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.3 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 88d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:29 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.4 |  | TOP PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 88d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:29 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.5 |  | ROD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 88d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:29 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.6 |  | COUPLING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 88d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:29 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.7 |  | COUPLING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 88d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:29 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.8 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 88d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:29 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.9 |  | GEAR BOX M082232,HOLLOW INPUT SOLID OUTPUT, FRAME 100L, MAKE- PBL GEAR RATIO 32.97 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 88d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:29 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.10 |  | MOTOR 2.2 KWx 1500RPM (FRAME SIZE- 100L) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 88d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:29 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.11 |  | HOUSING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 88d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:29 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.12 |  | TIE ROD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 88d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:29 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.13 |  | FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 88d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:29 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.14 |  | FRAME (GEAR BOX) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 88d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:29 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.15 |  | CARDAN SHAFT KI FLEX 150 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 90d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.16 |  | PNEU. CYL. BORE-125,ROD-32,STK-85 MM | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 90d16h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.17 |  | LOCKNUT M27X2P | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 88d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:29 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.18 |  | TUJ 60 TF - Y BEARING - ID60 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 88d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:29 PM | 16-Feb-26 11:52 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.19 |  | SHEAR BLOCK- 15X15X80MM | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.20 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 60 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.22 |  | Hexagon nut IS 1363-Part2 - M12-C | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.23 |  | Hexagon nut IS 1363-Part2 - M12-N | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.24 |  | Hexagon nut IS 1363-Part2 - M30-C | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.25 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M20 x 70 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.26 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M24 x 80 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.27 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.28 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M30-C | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.29 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M36-C | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.30 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.31 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.32 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.33 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.34 |  | Plain Washer (Type A) IS 2016 - 33 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.35 |  | Plain Washer (Type A) IS 2016 - 39 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.36 |  | Spring Lock Washer IS 6735 - 12 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.37 |  | Spring Lock Washer IS 6735 - 16 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.38 |  | Spring Lock Washer IS 6735 - 20 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.4.2.39 |  | Spring Lock Washer IS 6735 - 24 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:15 AM | 08-Nov-25 10:15 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5 |  | ENTRY PINCH ROLL ASSY.#5 | Subtask |  | 60d | 60d |  |  | CO | YES | [7 empty] | 100d9h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:14 AM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
35.5.1 |  | Release of PO | step |  |  |  |  | 35.5.2
35.5.1.1 |  | TOP PINCH ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 11:56 AM | 11-Nov-25 12:56 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.2 |  | BOTTOM PINCH ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:27 PM | 11-Nov-25 07:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.3 |  | TOP PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:27 PM | 21-Nov-25 12:38 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.4 |  | CARDEN SHAFT COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:27 PM | 21-Nov-25 12:38 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.5 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:27 PM | 21-Nov-25 12:38 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.6 |  | COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:27 PM | 21-Nov-25 12:38 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.7 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:27 PM | 21-Nov-25 12:38 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.8 |  | GEAR BOX M082232,HOLLOW INPUT SOLID OUTPUT, FRAME 100L, MAKE- PBL GEAR RATIO 32.97 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.1.9 |  | MOTOR 2.2KW, 4POLE, SIZE-M2BAX100LA4 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.1.10 |  | HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:27 PM | 11-Nov-25 07:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.11 |  | FRAME (GEAR BOX) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:27 PM | 11-Nov-25 07:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.12 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:27 PM | 11-Nov-25 07:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.13 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:27 PM | 21-Nov-25 12:38 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.14 |  | CARDAN SHAFT KI FLEX 150 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.15 |  | PNU. CYL. BORE- 125,ROD-32,STK-80MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.16 |  | SHEAR BLOCK- 15X15X80MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.1.17 |  | TUJ 60 TF - Y BEARING - ID60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 13h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:27 PM | 12-Nov-25 12:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.18 |  | M27_LOCK NUT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.1.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.20 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.22 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.23 |  | Hexagon nut IS 1363-Part2 - M12-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.24 |  | Hexagon nut IS 1363-Part2 - M30-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.25 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.26 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.27 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.28 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.29 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.30 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.31 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.32 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.1.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.2 |  | Ready for Assy | step |  |  |  | 35.5.1
35.5.2.1 |  | TOP PINCH ROLL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 11:56 AM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.2 |  | BOTTOM PINCH ROLL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.3 |  | TOP PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.4 |  | CARDEN SHAFT COUPLING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.5 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.6 |  | COUPLING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.7 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.8 |  | GEAR BOX M082232,HOLLOW INPUT SOLID OUTPUT, FRAME 100L, MAKE- PBL GEAR RATIO 32.97 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.9 |  | MOTOR 2.2KW, 4POLE, SIZE-M2BAX100LA4 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.10 |  | HOUSING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.11 |  | FRAME (GEAR BOX) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.12 |  | BASE FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.13 |  | TIE ROD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.14 |  | CARDAN SHAFT KI FLEX 150 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.15 |  | PNU. CYL. BORE- 125,ROD-32,STK-80MM | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 100d9h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.16 |  | SHEAR BLOCK- 15X15X80MM | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.17 |  | TUJ 60 TF - Y BEARING - ID60 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.18 |  | M27_LOCK NUT | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:27 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.5.2.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.2.20 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.2.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.2.22 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.2.23 |  | Hexagon nut IS 1363-Part2 - M12-N | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.2.24 |  | Hexagon nut IS 1363-Part2 - M30-N | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.2.25 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.2.26 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.2.27 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.2.28 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.2.29 |  | Spring Lock Washer IS 6735 - 12 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.2.30 |  | Spring Lock Washer IS 6735 - 16 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.2.31 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.2.32 |  | Spring Lock Washer IS 6735 - 24 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.5.2.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:16 AM | 08-Nov-25 10:16 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6 |  | EXIT PINCH ROLL ASSY. #1 | Subtask |  | 60d | 60d |  |  | CO | YES | [7 empty] | 100d9h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:14 AM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
35.6.1 |  | Release of PO | step |  |  |  |  | 35.6.2
35.6.1.1 |  | TOP PINCH ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.2 |  | BOTTOM PINCH ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.3 |  | TOP PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 21-Nov-25 12:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.4 |  | CARDEN SHAFT COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 21-Nov-25 12:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.5 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 21-Nov-25 12:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.6 |  | COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 21-Nov-25 12:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.7 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 21-Nov-25 12:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.8 |  | GEAR BOX M082228,HOLLOW INPUT SOLID OUTPUT, FRAME 112L, MAKE- PBL GEAR RATIO 28.27 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.1.9 |  | MOTOR 3.7 KW X 1500 RPM X FRAME SIZE 112M | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.1.10 |  | HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:22 PM | 11-Nov-25 07:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.11 |  | FRAME (GEAR BOX) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:22 PM | 11-Nov-25 07:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.12 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:22 PM | 11-Nov-25 07:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.13 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 21-Nov-25 12:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.14 |  | CARDAN SHAFT KI FLEX 150 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:22 PM | 11-Nov-25 07:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.15 |  | PNU. CYL. BORE- 125,ROD-32,STK-80MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:22 PM | 11-Nov-25 07:22 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.16 |  | SHEAR BLOCK- 15X15X80MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 50d17h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 06-Jan-26 02:44 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.17 |  | TUJ 60 TF - Y BEARING - ID60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 13h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 12-Nov-25 12:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.18 |  | M27_LOCK NUT | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.1.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.20 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.22 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.23 |  | Hexagon nut IS 1363-Part2 - M12-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.24 |  | Hexagon nut IS 1363-Part2 - M30-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.25 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.26 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.27 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.28 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.29 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.30 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.31 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.32 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.1.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.2 |  | Ready for Assy | step |  |  |  | 35.6.1
35.6.2.1 |  | TOP PINCH ROLL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.2 |  | BOTTOM PINCH ROLL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.3 |  | TOP PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.4 |  | CARDEN SHAFT COUPLING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.5 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.6 |  | COUPLING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.7 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.8 |  | GEAR BOX M082228,HOLLOW INPUT SOLID OUTPUT, FRAME 112L, MAKE- PBL GEAR RATIO 28.27 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.9 |  | MOTOR 3.7 KW X 1500 RPM X FRAME SIZE 112M | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.10 |  | HOUSING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.11 |  | FRAME (GEAR BOX) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.12 |  | BASE FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.13 |  | TIE ROD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.14 |  | CARDAN SHAFT KI FLEX 150 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:22 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.15 |  | PNU. CYL. BORE- 125,ROD-32,STK-80MM | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:22 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.16 |  | SHEAR BLOCK- 15X15X80MM | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.17 |  | TUJ 60 TF - Y BEARING - ID60 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.18 |  | M27_LOCK NUT | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 26-Feb-26 04:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.6.2.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.2.20 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.2.21 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.2.22 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 90 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.2.23 |  | Hexagon nut IS 1363-Part2 - M12-N | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.2.24 |  | Hexagon nut IS 1363-Part2 - M30-N | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.2.25 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.2.26 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.2.27 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.2.28 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.2.29 |  | Spring Lock Washer IS 6735 - 12 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.2.30 |  | Spring Lock Washer IS 6735 - 16 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.2.31 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.2.32 |  | Spring Lock Washer IS 6735 - 24 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.6.2.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:31 PM | 11-Nov-25 07:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7 |  | EXIT PINCH ROLL ASSY. #2 | Subtask |  | 60d | 60d |  |  | CO | YES | [7 empty] | 100d9h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  |  | 08-Nov-25 09:14 AM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
35.7.1 |  | Release of PO | step |  |  |  |  | 35.7.2
35.7.1.1 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.2 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.3 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.4 |  | BRG. BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.5 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.6 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.7 |  | BRG. BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.8 |  | SPACER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.9 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.10 |  | HOLDING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.11 |  | MOUNTING PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.12 |  | CARDEN SHAFT COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.13 |  | COUPLING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.14 |  | BRG. BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.15 |  | BRG. BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.16 |  | GEARBOX - M0822; RATIO - 28.27, FOOT MOUNTED -MAKE- PBL, SUITABLE FOR 3.7KW MOTOR @ 1500 RPM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.1.17 |  | MOTOR 3.7 KW 4 POLE 1500RPM (FRAME SIZE- M2BAX112MA4)FLANGE MOUNTING MAKE ABB | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.1.18 |  | TOP ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 11:55 AM | 11-Nov-25 12:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.19 |  | BOTTOM ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.20 |  | OPERATOR SIDE BOTTOM HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.21 |  | DRIVE SIDE BOTTOM HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.22 |  | DRIVE SIDE TOP HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.23 |  | OPERATOR SIDE TOP HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.24 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.25 |  | GEAR BOX FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.26 |  | CARDAN SHAFT KI FLEX 150 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 11:55 AM | 11-Nov-25 12:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.27 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.28 |  | TIE ROD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.29 |  | RETAINER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 9d2h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:33 PM | 21-Nov-25 12:43 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.30 |  | PNU. CYL. BORE-125,ROD-32,STK-85MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 11:55 AM | 11-Nov-25 12:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.31 |  | 22212_E-SPH.ROLLER BRG-ID60XOD110X28THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 13h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 12-Nov-25 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.32 |  | BEARING,SPHERICAL,22216 E(SPHERICAL ROLLER BEARING DR 80IDx140ODx33THK) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 13h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 12-Nov-25 12:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.33 |  | 30 X 40 X 5 AIA0300896 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.1.34 |  | AIA0700815-OIL SEAL-ID70XOD90X8 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 14-Nov-25 04:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.35 |  | AIA0900804-OIL SEAL_90x110x8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 2d16h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 14-Nov-25 04:12 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.36 |  | HOLLOW SHAFT ENCODER PART NO- 750729-25,MODEL-XHI 861 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.37 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.38 |  | STOPPER 15.00x15.00x60.00 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.39 |  | SHEAR BLOCK- 15X15X80MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.40 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 25 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.43 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.45 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.51 |  | Hexagon nut IS 1363-Part2 - M30-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.52 |  | Hexagon Nut Style 2 IS 1364-Part6 - M12-D-C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.53 |  | Hexagon Nut Style 2 IS 1364-Part6 - M20-D-C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.54 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.55 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.56 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.57 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.58 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.59 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.60 |  | Spring Lock Washer IS 6735 - 10 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.61 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.62 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.63 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.64 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.1.65 |  | Spring Lock Washer IS 6735 - 8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.2 |  | Ready for Assy | step |  |  |  | 35.7.1
35.7.2.1 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.2 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.3 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.4 |  | BRG. BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.5 |  | RETAINER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.6 |  | RETAINER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.7 |  | BRG. BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.8 |  | SPACER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.9 |  | RETAINER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.10 |  | HOLDING PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.11 |  | MOUNTING PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.12 |  | CARDEN SHAFT COUPLING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.13 |  | COUPLING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.14 |  | BRG. BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.15 |  | BRG. BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.16 |  | GEARBOX - M0822; RATIO - 28.27, FOOT MOUNTED -MAKE- PBL, SUITABLE FOR 3.7KW MOTOR @ 1500 RPM | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.17 |  | MOTOR 3.7 KW 4 POLE 1500RPM (FRAME SIZE- M2BAX112MA4)FLANGE MOUNTING MAKE ABB | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.18 |  | TOP ROLL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 98d2h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 11:55 AM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.19 |  | BOTTOM ROLL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:18 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.20 |  | OPERATOR SIDE BOTTOM HOUSING | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.2.21 |  | DRIVE SIDE BOTTOM HOUSING | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.2.22 |  | DRIVE SIDE TOP HOUSING | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.2.23 |  | OPERATOR SIDE TOP HOUSING | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.2.24 |  | BASE FRAME | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.2.25 |  | GEAR BOX FRAME | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.2.26 |  | CARDAN SHAFT KI FLEX 150 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:18 PM | 11-Nov-25 07:18 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
35.7.2.27 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:03 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.28 |  | TIE ROD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:03 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.29 |  | RETAINER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:03 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.30 |  | PNU. CYL. BORE-125,ROD-32,STK-85MM | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:47 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.31 |  | 22212_E-SPH.ROLLER BRG-ID60XOD110X28THK. | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:47 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.32 |  | BEARING,SPHERICAL,22216 E(SPHERICAL ROLLER BEARING DR 80IDx140ODx33THK) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 12:47 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.33 |  | 30 X 40 X 5 AIA0300896 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 97d |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:03 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.34 |  | AIA0700815-OIL SEAL-ID70XOD90X8 THK. | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:03 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.35 |  | AIA0900804-OIL SEAL_90x110x8 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 12-Nov-25 01:03 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.36 |  | HOLLOW SHAFT ENCODER PART NO- 750729-25,MODEL-XHI 861 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.37 |  | GREASE NIPPLE 1/8" BSP | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.38 |  | STOPPER 15.00x15.00x60.00 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.39 |  | SHEAR BLOCK- 15X15X80MM | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.40 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 25 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.41 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.42 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 35 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.43 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 50 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.45 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 70 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 70 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 16 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.51 |  | Hexagon nut IS 1363-Part2 - M30-N | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.52 |  | Hexagon Nut Style 2 IS 1364-Part6 - M12-D-C | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.53 |  | Hexagon Nut Style 2 IS 1364-Part6 - M20-D-C | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.54 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.55 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.56 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.57 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.58 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.59 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.60 |  | Spring Lock Washer IS 6735 - 10 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.61 |  | Spring Lock Washer IS 6735 - 12 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.62 |  | Spring Lock Washer IS 6735 - 16 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.63 |  | Spring Lock Washer IS 6735 - 20 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.64 |  | Spring Lock Washer IS 6735 - 24 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
35.7.2.65 |  | Spring Lock Washer IS 6735 - 8 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 97d13h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 11-Nov-25 06:33 PM | 26-Feb-26 04:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
36 | 44 | Category 1 - SUPPORT ROLL ASSY. - Engg | TASK |  | 3d | 3d |  | 41 | CO | YES | [7 empty] | 1h |  |  | 18-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  |  | 08-Dec-25 02:11 PM | 08-Dec-25 03:11 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
36.1 |  | SUPPORT ROLL ASSY. | Subtask |  | 3d | 3d |  |  | CO | NO | [7 empty] | 1h |  |  | 18-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  |  | 08-Dec-25 02:11 PM | 08-Dec-25 03:11 PM | [7 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
36.1.1 |  | Completion | step
36.1.1.1 |  | SUPPORT ROLL ASSY. | date |  | 3d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 18-Oct-25 12:00 PM | 22-Oct-25 03:00 AM |  |  | 08-Dec-25 02:11 PM | 08-Dec-25 03:11 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [11 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 0
37 | 81 | Category 1 - CHILL ROLL UNIT - Ordering & Manufacturing | TASK |  | 60d | 60d | 53 | 76 | IP | NO | 006-019 |  |  |  |  | 50d | 50d | 114d16h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | 10-Jan-26 09:38 AM |  |  |  | FAST |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
37.1 |  | CHILL ROLL ASSY. #1 | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 50d | 50d | 73d3h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 19-May-26 08:25 PM | 25-Feb-26 11:58 AM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
37.1.1 |  | Ready for Assy | step |  |  |  |  | 37.1.2
37.1.1.1 |  | WATER COOLED DEF. ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:55 PM | 03-Mar-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.2 |  | SNUBBER ROLL@ WATER COOLED DEF. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:55 PM | 03-Mar-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.3 |  | ARM FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:55 PM | 03-Mar-26 03:55 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.4 |  | TOP FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.5 |  | ROLL FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.6 |  | R.H. ARM CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.7 |  | L.H. ARM CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.8 |  | BRG. BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.9 |  | UPPER CHAIN COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.10 |  | LOWER CHAIN COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.11 |  | CYL. CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.12 |  | DUPLEX CHAIN (12B2), ROLLER DIA 12.07mm, PITCH 0.75'' (1238mm LONG), (65 NOS. LINKS), MAKE- RENOLD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.13 |  | ARM PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.14 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.15 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.16 |  | LOCKING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.17 |  | CYL. CLEVIS PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.18 |  | CYL. KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.19 |  | SPACER- 01 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.20 |  | SPACER- 02 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.21 |  | SPACER- 03 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.22 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.23 |  | RETAINER L.H | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.24 |  | END COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.25 |  | GEAR BOX END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.26 |  | SNUBBER ROLL SPROCKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.27 |  | GEAR BOX SPROCKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.28 |  | RETAINER R.H | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.29 |  | BASE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.30 |  | 3/4" BSP ROTARY UNIOIN R.H. THREAD, MAKE- SUPREME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.31 |  | 3/4" BSP ROTARY UNIOIN L.H. THREAD, MAKE- SUPREME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.32 |  | GEARED MOTOR- 1.5KW,1500RPM,4 POLE, RATIO-25.51:1, MODEL-M062222, MAKE- PBL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.33 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.34 |  | BEARING HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.35 |  | RETAINER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.36 |  | RETAINER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.37 |  | BEARING,SPHERICAL,22208 E(SPHERICAL ROLLER BRG D 40IDx80ODx23THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.38 |  | 22220_E-SPHERICAL ROLLER BEARING- ID100XOD180X46 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.39 |  | OIL SEAL-50ID x 70OD x 8THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.40 |  | 110X130X10_OIL SEAL_AIA1100831 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.41 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.42 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.43 |  | Cylindrical Pin IS 2393 - 10 x 20-DC | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.45 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.46 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.48 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.49 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.51 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.52 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.54 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.55 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.57 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.58 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.59 |  | Socket Head Cap Screw IS 2269 - M16 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.60 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.61 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.62 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.63 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.64 |  | Plain Washer (Type A) IS 2016 - 6.6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.65 |  | Spring Lock Washer IS 6735 - 6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.66 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.67 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.68 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.1.69 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 12:25 PM | 18-Mar-26 01:25 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2 |  | Release of PO | step |  |  |  | 37.1.1
37.1.2.1 |  | WATER COOLED DEF. ROLL | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.2 |  | SNUBBER ROLL@ WATER COOLED DEF. | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.3 |  | ARM FRAME | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.4 |  | TOP FRAME | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.5 |  | ROLL FRAME | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.6 |  | R.H. ARM CLEVIS | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.7 |  | L.H. ARM CLEVIS | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.8 |  | BRG. BLOCK | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.9 |  | UPPER CHAIN COVER | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.10 |  | LOWER CHAIN COVER | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.11 |  | CYL. CLEVIS | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.12 |  | DUPLEX CHAIN (12B2), ROLLER DIA 12.07mm, PITCH 0.75'' (1238mm LONG), (65 NOS. LINKS), MAKE- RENOLD | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.13 |  | ARM PIN | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.14 |  | KEEPER PLATE | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.15 |  | BUSH | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.16 |  | LOCKING PIN | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.17 |  | CYL. CLEVIS PIN | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.18 |  | CYL. KEEPER PLATE | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.19 |  | SPACER- 01 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.20 |  | SPACER- 02 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.21 |  | SPACER- 03 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.22 |  | END PLATE | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.23 |  | RETAINER L.H | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.24 |  | END COVER | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.25 |  | GEAR BOX END PLATE | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.26 |  | SNUBBER ROLL SPROCKET | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.27 |  | GEAR BOX SPROCKET | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.28 |  | RETAINER R.H | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.29 |  | BASE PLATE | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.30 |  | 3/4" BSP ROTARY UNIOIN R.H. THREAD, MAKE- SUPREME | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.31 |  | 3/4" BSP ROTARY UNIOIN L.H. THREAD, MAKE- SUPREME | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.32 |  | GEARED MOTOR- 1.5KW,1500RPM,4 POLE, RATIO-25.51:1, MODEL-M062222, MAKE- PBL | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.33 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.34 |  | BEARING HOUSING | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.35 |  | RETAINER-RH | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.36 |  | RETAINER-LH | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.37 |  | BEARING,SPHERICAL,22208 E(SPHERICAL ROLLER BRG D 40IDx80ODx23THK. mm) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 12:27 PM | 18-Mar-26 01:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.38 |  | 22220_E-SPHERICAL ROLLER BEARING- ID100XOD180X46 THK. | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 12:27 PM | 18-Mar-26 01:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.39 |  | OIL SEAL-50ID x 70OD x 8THK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 12:27 PM | 18-Mar-26 01:27 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.40 |  | 110X130X10_OIL SEAL_AIA1100831 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 12:26 PM | 18-Mar-26 01:26 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.41 |  | GREASE NIPPLE 1/8" BSP | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.42 |  | SHEAR BIOCK- 10x10x50mm | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.43 |  | Cylindrical Pin IS 2393 - 10 x 20-DC | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.45 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.46 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.48 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.49 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.51 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.52 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.54 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.55 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.57 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.58 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.59 |  | Socket Head Cap Screw IS 2269 - M16 x 100 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.60 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 50 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.61 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.62 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.63 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.64 |  | Plain Washer (Type A) IS 2016 - 6.6 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.65 |  | Spring Lock Washer IS 6735 - 6 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.66 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 16 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.67 |  | Spring Lock Washer IS 6735 - 12 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.68 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.1.2.69 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
37.2 |  | CHILL ROLL ASSY. #2 | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 50d | 50d | 73d3h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 19-May-26 08:25 PM | 25-Feb-26 11:59 AM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
37.2.1 |  | Ready for Assy | step |  |  |  |  | 37.2.2
37.2.1.1 |  | WATER COOLED DEF. ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.2 |  | SNUBBER ROLL@ WATER COOLED DEF. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.3 |  | ARM FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.4 |  | TOP FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.5 |  | ROLL FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.6 |  | R.H. ARM CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.7 |  | L.H. ARM CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.8 |  | BRG. BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.9 |  | UPPER CHAIN COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 10-Mar-26 05:31 PM | 10-Mar-26 06:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.10 |  | LOWER CHAIN COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 10-Mar-26 05:31 PM | 10-Mar-26 06:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.11 |  | CYL. CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.12 |  | DUPLEX CHAIN (12B2), ROLLER DIA 12.07mm, PITCH 0.75'' (1238mm LONG), (65 NOS. LINKS), MAKE- RENOLD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 10-Mar-26 05:31 PM | 10-Mar-26 06:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.13 |  | ARM PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.14 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.15 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.16 |  | LOCKING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.17 |  | CYL. CLEVIS PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.18 |  | CYL. KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.19 |  | SPACER- 01 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.20 |  | SPACER- 02 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.21 |  | SPACER- 03 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.22 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.23 |  | RETAINER L.H | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.24 |  | END COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.25 |  | GEAR BOX END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.26 |  | SNUBBER ROLL SPROCKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.27 |  | GEAR BOX SPROCKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.28 |  | RETAINER R.H | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.29 |  | BASE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.30 |  | 3/4" BSP ROTARY UNIOIN R.H. THREAD, MAKE- SUPREME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.31 |  | 3/4" BSP ROTARY UNIOIN L.H. THREAD, MAKE- SUPREME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.32 |  | GEARED MOTOR- 1.5KW,1500RPM,4 POLE, RATIO-25.51:1, MODEL-M062222, MAKE- PBL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.33 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.34 |  | BEARING HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.35 |  | RETAINER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.36 |  | RETAINER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.37 |  | BEARING,SPHERICAL,22208 E(SPHERICAL ROLLER BRG D 40IDx80ODx23THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.38 |  | 22220_E-SPHERICAL ROLLER BEARING- ID100XOD180X46 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.39 |  | OIL SEAL-50ID x 70OD x 8THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.40 |  | 110X130X10_OIL SEAL_AIA1100831 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.41 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.42 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.43 |  | Cylindrical Pin IS 2393 - 10 x 20-DC | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.45 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.46 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.48 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.49 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.51 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.52 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.54 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.55 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.57 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.58 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.59 |  | Socket Head Cap Screw IS 2269 - M16 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.60 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.61 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.62 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.63 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.64 |  | Plain Washer (Type A) IS 2016 - 6.6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.65 |  | Spring Lock Washer IS 6735 - 6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.66 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.67 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.68 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.1.69 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 6d10h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 03-Mar-26 02:59 PM | 10-Mar-26 05:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2 |  | Release of PO | step |  |  |  | 37.2.1
37.2.2.1 |  | WATER COOLED DEF. ROLL | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.2 |  | SNUBBER ROLL@ WATER COOLED DEF. | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.3 |  | ARM FRAME | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.4 |  | TOP FRAME | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.5 |  | ROLL FRAME | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.6 |  | R.H. ARM CLEVIS | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.7 |  | L.H. ARM CLEVIS | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.8 |  | BRG. BLOCK | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.9 |  | UPPER CHAIN COVER | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.10 |  | LOWER CHAIN COVER | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.11 |  | CYL. CLEVIS | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.12 |  | DUPLEX CHAIN (12B2), ROLLER DIA 12.07mm, PITCH 0.75'' (1238mm LONG), (65 NOS. LINKS), MAKE- RENOLD | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.13 |  | ARM PIN | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.14 |  | KEEPER PLATE | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.15 |  | BUSH | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.16 |  | LOCKING PIN | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.17 |  | CYL. CLEVIS PIN | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.18 |  | CYL. KEEPER PLATE | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.19 |  | SPACER- 01 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.20 |  | SPACER- 02 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.21 |  | SPACER- 03 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.22 |  | END PLATE | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.23 |  | RETAINER L.H | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.24 |  | END COVER | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.25 |  | GEAR BOX END PLATE | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.26 |  | SNUBBER ROLL SPROCKET | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.27 |  | GEAR BOX SPROCKET | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.28 |  | RETAINER R.H | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.29 |  | BASE PLATE | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.30 |  | 3/4" BSP ROTARY UNIOIN R.H. THREAD, MAKE- SUPREME | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.31 |  | 3/4" BSP ROTARY UNIOIN L.H. THREAD, MAKE- SUPREME | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.32 |  | GEARED MOTOR- 1.5KW,1500RPM,4 POLE, RATIO-25.51:1, MODEL-M062222, MAKE- PBL | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.33 |  | PNEU. CYL. BORE-160,ROD-40,STK-100 MM,MSO160 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.34 |  | BEARING HOUSING | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.35 |  | RETAINER-RH | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.36 |  | RETAINER-LH | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.37 |  | BEARING,SPHERICAL,22208 E(SPHERICAL ROLLER BRG D 40IDx80ODx23THK. mm) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 12:31 PM | 18-Mar-26 01:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.38 |  | 22220_E-SPHERICAL ROLLER BEARING- ID100XOD180X46 THK. | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 12:31 PM | 18-Mar-26 01:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.39 |  | OIL SEAL-50ID x 70OD x 8THK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 12:31 PM | 18-Mar-26 01:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.40 |  | 110X130X10_OIL SEAL_AIA1100831 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 12:31 PM | 18-Mar-26 01:31 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.41 |  | GREASE NIPPLE 1/8" BSP | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.42 |  | SHEAR BIOCK- 10x10x50mm | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.43 |  | Cylindrical Pin IS 2393 - 10 x 20-DC | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.44 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.45 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.46 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.48 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.49 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.51 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.52 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.54 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.55 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.57 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.58 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.59 |  | Socket Head Cap Screw IS 2269 - M16 x 100 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.60 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 50 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.61 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.62 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.63 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.64 |  | Plain Washer (Type A) IS 2016 - 6.6 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.65 |  | Spring Lock Washer IS 6735 - 6 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.66 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 16 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.67 |  | Spring Lock Washer IS 6735 - 12 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.68 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
37.2.2.69 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 90 | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 19-May-26 08:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38 | 89 | Category 2 - DRYER - Ordering & Manufacturing | TASK |  | 120d | 120d | 45 | 94 | IP | NO | 005-001 |  |  |  |  | 120d | 120d | 141d17h |  |  | 17-Aug-25 08:00 AM | 26-Dec-25 02:00 PM | 28-Mar-26 02:25 AM | 06-Aug-26 03:25 PM | 26-Feb-26 03:56 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
38.1 |  | HOT AIR DRYER ASSY.#1 @ CLEANING SECTION | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 120d | 120d | 141d17h |  |  | 17-Aug-25 08:00 AM | 26-Dec-25 02:00 PM |  | 06-Aug-26 03:25 PM | 26-Feb-26 03:56 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
38.1.1 |  | Release of PO | step |  |  |  |  | 38.1.2
38.1.1.1 |  | Hot Air Dryer Casing | date |  | 10d |  |  |  | IP | YES | [5 empty] | 10d |  | 28d8h |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM |  | 08-Apr-26 06:25 AM | 02-Mar-26 05:37 PM | [8 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.2 |  | Header 01 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.3 |  | Header 02 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.4 |  | Side Cover | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.5 |  | Vertical Support 01 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.6 |  | Vertical Support 02 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.7 |  | Tap Plate | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.8 |  | 2527-AIR-01-01-00-008 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.9 |  | Support Roll | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.10 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M12 x 35 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.11 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 40, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.12 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 45 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.13 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M20 x 55, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.14 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.15 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.16 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.17 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.18 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.19 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.1.20 |  | UCP-206 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2 |  | Ready for Assy | step |  |  |  | 38.1.1
38.1.2.1 |  | Hot Air Dryer Casing | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.2 |  | Header 01 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.3 |  | Header 02 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.4 |  | Side Cover | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.5 |  | Vertical Support 01 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.6 |  | Vertical Support 02 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.7 |  | Tap Plate | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.8 |  | 2527-AIR-01-01-00-008 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.9 |  | Support Roll | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.10 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M12 x 35 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.11 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 40, CL 8.8 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.12 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 45 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.13 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M20 x 55, CL 8.8 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.14 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.15 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.16 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.17 |  | Spring Lock Washer IS 6735 - 12 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.18 |  | Spring Lock Washer IS 6735 - 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.19 |  | Spring Lock Washer IS 6735 - 20 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.1.2.20 |  | UCP-206 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
38.2 |  | LOGO DRYER @ LOGO MARKER | Subtask |  | 120d |  |  |  | IP | YES | [5 empty] | 120d |  | 141d17h |  |  | 17-Aug-25 08:00 AM | 26-Dec-25 02:00 PM |  | 06-Aug-26 03:25 PM | 26-Feb-26 03:56 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
38.3 |  | COLD AIR DRYER @ CAG | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 120d | 120d | 141d17h |  |  | 17-Aug-25 08:00 AM | 26-Dec-25 02:00 PM |  | 06-Aug-26 03:25 PM | 26-Feb-26 03:56 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
38.3.1 |  | Release of PO | step |  |  |  |  | 38.3.2
38.3.1.1 |  | Hot Air Dryer Casing | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.1.2 |  | Header 01 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.1.3 |  | Header 02 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.1.4 |  | Side Cover | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.1.5 |  | BLOWER: MODEL-ECBB-2- 35 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.1.6 |  | BASE PLATE- 950x200x20thk. | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.1.7 |  | BASE PLATE- 900x150x18thk. | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.1.8 |  | GAS KIT | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.1.9 |  | GAS KIT | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.1.10 |  | DUCT | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.2 |  | Ready for Assy | step |  |  |  | 38.3.1
38.3.2.1 |  | Hot Air Dryer Casing | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.2.2 |  | Header 01 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.2.3 |  | Header 02 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.2.4 |  | Side Cover | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.2.5 |  | BLOWER: MODEL-ECBB-2- 35 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.2.6 |  | BASE PLATE- 950x200x20thk. | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.2.7 |  | BASE PLATE- 900x150x18thk. | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.2.8 |  | GAS KIT | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.2.9 |  | GAS KIT | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.3.2.10 |  | DUCT | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.4 |  | HOT AIR DRYER | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 120d | 120d | 141d17h |  |  | 17-Aug-25 08:00 AM | 26-Dec-25 02:00 PM |  | 06-Aug-26 03:25 PM | 26-Feb-26 03:56 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
38.4.1 |  | Release of PO | step |  |  |  |  | 38.4.2
38.4.1.1 |  | Hot Air Dryer Casing | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.4.1.2 |  | Header 01 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.4.1.3 |  | Header 02 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.4.1.4 |  | Side Cover | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.4.1.5 |  | BASE PLATE- 950x200x20thk. | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.4.1.6 |  | BASE PLATE- 900x150x18thk. | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.4.1.7 |  | GAS KIT | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.4.2 |  | Ready for Assy | step |  |  |  | 38.4.1
38.4.2.1 |  | Hot Air Dryer Casing | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.4.2.2 |  | Header 01 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.4.2.3 |  | Header 02 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.4.2.4 |  | Side Cover | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [10 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.4.2.5 |  | BASE PLATE- 950x200x20thk. | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.4.2.6 |  | BASE PLATE- 900x150x18thk. | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
38.4.2.7 |  | GAS KIT | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39 | 136 | Category 1 - SENSOR - Ordering & Manufacturing | TASK |  | 120d | 120d | 46 | 95 | IP | NO | 006-002 |  |  |  |  | 120d | 120d | 141d17h |  |  | 17-Aug-25 08:00 AM | 26-Dec-25 02:00 PM | 28-Mar-26 02:25 AM | 06-Aug-26 03:25 PM | 26-Feb-26 03:58 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
39.1 |  | EPC SENSOR ASSY.@ RECOILER | Subtask |  | 65d |  |  |  | IP | YES | [5 empty] | 65d |  | 86d17h |  |  | 17-Aug-25 08:00 AM | 27-Oct-25 04:00 PM |  | 07-Jun-26 11:25 AM | 26-Feb-26 03:58 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
39.2 |  | CPC SENSOR ASSY.@ STEERING ASSY. | Subtask |  | 65d |  |  |  | IP | YES | [5 empty] | 65d |  | 86d17h |  |  | 17-Aug-25 08:00 AM | 27-Oct-25 04:00 PM |  | 07-Jun-26 11:25 AM | 26-Feb-26 03:58 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
39.3 |  | BASE FRAME CPC SENSOR ASSY. | Subtask |  | 65d |  |  |  | IP | YES | [5 empty] | 65d |  | 86d17h |  |  | 17-Aug-25 08:00 AM | 27-Oct-25 04:00 PM |  | 07-Jun-26 11:25 AM | 26-Feb-26 03:58 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
39.4 |  | EPC SENSOR ASSY | Subtask |  | 120d | 120d |  |  | IP | YES | [5 empty] | 120d | 120d | 141d17h |  |  | 17-Aug-25 08:00 AM | 26-Dec-25 02:00 PM |  | 06-Aug-26 03:25 PM | 26-Feb-26 03:58 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
39.4.1 |  | Release of PO | step |  |  |  |  | 39.4.2
39.4.1.1 |  | COLUMN FRAME | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.2 |  | CANOPY | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.3 |  | TOP FRAME | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.4 |  | BOTTOM FRAME | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.5 |  | PASSING TABLE #1 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.6 |  | PASSING TABLE #2 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.7 |  | BOTTOM PLATE | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.8 |  | TUBE LIGHT | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.9 |  | CAMERA | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.10 |  | BAKELITE PLATE 260 X 500 X 10MM THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.11 |  | BAKELITE PLATE 260 X 540 X 10MM THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 50 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.13 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.14 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.15 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.16 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.17 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.18 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 90 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.19 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.20 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.1.21 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 17-Aug-25 08:00 AM | 28-Aug-25 05:00 AM | 28-Mar-26 02:25 AM | 08-Apr-26 06:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
39.4.2 |  | Ready for Assy | step |  |  |  | 39.4.1
39.4.2.1 |  | COLUMN FRAME | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.2 |  | CANOPY | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.3 |  | TOP FRAME | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.4 |  | BOTTOM FRAME | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.5 |  | PASSING TABLE #1 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.6 |  | PASSING TABLE #2 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.7 |  | BOTTOM PLATE | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.8 |  | TUBE LIGHT | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.9 |  | CAMERA | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.10 |  | BAKELITE PLATE 260 X 500 X 10MM THK | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.11 |  | BAKELITE PLATE 260 X 540 X 10MM THK | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.12 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 50 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.13 |  | Spring Lock Washer IS 6735 - 20 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.14 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.15 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 35 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.16 |  | Spring Lock Washer IS 6735 - 12 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.17 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.18 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 90 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.19 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.20 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
39.4.2.21 |  | Socket Countersunk Head Cap Screw IS 6761 - M6 x 16 | date |  | 110d |  |  |  | NS | NO | [5 empty] | 110d |  |  |  |  | 28-Aug-25 05:00 AM | 26-Dec-25 02:00 PM | 08-Apr-26 06:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
40 | 139 | Category 1 - TANK - Ordering & Manufacturing | TASK |  | 70d |  | 47 | 86 | IP | NO | 006-007 |  |  |  |  | 70d |  | 88d9h |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 18-Jun-26 08:25 AM | 02-Mar-26 05:05 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
41 | 45 | Category 1 - SUPPORT ROLL ASSY. - Ordering & Manufacturing | TASK |  | 60d | 60d | 36 | 77 | IP | YES | 006-018 |  |  |  |  | 60d | 60d | 72d1h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 27-May-26 01:25 PM | 09-Mar-26 05:29 PM |  |  |  | STUCK |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
41.1 |  | SUPPORT ROLL FRAME ASSY.#02 | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 60d | 60d | 72d1h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 27-May-26 01:25 PM | 09-Mar-26 05:29 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
41.1.1 |  | Release of PO | step |  |  |  |  | 41.1.2
41.1.1.1 |  | PLATE 220 X 115 X 20 MM THK | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.1.1.2 |  | SUPPORT ROLL FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 09-Mar-26 05:30 PM | 09-Mar-26 06:30 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.1.1.3 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.1.1.4 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.1.1.5 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.1.1.6 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.1.1.7 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.1.1.8 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.1.2 |  | Ready for Assy | step |  |  |  | 41.1.1
41.1.2.1 |  | PLATE 220 X 115 X 20 MM THK | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 27-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.1.2.2 |  | SUPPORT ROLL FRAME | date |  | 50d |  |  |  | NS | YES | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 23-Mar-26 02:25 AM | 16-May-26 07:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.1.2.3 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 27-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.1.2.4 |  | Spring Lock Washer IS 6735 - 16 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 27-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.1.2.5 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 27-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.1.2.6 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 27-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.1.2.7 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 27-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.1.2.8 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 27-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.2 |  | SUPPORT ROLL ASSY. | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 60d | 60d | 72d1h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 27-May-26 01:25 PM | 09-Mar-26 05:29 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
41.2.1 |  | Release of PO | step |  |  |  |  | 41.2.2
41.2.1.1 |  | SUPPORT ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 20-Mar-26 01:02 PM | 20-Mar-26 02:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.2.1.2 |  | UCP-206 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.2.2 |  | Ready for Assy | step |  |  |  | 41.2.1
41.2.2.1 |  | SUPPORT ROLL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 20-Mar-26 01:02 PM | 20-Mar-26 02:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
41.2.2.2 |  | UCP-206 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 27-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42 | 145 | Category 1 - ECL Process Tank Assembly- Ordering & Manufacturing | TASK |  | 70d | 70d | 48 | 87 | IP | NO | 006-008 |  |  |  |  | 70d | 70d | 74d7h |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 18-Jun-26 08:25 AM | 18-Mar-26 12:49 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
42.1 |  | ECL Process Tank Assembly | Subtask |  | 70d | 70d |  |  | IP | YES | [5 empty] | 70d | 70d | 74d7h |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM |  | 18-Jun-26 08:25 AM | 18-Mar-26 12:49 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
42.1.1 |  | Release of PO | step |  |  |  |  | 42.1.2
42.1.1.1 |  | Process Tank Casing | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.2 |  | Support | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.3 |  | Jactuator Cover | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.4 |  | Electrode Cover | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.5 |  | Electrode Cover | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.6 |  | Fume Exhaust Cover | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.7 |  | Sink Roll Cover | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.8 |  | Sink Roll Cover | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.9 |  | Deflector Roll Cover | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.10 |  | Stand | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.11 |  | Support Bracket | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.12 |  | Guide Bar | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.13 |  | Packing | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.14 |  | Packing | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.15 |  | Packing | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.16 |  | Packing | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.17 |  | Packing | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.18 |  | Packing | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.19 |  | Clamp Plate | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.20 |  | Packing | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.21 |  | Clamp Plate | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.22 |  | Packing | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.23 |  | Clamp Plate | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.1.24 |  | Packing | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.25 |  | Clamp Plate | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.26 |  | Clamp Plate | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.27 |  | Packing | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.28 |  | Packing | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.29 |  | Clamp Plate | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.30 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M12 x 60, CL- 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.31 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 35, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.32 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 55, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.33 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 35 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.34 |  | Socket Head Cap Screw IS 2269 - M16 x 45 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.35 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 50 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.36 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M24 x 50, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.37 |  | Hexagon Nut Style 1 IS 1364-Part3 - M10-D-N, CL-8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.38 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.39 |  | Spring Lock Washer IS 6735 - 10 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.40 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.41 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.1.42 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2 |  | Ready for Assy | step |  |  |  | 42.1.1
42.1.2.1 |  | Process Tank Casing | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.2 |  | Support | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.3 |  | Jactuator Cover | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.4 |  | Electrode Cover | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.5 |  | Electrode Cover | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.6 |  | Fume Exhaust Cover | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.7 |  | Sink Roll Cover | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.8 |  | Sink Roll Cover | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.9 |  | Deflector Roll Cover | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.10 |  | Stand | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.11 |  | Support Bracket | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.12 |  | Guide Bar | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.13 |  | Packing | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.14 |  | Packing | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.15 |  | Packing | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.16 |  | Packing | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.17 |  | Packing | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.18 |  | Packing | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.19 |  | Clamp Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.20 |  | Packing | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.21 |  | Clamp Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.22 |  | Packing | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.23 |  | Clamp Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.1.2.24 |  | Packing | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.25 |  | Clamp Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.26 |  | Clamp Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.27 |  | Packing | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.28 |  | Packing | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.29 |  | Clamp Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.30 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M12 x 60, CL- 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.31 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 35, CL 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.32 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 55, CL 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.33 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 35 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.34 |  | Socket Head Cap Screw IS 2269 - M16 x 45 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.35 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 50 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.36 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M24 x 50, CL 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.37 |  | Hexagon Nut Style 1 IS 1364-Part3 - M10-D-N, CL-8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.38 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.39 |  | Spring Lock Washer IS 6735 - 10 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.40 |  | Spring Lock Washer IS 6735 - 12 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.41 |  | Spring Lock Washer IS 6735 - 16 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.1.2.42 |  | Spring Lock Washer IS 6735 - 24 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2 |  | Deflector Roll Assembly | Subtask |  | 70d | 70d |  |  | IP | YES | [5 empty] | 70d | 70d | 74d7h |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM |  | 18-Jun-26 08:25 AM | 18-Mar-26 12:50 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
42.2.1 |  | Release of PO | step |  |  |  |  | 42.2.2
42.2.1.1 |  | Deflector Roll | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.2 |  | Squeeze Roll | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.3 |  | Base Frame | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.4 |  | Side frame | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.5 |  | Mounting Plate | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.6 |  | Guide Plate | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.7 |  | Guide Plate | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.8 |  | Adaptor | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.9 |  | Lock Nut | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.10 |  | Pneumatic Cylinder, ISO No.15552, Bore dia.-100, Rod dia. - 25, Stroke -100, Mounting - Head flange mtg., Working pressure- 5 Bar, Make Parker / eq. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.11 |  | Support | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.12 |  | Full Gear Coupling, Model - AFG-103, Make - Alliance / Eqi., Power- 5.5 KW, O/P RPMv - 57.32, Torque - 917Nm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.13 |  | Spacer | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.14 |  | Spacer | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.15 |  | Propeller Shaft Compressed Length-924.6mm,Slip Movement- 50.8mm,Make-Hardy Spicer/EQ,Series-1260 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.16 |  | Adaptor Roll Side | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.17 |  | Adaptor GM Side | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.18 |  | Coupling Guard | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.19 |  | Tie Bracket | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.20 |  | Sim Plates | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.21 |  | Bearing Unit-Take up, Make-SKF/EQ,Shaft Dia-60mm,Model No. UCT 212,Housing- T 212/Y,Bearing- UC 212 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.22 |  | Bearing Unit-Plummer Block , Make-SKF/EQ, Fixed End, Shaft Dia-80 mm, Housing-SNL 518-615, BRG No. 23218 CCL/W33, Adapter Sleeve-H 2318, Locating ring-2 x FRB 6.25/160,Seals- 2 x TSN 518 C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.23 |  | Bearing Unit-Plummer Block , Make-SKF/EQ, Flating End, Shaft Dia-80 mm, Housing-SNL 518-615, BRG No. 23218 CCL/W33, Adapter Sleeve-H 2318, Seals-2 x TSN 518 C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 12:59 PM | 18-Mar-26 01:59 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.24 |  | Parallel Key, Type-A-B,IS:2048,Size:W18 x H11 x L80 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.1.25 |  | Parallel Key, Type-A-B,IS:2048,Size:W16 x H10 x L58 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.26 |  | Solid shaft gearmotor, Solid shaft, IEC flange MTG for 4 kW I/P Motor, Ratio-9, Make-Bonfigoli, Model No-AS 45 P 9 100 B5 B3 BE 100LA 4 240415-50 IP55 CLF B5 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.27 |  | Solid shaft gearmotor, Solid shaft, IEC flange MTG for 2.2 kW I/P Motor, Ratio-6.22, Make-Bonfigoli, Model No-AS 30 P 6.22 100 B5 B3 BE 100LA 4 240/415-50 IP55 CLF B5 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.28 |  | Split Pin,Nominal Dia-6.3 mm x Length-70 mm,As per DIN EN ISO 1234 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.29 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M12 x 50, CL- 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.30 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M12 x 50, CL- 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.31 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M12 x 45, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.32 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 45, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.33 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 50, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.34 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 70 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.35 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M20 x 120, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.36 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.37 |  | Hexagon Nut Style 1 IS 1364-Part3 - M16-D-N | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.38 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N, CL-8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.39 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M30-N | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.40 |  | Plain Washer (Type A) IS 2016 - 30 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.41 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.42 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.43 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.44 |  | Spring Lock Washer IS 6735 - 8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.1.45 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M8 x 20, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2 |  | Ready for Assy | step |  |  |  | 42.2.1
42.2.2.1 |  | Deflector Roll | date |  | 60d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  |  | 23-Mar-26 10:07 AM | 23-Mar-26 11:07 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.2 |  | Squeeze Roll | date |  | 60d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  |  | 23-Mar-26 10:07 AM | 23-Mar-26 11:07 AM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.3 |  | Base Frame | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.4 |  | Side frame | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.5 |  | Mounting Plate | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.6 |  | Guide Plate | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.7 |  | Guide Plate | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.8 |  | Adaptor | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.9 |  | Lock Nut | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.10 |  | Pneumatic Cylinder, ISO No.15552, Bore dia.-100, Rod dia. - 25, Stroke -100, Mounting - Head flange mtg., Working pressure- 5 Bar, Make Parker / eq. | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.11 |  | Support | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.12 |  | Full Gear Coupling, Model - AFG-103, Make - Alliance / Eqi., Power- 5.5 KW, O/P RPMv - 57.32, Torque - 917Nm | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.13 |  | Spacer | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.14 |  | Spacer | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.15 |  | Propeller Shaft Compressed Length-924.6mm,Slip Movement- 50.8mm,Make-Hardy Spicer/EQ,Series-1260 | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.16 |  | Adaptor Roll Side | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.17 |  | Adaptor GM Side | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.18 |  | Coupling Guard | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.19 |  | Tie Bracket | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.20 |  | Sim Plates | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.21 |  | Bearing Unit-Take up, Make-SKF/EQ,Shaft Dia-60mm,Model No. UCT 212,Housing- T 212/Y,Bearing- UC 212 | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.22 |  | Bearing Unit-Plummer Block , Make-SKF/EQ, Fixed End, Shaft Dia-80 mm, Housing-SNL 518-615, BRG No. 23218 CCL/W33, Adapter Sleeve-H 2318, Locating ring-2 x FRB 6.25/160,Seals- 2 x TSN 518 C | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.23 |  | Bearing Unit-Plummer Block , Make-SKF/EQ, Flating End, Shaft Dia-80 mm, Housing-SNL 518-615, BRG No. 23218 CCL/W33, Adapter Sleeve-H 2318, Seals-2 x TSN 518 C | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.24 |  | Parallel Key, Type-A-B,IS:2048,Size:W18 x H11 x L80 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
42.2.2.25 |  | Parallel Key, Type-A-B,IS:2048,Size:W16 x H10 x L58 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.26 |  | Solid shaft gearmotor, Solid shaft, IEC flange MTG for 4 kW I/P Motor, Ratio-9, Make-Bonfigoli, Model No-AS 45 P 9 100 B5 B3 BE 100LA 4 240415-50 IP55 CLF B5 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.27 |  | Solid shaft gearmotor, Solid shaft, IEC flange MTG for 2.2 kW I/P Motor, Ratio-6.22, Make-Bonfigoli, Model No-AS 30 P 6.22 100 B5 B3 BE 100LA 4 240/415-50 IP55 CLF B5 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.28 |  | Split Pin,Nominal Dia-6.3 mm x Length-70 mm,As per DIN EN ISO 1234 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.29 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M12 x 50, CL- 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.30 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M12 x 50, CL- 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.31 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M12 x 45, CL 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.32 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 45, CL 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.33 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 50, CL 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.34 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 70 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.35 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M20 x 120, CL 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.36 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.37 |  | Hexagon Nut Style 1 IS 1364-Part3 - M16-D-N | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.38 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N, CL-8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.39 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M30-N | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.40 |  | Plain Washer (Type A) IS 2016 - 30 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.41 |  | Spring Lock Washer IS 6735 - 12 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.42 |  | Spring Lock Washer IS 6735 - 16 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.43 |  | Spring Lock Washer IS 6735 - 20 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.44 |  | Spring Lock Washer IS 6735 - 8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.2.2.45 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M8 x 20, CL 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.3 |  | Sink Roll Assembly | Subtask |  | 70d | 70d |  |  | IP | YES | [5 empty] | 70d | 70d | 74d6h |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM |  | 18-Jun-26 08:25 AM | 18-Mar-26 01:01 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
42.3.1 |  | Release of PO | step |  |  |  |  | 42.3.2
42.3.1.1 |  | Sink Roll | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:01 PM | 18-Mar-26 02:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.2 |  | Stand | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:01 PM | 18-Mar-26 02:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.3 |  | Stand | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:01 PM | 18-Mar-26 02:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.4 |  | Coupling Guard | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.5 |  | Full Gear Coupling, Model - AFG-103, Make - Alliance / Eqi., Power- 5.5 KW, O/P RPMv - 57.32, Torque - 917Nm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:01 PM | 18-Mar-26 02:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.6 |  | Spacer | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:01 PM | 18-Mar-26 02:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.7 |  | Spacer | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:01 PM | 18-Mar-26 02:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.8 |  | Solid shaft gearmotor, Solid shaft, IEC flange MTG for 7.5 kW I/P Motor, Ratio-20.5, Make-Bonfigoli, Model No-AS 60 P 20.5 132 B5 B3 BE 132MA 4 240/415-50 IP55 CLF B5 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.9 |  | Bearing Unit-Plummer Block , Make-SKF/EQ, Fixed End, Shaft Dia-80 mm, Housing-SNL 518-615, BRG No. 23218 CCL/W33, Adapter Sleeve-H 2318, Locating ring-2 x FRB 6.25/160,Seals- 2 x TSN 518 C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:01 PM | 18-Mar-26 02:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.10 |  | Bearing Unit-Plummer Block , Make-SKF/EQ, Flating End, Shaft Dia-80 mm, Housing-SNL 518-615, BRG No. 23218 CCL/W33, Adapter Sleeve-H 2318, Seals-2 x TSN 518 C | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:01 PM | 18-Mar-26 02:01 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.11 |  | Parallel Key, Type-A-B,IS:2048,Size:W18 x H11 x L80 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.12 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M20 x 100, CL- 8.8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:02 PM | 18-Mar-26 02:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.13 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M20 x 90, CL- 8.8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:02 PM | 18-Mar-26 02:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.14 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 30, CL 8.8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:02 PM | 18-Mar-26 02:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.15 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 70, CL 8.8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:02 PM | 18-Mar-26 02:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.16 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 90, CL 8.8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:02 PM | 18-Mar-26 02:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.17 |  | Hexagon Nut Style 1 IS 1364-Part3 - M10-D-N, CL-8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:02 PM | 18-Mar-26 02:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.18 |  | Hexagon Nut Style 1 IS 1364-Part3 - M16-D-N, CL-8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:02 PM | 18-Mar-26 02:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.19 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N, CL-8 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:02 PM | 18-Mar-26 02:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.20 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M20-N | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:02 PM | 18-Mar-26 02:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.21 |  | Spring Lock Washer IS 6735 - 10 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:02 PM | 18-Mar-26 02:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.1.22 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:02 PM | 18-Mar-26 02:02 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2 |  | Ready for Assy | step |  |  |  | 42.3.1
42.3.2.1 |  | Sink Roll | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.2 |  | Stand | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.3 |  | Stand | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.4 |  | Coupling Guard | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.5 |  | Full Gear Coupling, Model - AFG-103, Make - Alliance / Eqi., Power- 5.5 KW, O/P RPMv - 57.32, Torque - 917Nm | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.6 |  | Spacer | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.7 |  | Spacer | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.8 |  | Solid shaft gearmotor, Solid shaft, IEC flange MTG for 7.5 kW I/P Motor, Ratio-20.5, Make-Bonfigoli, Model No-AS 60 P 20.5 132 B5 B3 BE 132MA 4 240/415-50 IP55 CLF B5 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.9 |  | Bearing Unit-Plummer Block , Make-SKF/EQ, Fixed End, Shaft Dia-80 mm, Housing-SNL 518-615, BRG No. 23218 CCL/W33, Adapter Sleeve-H 2318, Locating ring-2 x FRB 6.25/160,Seals- 2 x TSN 518 C | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.10 |  | Bearing Unit-Plummer Block , Make-SKF/EQ, Flating End, Shaft Dia-80 mm, Housing-SNL 518-615, BRG No. 23218 CCL/W33, Adapter Sleeve-H 2318, Seals-2 x TSN 518 C | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.11 |  | Parallel Key, Type-A-B,IS:2048,Size:W18 x H11 x L80 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.12 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M20 x 100, CL- 8.8 | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.13 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M20 x 90, CL- 8.8 | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.14 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 30, CL 8.8 | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.15 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 70, CL 8.8 | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.16 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 90, CL 8.8 | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.17 |  | Hexagon Nut Style 1 IS 1364-Part3 - M10-D-N, CL-8 | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.18 |  | Hexagon Nut Style 1 IS 1364-Part3 - M16-D-N, CL-8 | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.19 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N, CL-8 | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.20 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M20-N | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.21 |  | Spring Lock Washer IS 6735 - 10 | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.3.2.22 |  | Spring Lock Washer IS 6735 - 20 | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
42.4 |  | Electrode Assembly | Subtask |  | 70d | 70d |  |  | IP | YES | [5 empty] | 70d | 70d | 74d6h |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM |  | 18-Jun-26 08:25 AM | 18-Mar-26 01:02 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
42.4.1 |  | Release of PO | step |  |  |  |  | 42.4.2
42.4.1.1 |  | Electrode | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:03 PM | 18-Mar-26 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.2 |  | Electrode | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:03 PM | 18-Mar-26 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.3 |  | Electrode | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:03 PM | 18-Mar-26 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.4 |  | Electrode | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:03 PM | 18-Mar-26 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.5 |  | Support | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.6 |  | Beam | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.7 |  | Frame | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.8 |  | Support | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.9 |  | Shaft | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.10 |  | Cradle Frame | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.11 |  | Bracket | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.12 |  | Cradle Frame | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.13 |  | Support | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.14 |  | Support | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.15 |  | Stopper | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.16 |  | Plate | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.17 |  | Insulation Plate | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.18 |  | Insulation Plate | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.19 |  | Bracket | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.20 |  | Shaft | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.21 |  | Bracket | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.22 |  | Taper Block | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.23 |  | Taper Block | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.1.24 |  | Adjusting Screw | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.25 |  | Collar | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.26 |  | Cylinder Mounting | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.27 |  | Cylinder Guide | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.28 |  | Insulation Plate | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.29 |  | Bracket | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.30 |  | Insulation Plate | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.31 |  | Arm | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.32 |  | Housing | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.33 |  | Bush | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.34 |  | Shaft | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.35 |  | Shaft | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.36 |  | Bracket | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.37 |  | Guide Plate Support | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.38 |  | Guide Plate | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.39 |  | Stop Block | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.40 |  | Insulation Bush | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.41 |  | Insulation Washer | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.42 |  | Collar | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.43 |  | Collar | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.44 |  | Insulation Bush | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.45 |  | Packing Plate | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.46 |  | Insulation Washer | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.47 |  | Inverted Machine Jactuator, 5T, Clevis End, Ratio. 6:1, B.O. - Hitork / Equi. | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.48 |  | Hydraulic Cylinder, Bore Dia. 100 x Rod 56 x Stk 300, Intermediate Trunnion, B.O.- Parkar / Equi. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:03 PM | 18-Mar-26 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.49 |  | Pin | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.50 |  | Washer | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.51 |  | Hand Wheel | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.52 |  | Flange | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.53 |  | Bracket | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.54 |  | Insulation Bush | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.55 |  | Insulation Washer | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.56 |  | Pin | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.57 |  | Washer | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.58 |  | PIN | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.59 |  | Parallel Key | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.60 |  | Parallel Key | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.61 |  | Insulation Bush | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.62 |  | Packing Plate | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.63 |  | Insulation Separator | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.64 |  | Clamp Plate | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.65 |  | Termination Block | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.66 |  | Suitable for 5000 Ampere | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.67 |  | Suitable for Bus bar | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.68 |  | Pillow Block, #UCP 320, B. O.- SKF / Equi | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:03 PM | 18-Mar-26 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.69 |  | Pillow Block, #UCP 315, B.O.- SKF/EQUI | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM |  |  | 18-Mar-26 01:03 PM | 18-Mar-26 02:03 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.70 |  | 3/4 " x 1/2 " BSPP Straight Adaptor Male - Male | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.71 |  | 1/2" Hyd. Hose SAF 100 R2 Swivel Nut Female 1000 Lg | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.72 |  | 1/2" Hyd. Hose SAF 100 R2 Swivel Nut Female 800 Lg | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.73 |  | Parallel Key, Type-A-B,IS:2048,Size:W6 x H6 x L25 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.74 |  | Socket Set Screw - Cone Point IS 6094 - M12 x 25 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.75 |  | Socket Set Screw - Cone Point IS 6094 - M16 x 25 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.76 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N, CL-8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.77 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M30 x 150, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.78 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M20 x 160, CL- 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.79 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.80 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N, CL-8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.81 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M20-N | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.82 |  | Socket Head Cap Screw IS 2269 - M16 x 80 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.83 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M16-N | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.84 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.85 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M16 x 65, CL- 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.86 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 100, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.87 |  | Hexagon Nut Style 1 IS 1364-Part3 - M16-D-N, CL-8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.88 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M20 x 65, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.89 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M16 x 120, CL- 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.90 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M30 x 280, CL- 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.91 |  | Spring Lock Washer IS 6735 - 8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.92 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M24 x 110, CL- 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.93 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.94 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M24 x 60, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.95 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 45 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.96 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.97 |  | Hexagon Nut Style 1 IS 1364-Part3 - M10-D-N | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.98 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 50, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.99 |  | Washer DIN 434 - 14 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.100 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M16 x 70, CL- 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.101 |  | Washer DIN 434 - 18 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.102 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 50, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.103 |  | Spring Lock Washer IS 6735 - 10 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.104 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 35, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.105 |  | Hexagon Nut Style 1 IS 1364-Part3 - M10-D-N, CL-8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.106 |  | Split pin ISO 1234 - 5 x 50 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.107 |  | Spring Lock Washer IS 6735 - 10 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.108 |  | Socket Head Cap Screw IS 2269 - M12 x 50 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.109 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.110 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.111 |  | Socket Head Cap Screw IS 2269 - M10 x 60 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.112 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N, CL-8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.113 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.114 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M12 x 60 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.115 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 25 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.116 |  | Washer DIN 434 - 11 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.1.117 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M20 x 70, CL 8.8 | date |  | 10d |  |  |  | NS | YES | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2 |  | Ready for Assy | step |  |  |  | 42.4.1
42.4.2.1 |  | Electrode | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.2 |  | Electrode | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.3 |  | Electrode | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.4 |  | Electrode | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.5 |  | Support | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.6 |  | Beam | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.7 |  | Frame | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.8 |  | Support | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.9 |  | Shaft | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.10 |  | Cradle Frame | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.11 |  | Bracket | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.12 |  | Cradle Frame | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.13 |  | Support | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.14 |  | Support | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.15 |  | Stopper | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.16 |  | Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.17 |  | Insulation Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.18 |  | Insulation Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.19 |  | Bracket | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.20 |  | Shaft | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.21 |  | Bracket | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.22 |  | Taper Block | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.23 |  | Taper Block | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.4.2.24 |  | Adjusting Screw | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.25 |  | Collar | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.26 |  | Cylinder Mounting | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.27 |  | Cylinder Guide | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.28 |  | Insulation Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.29 |  | Bracket | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.30 |  | Insulation Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.31 |  | Arm | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.32 |  | Housing | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.33 |  | Bush | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.34 |  | Shaft | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.35 |  | Shaft | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.36 |  | Bracket | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.37 |  | Guide Plate Support | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.38 |  | Guide Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.39 |  | Stop Block | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.40 |  | Insulation Bush | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.41 |  | Insulation Washer | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.42 |  | Collar | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.43 |  | Collar | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.44 |  | Insulation Bush | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.45 |  | Packing Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.46 |  | Insulation Washer | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.47 |  | Inverted Machine Jactuator, 5T, Clevis End, Ratio. 6:1, B.O. - Hitork / Equi. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.48 |  | Hydraulic Cylinder, Bore Dia. 100 x Rod 56 x Stk 300, Intermediate Trunnion, B.O.- Parkar / Equi. | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.49 |  | Pin | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.50 |  | Washer | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.51 |  | Hand Wheel | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.52 |  | Flange | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.53 |  | Bracket | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.54 |  | Insulation Bush | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.55 |  | Insulation Washer | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.56 |  | Pin | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.57 |  | Washer | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.58 |  | PIN | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.59 |  | Parallel Key | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.60 |  | Parallel Key | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.61 |  | Insulation Bush | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.62 |  | Packing Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.63 |  | Insulation Separator | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.64 |  | Clamp Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.65 |  | Termination Block | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.66 |  | Suitable for 5000 Ampere | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.67 |  | Suitable for Bus bar | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.68 |  | Pillow Block, #UCP 320, B. O.- SKF / Equi | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.69 |  | Pillow Block, #UCP 315, B.O.- SKF/EQUI | date |  | 60d |  |  |  | NS | YES | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 07-Jun-26 11:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.70 |  | 3/4 " x 1/2 " BSPP Straight Adaptor Male - Male | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.71 |  | 1/2" Hyd. Hose SAF 100 R2 Swivel Nut Female 1000 Lg | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.72 |  | 1/2" Hyd. Hose SAF 100 R2 Swivel Nut Female 800 Lg | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.73 |  | Parallel Key, Type-A-B,IS:2048,Size:W6 x H6 x L25 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.74 |  | Socket Set Screw - Cone Point IS 6094 - M12 x 25 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.75 |  | Socket Set Screw - Cone Point IS 6094 - M16 x 25 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.76 |  | Hexagon Nut Style 1 IS 1364-Part3 - M30-D-N, CL-8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.77 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M30 x 150, CL 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.78 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M20 x 160, CL- 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.79 |  | Spring Lock Washer IS 6735 - 20 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.80 |  | Hexagon Nut Style 1 IS 1364-Part3 - M20-D-N, CL-8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.81 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M20-N | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.82 |  | Socket Head Cap Screw IS 2269 - M16 x 80 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.83 |  | Hexagon Thin Nut (chamfered) IS 1364-Part4 - M16-N | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.84 |  | Spring Lock Washer IS 6735 - 16 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.85 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M16 x 65, CL- 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.86 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 100, CL 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.87 |  | Hexagon Nut Style 1 IS 1364-Part3 - M16-D-N, CL-8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.88 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M20 x 65, CL 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.89 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M16 x 120, CL- 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.90 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M30 x 280, CL- 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.91 |  | Spring Lock Washer IS 6735 - 8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.92 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M24 x 110, CL- 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.93 |  | Spring Lock Washer IS 6735 - 24 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.94 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M24 x 60, CL 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.95 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 45 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.96 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.97 |  | Hexagon Nut Style 1 IS 1364-Part3 - M10-D-N | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.98 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 50, CL 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.99 |  | Washer DIN 434 - 14 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.100 |  | Hexagon Head Bolt (Grade A) IS 1364(Part1) - M16 x 70, CL- 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.101 |  | Washer DIN 434 - 18 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.102 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 50, CL 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.103 |  | Spring Lock Washer IS 6735 - 10 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.104 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 35, CL 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.105 |  | Hexagon Nut Style 1 IS 1364-Part3 - M10-D-N, CL-8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.106 |  | Split pin ISO 1234 - 5 x 50 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.107 |  | Spring Lock Washer IS 6735 - 10 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.108 |  | Socket Head Cap Screw IS 2269 - M12 x 50 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.109 |  | Spring Lock Washer IS 6735 - 12 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.110 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.111 |  | Socket Head Cap Screw IS 2269 - M10 x 60 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.112 |  | Hexagon Nut Style 1 IS 1364-Part3 - M12-D-N, CL-8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.113 |  | Spring Lock Washer IS 6735 - 12 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.114 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M12 x 60 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.115 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M10 x 25 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.116 |  | Washer DIN 434 - 11 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.4.2.117 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M20 x 70, CL 8.8 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5 |  | Water Piping Assembly | Subtask |  | 70d | 70d |  |  | NS | YES | [5 empty] | 70d | 70d |  |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
42.5.1 |  | Release of PO | step |  |  |  |  | 42.5.2
42.5.1.1 |  | SPRAY PIPE | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.2 |  | SPRAY PIPE | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.3 |  | SPRAY PIPE | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.4 |  | SPRAY PIPING | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.5 |  | SPRAY PIPE | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.6 |  | Support Plate | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.7 |  | Insulation Plate | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.8 |  | INSULATION WASHER | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.9 |  | SUPPORT BRACKET | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.10 |  | Insulation Plate | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.11 |  | INSULATION BUSH | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.12 |  | SUPPORT | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.13 |  | Insulation Plate | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.14 |  | SUPPORT | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.15 |  | SUPPORT | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.16 |  | SUPPORT | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.17 |  | SUPPORT | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.18 |  | SUPPORT | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.19 |  | HEADER | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.20 |  | HEADER | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.21 |  | PIPING | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.22 |  | PIPING | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.23 |  | HEADER | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.1.24 |  | HEADER | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.1.25 |  | PIPING | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.1.26 |  | PIPING | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.1.27 |  | HEADER | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.1.28 |  | PIPING | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.1.29 |  | Gasket 3 Thk For DN 50 Flange DIN | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.1.30 |  | Gasket 3 Thk For DN 65 Flange DIN | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.1.31 |  | U' Bolt for 50 NB Pipe, M12 with Nut & Spring Washer # B.O. AISI 304 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.1.32 |  | U' Bolt for 50 NB Pipe, M12 with Nut & Spring Washer # B.O. AISI 304 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.1.33 |  | U' Bolt for 65 NB Pipe, M12 with Nut & Spring Washer # B.O. AISI 304 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.1.34 |  | U' Bolt for 80 NB Pipe, M12 with Nut & Spring Washer # B.O. AISI 304 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.2 |  | Ready for Assy | step |  |  |  | 42.5.1
42.5.2.1 |  | SPRAY PIPE | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.2 |  | SPRAY PIPE | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.3 |  | SPRAY PIPE | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.4 |  | SPRAY PIPING | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.5 |  | SPRAY PIPE | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.6 |  | Support Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.7 |  | Insulation Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.8 |  | INSULATION WASHER | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.9 |  | SUPPORT BRACKET | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.10 |  | Insulation Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.11 |  | INSULATION BUSH | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.12 |  | SUPPORT | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.13 |  | Insulation Plate | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.14 |  | SUPPORT | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.15 |  | SUPPORT | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.16 |  | SUPPORT | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.17 |  | SUPPORT | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.18 |  | SUPPORT | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.19 |  | HEADER | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.20 |  | HEADER | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.21 |  | PIPING | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.22 |  | PIPING | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.23 |  | HEADER | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.5.2.24 |  | HEADER | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.2.25 |  | PIPING | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.2.26 |  | PIPING | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.2.27 |  | HEADER | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.2.28 |  | PIPING | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.2.29 |  | Gasket 3 Thk For DN 50 Flange DIN | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.2.30 |  | Gasket 3 Thk For DN 65 Flange DIN | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.2.31 |  | U' Bolt for 50 NB Pipe, M12 with Nut & Spring Washer # B.O. AISI 304 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.2.32 |  | U' Bolt for 50 NB Pipe, M12 with Nut & Spring Washer # B.O. AISI 304 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.2.33 |  | U' Bolt for 65 NB Pipe, M12 with Nut & Spring Washer # B.O. AISI 304 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.5.2.34 |  | U' Bolt for 80 NB Pipe, M12 with Nut & Spring Washer # B.O. AISI 304 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
42.6 |  | GA of ECL Process Tank | Subtask |  | 70d | 70d |  |  | NS | YES | [5 empty] | 70d | 70d |  |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
42.6.1 |  | Release of PO | step |  |  |  |  | 42.6.2
42.6.1.1 |  | ECL Process Tank Assembly | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.6.1.2 |  | Deflector Roll Assembly | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.6.1.3 |  | Sink Roll Assembly | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.6.1.4 |  | Electrode Assembly | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.6.1.5 |  | Water Piping Assembly | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.6.1.6 |  | Chemical Anchor Bolt M16 x 190 mm with capsule,nut & washer,Grade- 8.8, Make- Hilti / Equi. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.6.1.7 |  | Chemical Anchor Bolt M20 x 260 mm with capsule,nut & washer,Grade- 8.8, Make- Hilti / Equi. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.6.1.8 |  | Chemical Anchor Bolt M24 x 300 mm with capsule,nut & washer,Grade- 8.8, Make- Hilti / Equi. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.6.2 |  | Ready for Assy | step |  |  |  | 42.6.1
42.6.2.1 |  | ECL Process Tank Assembly | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.6.2.2 |  | Deflector Roll Assembly | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.6.2.3 |  | Sink Roll Assembly | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.6.2.4 |  | Electrode Assembly | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.6.2.5 |  | Water Piping Assembly | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.6.2.6 |  | Chemical Anchor Bolt M16 x 190 mm with capsule,nut & washer,Grade- 8.8, Make- Hilti / Equi. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.6.2.7 |  | Chemical Anchor Bolt M20 x 260 mm with capsule,nut & washer,Grade- 8.8, Make- Hilti / Equi. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
42.6.2.8 |  | Chemical Anchor Bolt M24 x 300 mm with capsule,nut & washer,Grade- 8.8, Make- Hilti / Equi. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
43 | 42 | Category 1 - TURN ROLL ASSY. - Ordering & Manufacturing | TASK |  | 60d | 60d | 32 | 62 | IP | YES | 006-028 |  |  |  |  | 1d | 1d | 4d13h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 24-Mar-26 02:25 AM | 18-Mar-26 04:45 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
43.1 |  | TURN UP ROLL ASSY. @CAG | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 1d |  | 4d13h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 24-Mar-26 02:25 AM | 18-Mar-26 04:45 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
43.1.1 |  | Release of PO | step |  |  |  |  | 43.1.2
43.1.1.1 |  | ROD END CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.2 |  | BASE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.3 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.4 |  | CYL. ROD END CLEVIS PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.5 |  | CYL. BLIND END CLEVIS PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.6 |  | ARM PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.7 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.8 |  | SPACER- 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.9 |  | SPACER- 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.10 |  | LOCKING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.11 |  | RETAINER L.H | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.12 |  | END COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.13 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.14 |  | LOCK PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.15 |  | GEAR BOX SPROCKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.16 |  | SNUBBER ROLL SPROCKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.17 |  | RETAINER R.H | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.18 |  | GEAR BOX LOCK PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.19 |  | BUSH- 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.20 |  | GEARED MOTOR- 1.5KW,1500RPM,4 POLE, RATIO-25.51:1, MODEL-M0622, MAKE- PBL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.21 |  | TURNUP ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.22 |  | SNUBBER ROLL@TURNUP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.23 |  | ARM BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.24 |  | TOP MOTOR FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.25 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.26 |  | L.H. ARM CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.27 |  | R.H. ARM CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.28 |  | BRG. BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.29 |  | UPPER CHAIN COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.30 |  | LOWER CHAIN COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.31 |  | CYL. CLEVIS FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.32 |  | PNEU. CYL. BORE DIA 125, ROD DIA 32, STROKE - 100 MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.33 |  | DUPLEX CHAIN (12B2), ROLLER DIA 12.07mm, PITCH 0.75'' (1150mm LONG), (60 NOS. LINKS), MAKE- RENOLD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.34 |  | RETAINER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.35 |  | RETAINER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.36 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.37 |  | END COVER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.38 |  | END COVER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.39 |  | BEARING HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.40 |  | 110X130X10_OIL SEAL_AIA1100831 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.41 |  | BEARING,SPHERICAL,22208 E(SPHERICAL ROLLER BRG D 40IDx80ODx23THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.42 |  | 22220_E-SPHERICAL ROLLER BEARING- ID100XOD180X46 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.43 |  | OIL SEAL-50ID x 70OD x 8THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.44 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.45 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.54 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.57 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.58 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.59 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.60 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.61 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.62 |  | Plain Washer (Type A) IS 2016 - 6.6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.63 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.64 |  | Socket Head Cap Screw IS 2269 - M16 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.65 |  | Cylindrical Pin IS 2393 - 10 x 30-DC | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.66 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.67 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.68 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.69 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.70 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.71 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.72 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.73 |  | Spring Lock Washer IS 6735 - 6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.74 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.75 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.76 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.1.77 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2 |  | Ready for Assy | step |  |  |  | 43.1.1
43.1.2.1 |  | ROD END CLEVIS | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:47 PM | 18-Mar-26 05:47 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.2 |  | BASE PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.3 |  | KEEPER PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.4 |  | CYL. ROD END CLEVIS PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.5 |  | CYL. BLIND END CLEVIS PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.6 |  | ARM PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.7 |  | BUSH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:48 PM | 18-Mar-26 05:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.8 |  | SPACER- 1 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.9 |  | SPACER- 2 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.10 |  | LOCKING PIN | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.11 |  | RETAINER L.H | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.12 |  | END COVER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.13 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.14 |  | LOCK PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.15 |  | GEAR BOX SPROCKET | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.16 |  | SNUBBER ROLL SPROCKET | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.17 |  | RETAINER R.H | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.18 |  | GEAR BOX LOCK PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.19 |  | BUSH- 2 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:48 PM | 18-Mar-26 05:48 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.20 |  | GEARED MOTOR- 1.5KW,1500RPM,4 POLE, RATIO-25.51:1, MODEL-M0622, MAKE- PBL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.21 |  | TURNUP ROLL | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.22 |  | SNUBBER ROLL@TURNUP | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.23 |  | ARM BASE FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.24 |  | TOP MOTOR FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.25 |  | BASE FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.26 |  | L.H. ARM CLEVIS | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.27 |  | R.H. ARM CLEVIS | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.28 |  | BRG. BLOCK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.29 |  | UPPER CHAIN COVER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.30 |  | LOWER CHAIN COVER | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.31 |  | CYL. CLEVIS FRAME | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.32 |  | PNEU. CYL. BORE DIA 125, ROD DIA 32, STROKE - 100 MM | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.33 |  | DUPLEX CHAIN (12B2), ROLLER DIA 12.07mm, PITCH 0.75'' (1150mm LONG), (60 NOS. LINKS), MAKE- RENOLD | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:46 PM | 18-Mar-26 05:46 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.34 |  | RETAINER-RH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.35 |  | RETAINER-LH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.36 |  | END PLATE | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.37 |  | END COVER-RH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.38 |  | END COVER-LH | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.39 |  | BEARING HOUSING | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.40 |  | 110X130X10_OIL SEAL_AIA1100831 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.41 |  | BEARING,SPHERICAL,22208 E(SPHERICAL ROLLER BRG D 40IDx80ODx23THK. mm) | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.42 |  | 22220_E-SPHERICAL ROLLER BEARING- ID100XOD180X46 THK. | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.43 |  | OIL SEAL-50ID x 70OD x 8THK | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.44 |  | GREASE NIPPLE 1/8" BSP | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.45 |  | SHEAR BIOCK- 10x10x50mm | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 60 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 16 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.54 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.57 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.58 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.59 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.60 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.61 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.62 |  | Plain Washer (Type A) IS 2016 - 6.6 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.63 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.64 |  | Socket Head Cap Screw IS 2269 - M16 x 100 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.65 |  | Cylindrical Pin IS 2393 - 10 x 30-DC | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.66 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.67 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.68 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.69 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.70 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.71 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.72 |  | Spring Lock Washer IS 6735 - 12 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.73 |  | Spring Lock Washer IS 6735 - 6 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.74 |  | Spring Lock Washer IS 6735 - 24 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.75 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 50 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.76 |  | Spring Lock Washer IS 6735 - 20 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.1.2.77 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 65 | date |  | 50d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2 |  | TURN DOWN ROLL ASSY. @CAG | Subtask |  | 60d | 60d |  |  | IP | YES | [5 empty] | 1d |  | 4d13h |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM |  | 24-Mar-26 02:25 AM | 18-Mar-26 04:45 PM | [8 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
43.2.1 |  | Release of PO | step |  |  |  |  | 43.2.2
43.2.1.1 |  | ROD END CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.2 |  | BASE PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.3 |  | KEEPER PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.4 |  | CYL. ROD END CLEVIS PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.5 |  | CYL. BLIND END CLEVIS PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.6 |  | ARM PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.7 |  | BUSH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.8 |  | SPACER- 1 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.9 |  | SPACER- 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.10 |  | LOCKING PIN | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.11 |  | RETAINER L.H | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.12 |  | END COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.13 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.14 |  | LOCK PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.15 |  | GEAR BOX SPROCKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.16 |  | SNUBBER ROLL SPROCKET | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.17 |  | RETAINER R.H | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.18 |  | GEAR BOX LOCK PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.19 |  | BUSH- 2 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.20 |  | GEARED MOTOR- 1.5KW,1500RPM,4 POLE, RATIO-25.51:1, MODEL-M0622, MAKE- PBL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.21 |  | TURN DOWN ROLL | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.22 |  | SNUBBER ROLL@TURNUP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.23 |  | CYL. CLEVIS FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.24 |  | ARM BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.25 |  | TOP MOTOR FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.26 |  | BASE FRAME | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.27 |  | L.H. ARM CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.28 |  | R.H. ARM CLEVIS | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.29 |  | BRG. BLOCK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.30 |  | UPPER CHAIN COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.31 |  | LOWER CHAIN COVER | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.32 |  | PNEU. CYL. BORE DIA 125, ROD DIA 32, STROKE - 100 MM | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.33 |  | DUPLEX CHAIN (12B2), ROLLER DIA 12.07mm, PITCH 0.75'' (1150mm LONG), (60 NOS. LINKS), MAKE- RENOLD | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.34 |  | RETAINER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.35 |  | RETAINER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.36 |  | END PLATE | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.37 |  | END COVER-RH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.38 |  | END COVER-LH | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.39 |  | BEARING HOUSING | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.40 |  | 110X130X10_OIL SEAL_AIA1100831 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.41 |  | BEARING,SPHERICAL,22208 E(SPHERICAL ROLLER BRG D 40IDx80ODx23THK. mm) | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.42 |  | 22220_E-SPHERICAL ROLLER BEARING- ID100XOD180X46 THK. | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.43 |  | OIL SEAL-50ID x 70OD x 8THK | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.44 |  | GREASE NIPPLE 1/8" BSP | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.45 |  | SHEAR BIOCK- 10x10x50mm | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 60 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 16 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.54 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.57 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.58 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.59 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.60 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.61 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.62 |  | Plain Washer (Type A) IS 2016 - 6.6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.63 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.64 |  | Socket Head Cap Screw IS 2269 - M16 x 100 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.65 |  | Cylindrical Pin IS 2393 - 10 x 30-DC | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.66 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.67 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.68 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.69 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.70 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.71 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.72 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.73 |  | Spring Lock Washer IS 6735 - 6 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.74 |  | Spring Lock Washer IS 6735 - 24 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.75 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 50 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.76 |  | Spring Lock Washer IS 6735 - 20 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.1.77 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 65 | date |  | 10d |  |  |  | CO | YES | [5 empty] | 0d |  | 1h |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2 |  | Ready for Assy | step |  |  |  | 43.2.1
43.2.2.1 |  | ROD END CLEVIS | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.2 |  | BASE PLATE | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.3 |  | KEEPER PLATE | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.4 |  | CYL. ROD END CLEVIS PIN | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.5 |  | CYL. BLIND END CLEVIS PIN | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.6 |  | ARM PIN | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.7 |  | BUSH | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.8 |  | SPACER- 1 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.9 |  | SPACER- 2 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.10 |  | LOCKING PIN | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.11 |  | RETAINER L.H | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.12 |  | END COVER | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.13 |  | END PLATE | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.14 |  | LOCK PLATE | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.15 |  | GEAR BOX SPROCKET | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.16 |  | SNUBBER ROLL SPROCKET | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.17 |  | RETAINER R.H | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.18 |  | GEAR BOX LOCK PLATE | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.19 |  | BUSH- 2 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.20 |  | GEARED MOTOR- 1.5KW,1500RPM,4 POLE, RATIO-25.51:1, MODEL-M0622, MAKE- PBL | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.21 |  | TURN DOWN ROLL | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.22 |  | SNUBBER ROLL@TURNUP | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.23 |  | CYL. CLEVIS FRAME | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.24 |  | ARM BASE FRAME | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.25 |  | TOP MOTOR FRAME | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.26 |  | BASE FRAME | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.27 |  | L.H. ARM CLEVIS | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.28 |  | R.H. ARM CLEVIS | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.29 |  | BRG. BLOCK | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.30 |  | UPPER CHAIN COVER | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.31 |  | LOWER CHAIN COVER | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.32 |  | PNEU. CYL. BORE DIA 125, ROD DIA 32, STROKE - 100 MM | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.33 |  | DUPLEX CHAIN (12B2), ROLLER DIA 12.07mm, PITCH 0.75'' (1150mm LONG), (60 NOS. LINKS), MAKE- RENOLD | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.34 |  | RETAINER-RH | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.35 |  | RETAINER-LH | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.36 |  | END PLATE | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.37 |  | END COVER-RH | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.38 |  | END COVER-LH | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.39 |  | BEARING HOUSING | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.40 |  | 110X130X10_OIL SEAL_AIA1100831 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.41 |  | BEARING,SPHERICAL,22208 E(SPHERICAL ROLLER BRG D 40IDx80ODx23THK. mm) | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.42 |  | 22220_E-SPHERICAL ROLLER BEARING- ID100XOD180X46 THK. | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.43 |  | OIL SEAL-50ID x 70OD x 8THK | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.44 |  | GREASE NIPPLE 1/8" BSP | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.45 |  | SHEAR BIOCK- 10x10x50mm | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.46 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M10 x 30 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.47 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.48 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.49 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 45 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.50 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 55 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.51 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 60 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.52 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 80 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.53 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M6 x 16 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.54 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 30 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.55 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.57 |  | Plain Washer (Type A) IS 2016 - 11 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.58 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.59 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.60 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.61 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.62 |  | Plain Washer (Type A) IS 2016 - 6.6 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.63 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.64 |  | Socket Head Cap Screw IS 2269 - M16 x 100 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.65 |  | Cylindrical Pin IS 2393 - 10 x 30-DC | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.66 |  | Spring Lock Washer IS 3063 - 10-A | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.67 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.68 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.69 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.70 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.71 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.72 |  | Spring Lock Washer IS 6735 - 12 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.73 |  | Spring Lock Washer IS 6735 - 6 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.74 |  | Spring Lock Washer IS 6735 - 24 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.75 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 50 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.76 |  | Spring Lock Washer IS 6735 - 20 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
43.2.2.77 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 65 | date |  | 50d |  |  |  | CO | NO | [5 empty] | 0d |  | 1h |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM |  |  | 18-Mar-26 04:51 PM | 18-Mar-26 05:51 PM | [7 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
44 | 85 | Category 2 - LOGO MARKER ASSY - Engg | TASK |  | 5d | 5d |  | 69 | NS | YES | 004-000 |  |  |  |  | 5d | 5d |  |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM |  |  |  |  | START ASAP |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
44.1 |  | LOGO MARKER ASSY | Subtask |  | 5d | 5d |  |  | NS | NO | [5 empty] | 5d | 5d |  |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
44.1.1 |  | Completion | step
44.1.1.1 |  | LOGO MARKER ASSY | date |  | 5d |  |  |  | NS | NO | [5 empty] | 5d |  |  |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
45 | 88 | Category 2 - DRYER - Engg | TASK |  | 5d | 5d |  | 38 | NS | YES | 005-001 |  |  |  |  | 5d | 5d |  |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM |  |  |  |  | START ASAP |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
45.1 |  | DRYER | Subtask |  | 5d | 5d |  |  | NS | NO | [5 empty] | 5d | 5d |  |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
45.1.1 |  | Completion | step
45.1.1.1 |  | HOT AIR DRYER ASSY.#1 @ CLEANING SECTION | date |  | 4d |  |  |  | NS | NO | [5 empty] | 4d |  |  |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
45.1.1.2 |  | COLD AIR DRYER @ CAG | date |  | 5d |  |  |  | NS | NO | [5 empty] | 5d |  |  |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
45.1.1.3 |  | LOGO DRYER @ LOGO MARKER | date |  | 5d |  |  |  | NS | NO | [5 empty] | 5d |  |  |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
46 | 135 | Category 1 - SENSOR - Engg | TASK |  | 5d | 5d |  | 39 | NS | YES | 006-002 |  |  |  |  | 5d | 5d |  |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM |  |  |  |  | START ASAP |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
46.1 |  | SENSOR | Subtask |  | 5d | 5d |  |  | NS | NO | [5 empty] | 5d | 5d |  |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
46.1.1 |  | Completion | step
46.1.1.1 |  | EPC SENSOR ASSY.@ RECOILER | date |  | 4d |  |  |  | NS | NO | [5 empty] | 4d |  |  |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
46.1.1.2 |  | CPC SENSOR ASSY.@ STEERING ASSY. | date |  | 5d |  |  |  | NS | NO | [5 empty] | 5d |  |  |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
46.1.1.3 |  | BASE FRAME CPC SENSOR ASSY. | date |  | 4d |  |  |  | NS | NO | [5 empty] | 4d |  |  |  |  | 12-Aug-25 01:00 AM | 15-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
47 | 138 | Category 1 - TANK - Engg | TASK |  | 10d |  |  | 40 | NS | YES | 006-007 |  |  |  |  | 10d |  |  |  |  | 30-Sep-25 06:00 AM | 10-Oct-25 07:00 PM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM |  |  |  |  | START ASAP |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
48 | 144 | Category 1 - ECL Process Tank Assembly- Engg | TASK |  | 10d |  |  | 42 | NS | YES | 006-008 |  |  |  |  | 10d |  |  |  |  | 30-Sep-25 06:00 AM | 10-Oct-25 07:00 PM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM |  |  |  |  | START ASAP |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
49 | 147 | Category 1 - DEGREASING TANK ASSY- Engg | TASK |  | 10d |  |  | 71 | NS | YES | 006-009 |  |  |  |  | 10d |  |  |  |  | 30-Sep-25 06:00 AM | 10-Oct-25 07:00 PM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM |  |  |  |  | START ASAP |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
50 | 132 | Category 1 - HOLE DETECTOR - Engg | TASK |  | 5d | 5d |  | 70 | NS | YES | 006-010 |  |  |  |  | 5d | 5d |  |  |  | 05-Oct-25 01:00 PM | 10-Oct-25 07:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM |  |  |  |  | START ASAP |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
50.1 |  | HOLE DETECTOR | Subtask |  | 5d | 5d |  |  | NS | NO | [5 empty] | 5d | 5d |  |  |  | 05-Oct-25 01:00 PM | 10-Oct-25 07:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
50.1.1 |  | Completion | step
50.1.1.1 |  | WELD HOLE DETECTOR ASSY.#01 (BEFORE BRIDLE ROLL#3) | date |  | 4d |  |  |  | NS | NO | [5 empty] | 4d |  |  |  |  | 05-Oct-25 01:00 PM | 09-Oct-25 07:00 PM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
50.1.1.2 |  | WELD HOLE DETECTOR ASSY.#02 (AFTER CAG) | date |  | 5d |  |  |  | NS | NO | [5 empty] | 5d |  |  |  |  | 05-Oct-25 01:00 PM | 10-Oct-25 07:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
50.1.1.3 |  | WELD HOLE DETECTOR ASSY.#03 (AFTER EXIT ACC ASSY.) | date |  | 4d |  |  |  | NS | NO | [5 empty] | 4d |  |  |  |  | 05-Oct-25 01:00 PM | 09-Oct-25 07:00 PM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
51 | 65 | Category 1 - MANUAL TINSEL SCRAPPER - Engg | TASK |  | 3d | 3d |  | 68 | NS | YES | 006-016 |  |  |  |  | 3d | 3d |  |  |  | 18-Oct-25 12:00 PM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 26-Mar-26 02:25 AM |  |  |  |  | START ASAP |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
51.1 |  | MANUAL TINSEL SCRAPPER | Subtask |  | 3d | 3d |  |  | NS | NO | [5 empty] | 3d | 3d |  |  |  | 18-Oct-25 12:00 PM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 26-Mar-26 02:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
51.1.1 |  | Completion | step
51.1.1.1 |  | MANUAL TINSEL SCRAPPER | date |  | 3d |  |  |  | NS | NO | [5 empty] | 3d |  |  |  |  | 18-Oct-25 12:00 PM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 26-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
52 | 141 | Category 1 - PNEUMATIC & HYDRAULIC FITTINGS - Engg | TASK |  | 2d |  |  | 66 | NS | YES | 006-017 |  |  |  |  | 2d |  |  |  |  | 20-Oct-25 03:00 AM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 25-Mar-26 02:25 AM |  |  |  |  | START ASAP |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
53 | 80 | Category 1 - CHILL ROLL UNIT - Engg | TASK |  | 3d | 3d |  | 37 | NS | YES | 006-019 |  |  |  |  | 3d | 3d |  |  |  | 18-Oct-25 12:00 PM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 26-Mar-26 02:25 AM |  |  |  |  | START ASAP |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
53.1 |  | CHILL ROLL UNIT | Subtask |  | 3d | 3d |  |  | NS | NO | [5 empty] | 3d | 3d |  |  |  | 18-Oct-25 12:00 PM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 26-Mar-26 02:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
53.1.1 |  | Completion | step
53.1.1.1 |  | CHILL ROLL ASSY. #1 | date |  | 3d |  |  |  | NS | NO | [5 empty] | 3d |  |  |  |  | 18-Oct-25 12:00 PM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 26-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
53.1.1.2 |  | CHILL ROLL ASSY. #2 | date |  | 3d |  |  |  | NS | NO | [5 empty] | 3d |  |  |  |  | 18-Oct-25 12:00 PM | 22-Oct-25 03:00 AM | 23-Mar-26 02:25 AM | 26-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
54 | 40 | Category 1 - DEFLECTOR ROLL ASSY - Assembly | TASK |  | 10d |  | 8 | 97 | NS | YES | 006-030 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM |  |  |  |  | START ASAP |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
55 | 73 | Category 2 - BRIDLE ROLL ASSY. - Assembly | TASK |  | 10d |  | 11 | 104 | NS | YES | 007-029 |  |  |  |  | 10d |  |  |  |  | 25-Dec-25 02:00 PM | 05-Jan-26 06:00 PM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM |  |  |  |  | START ASAP |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
56 | 92 | Category 2 - COATER STRUCTURE - Ordering & Manufacturing | TASK |  | 100d | 100d | 30 | 90 | NS | YES | 010-005 |  |  |  |  | 100d | 100d |  |  |  | 17-Aug-25 08:00 AM | 04-Dec-25 05:00 PM | 23-Mar-26 02:25 AM | 10-Jul-26 05:25 AM |  |  |  |  | START ASAP |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
56.1 |  | COATER STRUCTURE | Subtask |  | 100d |  |  |  | NS | NO | [5 empty] | 100d |  |  |  |  | 17-Aug-25 08:00 AM | 04-Dec-25 05:00 PM | 23-Mar-26 02:25 AM | 10-Jul-26 05:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
57 | 102 | Category 5 - BOI - Engg | TASK |  | 10d |  |  | 72 | NS | YES | 011-020 |  |  |  |  | 10d |  |  |  |  | 12-Nov-25 08:00 PM | 24-Nov-25 04:00 AM | 23-Mar-26 02:25 AM | 02-Apr-26 03:25 PM |  |  |  |  | START ASAP |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
58 | 94 | Category 5 - SHEAR ASSY - Engg | TASK |  | 5d | 5d |  | 7 | NS | YES | 011-031 |  |  |  |  | 5d | 5d |  |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM |  |  |  |  | START ASAP |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
58.1 |  | SHEAR ASSY. | Subtask |  | 5d | 5d |  |  | NS | NO | [5 empty] | 5d | 5d |  |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
58.1.1 |  | Completion | step
58.1.1.1 |  | DOUBLE DECKER ENTRY SHEAR ASSY. | date |  | 5d |  |  |  | NS | NO | [5 empty] | 5d |  |  |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
58.1.1.2 |  | DELIVERY SHEAR ASSY. | date |  | 5d |  |  |  | NS | NO | [5 empty] | 5d |  |  |  |  | 12-Aug-25 01:00 AM | 16-Aug-25 09:00 PM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
59 | 99 | Category 3/4 - Engg | TASK |  | 5d | 5d |  | 9 | NS | YES | 014-012 |  |  |  |  | 5d | 5d |  |  |  | 01-Sep-25 07:00 AM | 06-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM |  |  |  |  | START ASAP |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
59.1 |  | COATING THK GAUGE ASSY. (SPACE PROVISION) | Subtask |  | 4d | 4d |  |  | NS | NO | [5 empty] | 4d | 4d |  |  |  | 01-Sep-25 07:00 AM | 05-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
59.1.1 |  | Completion | step
59.1.1.1 |  | COATING THK GAUGE ASSY. (SPACE PROVISION) | date |  | 4d |  |  |  | NS | NO | [5 empty] | 4d |  |  |  |  | 01-Sep-25 07:00 AM | 05-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
59.2 |  | CHEMICAL HANDLING SYSTEM | Subtask |  | 4d | 4d |  |  | NS | NO | [5 empty] | 4d | 4d |  |  |  | 01-Sep-25 07:00 AM | 05-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
59.2.1 |  | Completion | step
59.2.1.1 |  | CHEMICAL HANDLING SYSTEM | date |  | 4d |  |  |  | NS | NO | [5 empty] | 4d |  |  |  |  | 01-Sep-25 07:00 AM | 05-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
59.3 |  | STRIP INDUCTION HEATER ASSY. WITH DRYER | Subtask |  | 4d | 4d |  |  | NS | NO | [5 empty] | 4d | 4d |  |  |  | 01-Sep-25 07:00 AM | 05-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
59.3.1 |  | Completion | step
59.3.1.1 |  | STRIP INDUCTION HEATER ASSY. WITH DRYER | date |  | 4d |  |  |  | NS | NO | [5 empty] | 4d |  |  |  |  | 01-Sep-25 07:00 AM | 05-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
59.4 |  | EDGE WIPER ASSY. | Subtask |  | 4d | 4d |  |  | NS | NO | [5 empty] | 4d | 4d |  |  |  | 01-Sep-25 07:00 AM | 05-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
59.4.1 |  | Completion | step
59.4.1.1 |  | EDGE WIPER ASSY. | date |  | 4d |  |  |  | NS | NO | [5 empty] | 4d |  |  |  |  | 01-Sep-25 07:00 AM | 05-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
59.5 |  | WELDER | Subtask |  | 4d | 4d |  |  | NS | NO | [5 empty] | 4d | 4d |  |  |  | 01-Sep-25 07:00 AM | 05-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
59.5.1 |  | Completion | step
59.5.1.1 |  | SEAM WELDER ASSY. | date |  | 4d |  |  |  | NS | NO | [5 empty] | 4d |  |  |  |  | 01-Sep-25 07:00 AM | 05-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
59.6 |  | TENSION LEVELLER (TLL) | Subtask |  | 4d | 4d |  |  | NS | NO | [5 empty] | 4d | 4d |  |  |  | 01-Sep-25 07:00 AM | 05-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
59.6.1 |  | Completion | step
59.6.1.1 |  | TENSION LEVELLER (TLL) | date |  | 4d |  |  |  | NS | NO | [5 empty] | 4d |  |  |  |  | 01-Sep-25 07:00 AM | 05-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
59.7 |  | FUME EXHAUST SYSTEM FOR CLANING SECTION | Subtask |  | 4d | 4d |  |  | NS | NO | [5 empty] | 4d | 4d |  |  |  | 01-Sep-25 07:00 AM | 05-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
59.7.1 |  | Completion | step
59.7.1.1 |  | FUME EXHAUST SYSTEM FOR CLANING SECTION | date |  | 4d |  |  |  | NS | NO | [5 empty] | 4d |  |  |  |  | 01-Sep-25 07:00 AM | 05-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 27-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
59.8 |  | SEMI AUTOMATIC STRIP STRAPPING MACHINE | Subtask |  | 5d | 5d |  |  | NS | NO | [5 empty] | 5d | 5d |  |  |  | 01-Sep-25 07:00 AM | 06-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
59.8.1 |  | Completion | step
59.8.1.1 |  | SEMI AUTOMATIC STRIP STRAPPING MACHINE | date |  | 5d |  |  |  | NS | NO | [5 empty] | 5d |  |  |  |  | 01-Sep-25 07:00 AM | 06-Sep-25 07:00 AM | 23-Mar-26 02:25 AM | 28-Mar-26 02:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
60 | 79 | Category 2 - COATER - Assembly | TASK |  | 10d |  | 2 | 100 | NS | NO | 003-025 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 24-Mar-26 02:25 AM | 03-Apr-26 03:25 PM |  |  |  |  | CONSIDER EARLY START |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
61 | 20 | Category 1 - STEERING ROLL ASSY. - Assembly | TASK |  | 10d |  | 3 | 97 | NS | NO | 006-027 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 24-Mar-26 02:25 AM | 03-Apr-26 03:25 PM |  |  |  |  | CONSIDER EARLY START |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
62 | 43 | Category 1 - TURN ROLL ASSY. - Assembly | TASK |  | 10d |  | 43 | 97 | NS | NO | 006-028 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 24-Mar-26 02:25 AM | 03-Apr-26 03:25 PM |  |  |  |  | CONSIDER EARLY START |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
63 | 28 | Category 2 - ENTRY ACCUMULATOR ASSY. - Assembly | TASK |  | 10d |  | 6 | 105 | NS | NO | 008-026 |  |  |  |  | 10d |  |  |  |  | 25-Dec-25 02:00 PM | 05-Jan-26 06:00 PM | 24-Mar-26 02:25 AM | 03-Apr-26 03:25 PM |  |  |  |  | CONSIDER EARLY START |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
64 | 61 | Category 2 - UNCOILER ASSY #1 - Assembly | TASK |  | 10d |  | 12 | 96 | NS | NO | 001-023 |  |  |  |  | 10d |  |  |  |  | 27-Dec-25 02:00 PM | 07-Jan-26 06:00 PM | 25-Mar-26 01:00 AM | 04-Apr-26 02:00 PM |  |  |  |  | CONSIDER EARLY START |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
65 | 31 | Category 2 - EXIT ACCUMULATOR ASSY. - Assembly | TASK |  | 10d |  | 10 | 106 | NS | NO | 009-024 |  |  |  |  | 10d |  |  |  |  | 25-Dec-25 02:00 PM | 05-Jan-26 06:00 PM | 25-Mar-26 01:00 AM | 04-Apr-26 02:00 PM |  |  |  |  | CONSIDER EARLY START |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
66 | 142 | Category 1 - PNEUMATIC & HYDRAULIC FITTINGS- Ordering & Manufacturing | TASK |  | 60d | 60d | 52 | 78 | NS | NO | 006-017 |  |  |  |  | 60d | 60d |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 25-Mar-26 02:25 AM | 29-May-26 01:25 PM |  |  |  |  | CONSIDER EARLY START |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
66.1 |  | Release of PO | step |  |  |  |  | 66.2
66.1.1 |  | 1 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.1.2 |  | 1 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.1.3 |  | 1 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.1.4 |  | 1 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.1.5 |  | 1 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.1.6 |  | 1 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.1.7 |  | 1 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.1.8 |  | 1 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.1.9 |  | 1 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.1.10 |  | 1 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 22-Oct-25 03:00 AM | 01-Nov-25 04:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.2 |  | Ready for Assy | step |  |  |  | 66.1
66.2.1 |  | 1 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.2.2 |  | 1 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.2.3 |  | 1 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.2.4 |  | 1 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.2.5 |  | 1 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.2.6 |  | 1 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.2.7 |  | 1 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.2.8 |  | 1 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.2.9 |  | 1 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
66.2.10 |  | 1 | date |  | 50d |  |  |  | NS | NO | [5 empty] | 50d |  |  |  |  | 01-Nov-25 04:00 PM | 26-Dec-25 02:00 PM | 04-Apr-26 03:25 PM | 29-May-26 01:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
67 | 24 | Category 1 - PINCH ROLL ASSY. - Assembly | TASK |  | 10d |  | 35 | 97 | NS | NO | 006-022 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 25-Mar-26 02:25 AM | 04-Apr-26 03:25 PM |  |  |  |  | CONSIDER EARLY START |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
68 | 66 | Category 1 - MANUAL TINSEL SCRAPPER - Ordering & Manufacturing | TASK |  | 60d | 60d | 51 | 79 | NS | NO | 006-016 |  |  |  |  | 60d | 60d |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 30-May-26 01:25 PM |  |  |  |  | CONSIDER EARLY START |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
68.1 |  | MANUAL TINSEL SCRAPPER | Subtask |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 26-Mar-26 02:25 AM | 30-May-26 01:25 PM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
69 | 86 | Category 2 - LOGO MARKER ASSY - Ordering & Manufacturing | TASK |  | 120d | 120d | 44 | 93 | NS | NO | 004-000 |  |  |  |  | 120d | 120d |  |  |  | 17-Aug-25 08:00 AM | 26-Dec-25 02:00 PM | 28-Mar-26 02:25 AM | 06-Aug-26 03:25 PM |  |  |  |  | CONSIDER EARLY START |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
69.1 |  | LOGO MARKER ASSY | Subtask |  | 120d |  |  |  | NS | NO | [5 empty] | 120d |  |  |  |  | 17-Aug-25 08:00 AM | 26-Dec-25 02:00 PM | 28-Mar-26 02:25 AM | 06-Aug-26 03:25 PM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
70 | 133 | Category 1 - HOLE DETECTOR - Ordering & Manufacturing | TASK |  | 70d | 70d | 50 | 84 | NS | NO | 006-010 |  |  |  |  | 70d | 70d |  |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM | 28-Mar-26 02:25 AM | 12-Jun-26 05:25 PM |  |  |  |  | CONSIDER EARLY START |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
70.1 |  | WELD HOLE DETECTOR ASSY.#01 (BEFORE BRIDLE ROLL#3) | Subtask |  | 70d |  |  |  | NS | NO | [5 empty] | 70d |  |  |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM | 28-Mar-26 02:25 AM | 12-Jun-26 05:25 PM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
70.2 |  | WELD HOLE DETECTOR ASSY.#02 (AFTER CAG) | Subtask |  | 70d |  |  |  | NS | NO | [5 empty] | 70d |  |  |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM | 28-Mar-26 02:25 AM | 12-Jun-26 05:25 PM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
70.3 |  | WELD HOLE DETECTOR ASSY.#03 (AFTER EXIT ACC ASSY.) | Subtask |  | 70d |  |  |  | NS | NO | [5 empty] | 70d |  |  |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM | 28-Mar-26 02:25 AM | 12-Jun-26 05:25 PM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
71 | 148 | Category 1 - DEGREASING TANK ASSY- Ordering & Manufacturing | TASK |  | 70d | 70d | 49 | 88 | NS | NO | 006-009 |  |  |  |  | 70d | 70d |  |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 18-Jun-26 08:25 AM |  |  |  |  | CONSIDER EARLY START |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
71.1 |  | DEGREASING TANK ASSY | Subtask |  | 70d | 70d |  |  | NS | NO | [5 empty] | 70d | 70d |  |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
71.1.1 |  | Release of PO | step |  |  |  |  | 71.1.2
71.1.1.1 |  | Gasket 3 THK. X O.D 190 X I.D 115 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.2 |  | PLATE 5 THK. X 30 X 1720 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.3 |  | PLATE 6THK X 150 X 1720 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.4 |  | Gasket 3 THK. X O.D 120 X I.D 55 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.5 |  | Gasket 3 THK. X O.D 190 X I.D 115 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.6 |  | FLANGE, DN 80 (SLIP-ON) | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.7 |  | DEGREASING TANK | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.8 |  | SPRAY HEADER 1 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.9 |  | SPRAY HEADER 2 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.10 |  | SPRAY HEADER | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.11 |  | TANK COVER | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.12 |  | Header Connector | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.13 |  | Main Header | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.14 |  | HEADER SUPPORT | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.15 |  | Hexagon Nut Style 2 IS 1364-Part6 - M10-W-N | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.16 |  | Socket Head Cap Screw IS 2269 - M12 x 35 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.17 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.18 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.20 |  | Hexagon nut IS 1363-Part2 - M12-C | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.21 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.22 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.1.23 |  | Hexagon nut IS 1363-Part2 - M16-C | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2 |  | Ready for Assy | step |  |  |  | 71.1.1
71.1.2.1 |  | Gasket 3 THK. X O.D 190 X I.D 115 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.2 |  | PLATE 5 THK. X 30 X 1720 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.3 |  | PLATE 6THK X 150 X 1720 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.4 |  | Gasket 3 THK. X O.D 120 X I.D 55 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.5 |  | Gasket 3 THK. X O.D 190 X I.D 115 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.6 |  | FLANGE, DN 80 (SLIP-ON) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.7 |  | DEGREASING TANK | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.8 |  | SPRAY HEADER 1 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.9 |  | SPRAY HEADER 2 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.10 |  | SPRAY HEADER | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.11 |  | TANK COVER | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.12 |  | Header Connector | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.13 |  | Main Header | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.14 |  | HEADER SUPPORT | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.15 |  | Hexagon Nut Style 2 IS 1364-Part6 - M10-W-N | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.16 |  | Socket Head Cap Screw IS 2269 - M12 x 35 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.17 |  | Spring Lock Washer IS 6735 - 12 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.18 |  | Spring Lock Washer IS 6735 - 12 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.19 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.20 |  | Hexagon nut IS 1363-Part2 - M12-C | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.21 |  | Spring Lock Washer IS 6735 - 16 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.22 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.1.2.23 |  | Hexagon nut IS 1363-Part2 - M16-C | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2 |  | BRUSHING TANK ASSY | Subtask |  | 70d | 70d |  |  | NS | NO | [5 empty] | 70d | 70d |  |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
71.2.1 |  | Release of PO | step |  |  |  |  | 71.2.2
71.2.1.1 |  | GASKET | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.2 |  | BLIND FLANGE | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.3 |  | Clamp | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.4 |  | Flap | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.5 |  | Gasket To Suit PN6 Flange AS PER EN- 1092, DN32, 3 THK | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.6 |  | GASKET | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.7 |  | SIDE COVER | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.8 |  | BRUSHING TANK | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.9 |  | TANK COVER | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.10 |  | SPRAY HEADER SUPPORT | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.11 |  | SPRAY HEADER 1 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.12 |  | Header Connector-1 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.13 |  | Header Connector-2 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.14 |  | MAIN HEADER | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.15 |  | HEADER SUPPORT | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.16 |  | HEADER SUPPORT | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.17 |  | Hexagon Nut Style 1 IS 1364-Part3 - M10- W-N | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.18 |  | Socket Head Cap Screw IS 2269 - M12 x 35 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.19 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.20 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.21 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 50 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.22 |  | Hexagon nut IS 1363-Part2 - M16-C | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.23 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M12 x 50 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.1.24 |  | Hexagon nut IS 1363-Part2 - M12-C | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2 |  | Ready for Assy | step |  |  |  | 71.2.1
71.2.2.1 |  | GASKET | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.2 |  | BLIND FLANGE | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.3 |  | Clamp | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.4 |  | Flap | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.5 |  | Gasket To Suit PN6 Flange AS PER EN- 1092, DN32, 3 THK | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.6 |  | GASKET | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.7 |  | SIDE COVER | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.8 |  | BRUSHING TANK | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.9 |  | TANK COVER | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.10 |  | SPRAY HEADER SUPPORT | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.11 |  | SPRAY HEADER 1 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.12 |  | Header Connector-1 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.13 |  | Header Connector-2 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.14 |  | MAIN HEADER | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.15 |  | HEADER SUPPORT | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.16 |  | HEADER SUPPORT | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.17 |  | Hexagon Nut Style 1 IS 1364-Part3 - M10- W-N | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.18 |  | Socket Head Cap Screw IS 2269 - M12 x 35 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.19 |  | Spring Lock Washer IS 6735 - 12 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.20 |  | Spring Lock Washer IS 6735 - 16 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.21 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M16 x 50 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.22 |  | Hexagon nut IS 1363-Part2 - M16-C | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.23 |  | Hexagon Head Screw (Grade A) IS 1364(Part2) - M12 x 50 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.2.2.24 |  | Hexagon nut IS 1363-Part2 - M12-C | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1 |  | 0 |  | 0
71.3 |  | BRUSHING TANK ASSY #2 | Subtask |  | 70d | 70d |  |  | NS | NO | [5 empty] | 70d | 70d |  |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
71.3.1 |  | Release of PO | step |  |  |  |  | 71.3.2
71.3.1.1 |  | GASKET 3 THK X O.D190 X I.D115 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.2 |  | PLATE 12 X O.D190 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.3 |  | PLATE 5 THK X 30 X 1670 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.4 |  | FLAP 6 THK X 150 X 1670 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.5 |  | Gasket To Suit PN6 Flange AS PER EN-1092, DN32, 3 THK | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.6 |  | GASKET 80NB (1092-1 TYP -01 PN 06) | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.7 |  | SIDE COVER | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.8 |  | BRUSHING TANK | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.9 |  | TANK COVER 2 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.10 |  | SPRAY HEADER SUPPORT | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.11 |  | SPRAY HEADER 2 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.12 |  | Header Connector-1 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.13 |  | Header Connector-2 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.14 |  | SPRAY HEADER | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.15 |  | HEADER SUPPORT | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.16 |  | HEADER SUPPORT | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.17 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.18 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.19 |  | Hexagon nut IS 1363-Part2 - M10-C | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.20 |  | Hexagon nut IS 1363-Part2 - M12-C | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.21 |  | Hexagon nut IS 1363-Part2 - M16-C | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.22 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.23 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.1.24 |  | Socket Head Cap Screw IS 2269 - M12 x 35 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.3.1.25 |  | Spring Lock Washer IS 6735 - 12 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.3.1.26 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.3.2 |  | Ready for Assy | step |  |  |  | 71.3.1
71.3.2.1 |  | GASKET 3 THK X O.D190 X I.D115 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.2 |  | PLATE 12 X O.D190 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.3 |  | PLATE 5 THK X 30 X 1670 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.4 |  | FLAP 6 THK X 150 X 1670 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.5 |  | Gasket To Suit PN6 Flange AS PER EN-1092, DN32, 3 THK | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.6 |  | GASKET 80NB (1092-1 TYP -01 PN 06) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.7 |  | SIDE COVER | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.8 |  | BRUSHING TANK | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.9 |  | TANK COVER 2 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.10 |  | SPRAY HEADER SUPPORT | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.11 |  | SPRAY HEADER 2 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.12 |  | Header Connector-1 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.13 |  | Header Connector-2 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.14 |  | SPRAY HEADER | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.15 |  | HEADER SUPPORT | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.16 |  | HEADER SUPPORT | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.17 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.18 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 55 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.19 |  | Hexagon nut IS 1363-Part2 - M10-C | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.20 |  | Hexagon nut IS 1363-Part2 - M12-C | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.21 |  | Hexagon nut IS 1363-Part2 - M16-C | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.22 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.23 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  |  | 1 | 0 | 1 |  | 0 |  | 0
71.3.2.24 |  | Socket Head Cap Screw IS 2269 - M12 x 35 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.3.2.25 |  | Spring Lock Washer IS 6735 - 12 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.3.2.26 |  | Spring Lock Washer IS 6735 - 16 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4 |  | HOT WATER RINSING TANK ASSY | Subtask |  | 70d | 70d |  |  | NS | NO | [5 empty] | 70d | 70d |  |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
71.4.1 |  | Release of PO | step |  |  |  |  | 71.4.2
71.4.1.1 |  | GASKET 3 X O.D.190 X I.D.115 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.2 |  | FLAP 6 THK X 150 X 1720 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.3 |  | PLATE 5 THK. X 30 X 1720 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.4 |  | BLIND FLANGE 80NB,PN6 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.5 |  | BLIND FLANGE 65NB(EN 1092-1,TYP01, PN 06 0 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.6 |  | GASKET OD 160, ID 85 , PCD 130 , 3 THK | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.7 |  | GASKET TO SUIT PN6 FLANGE AS PER EN- 1092, DN32, 3 THK | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.8 |  | GASKET 80 NB (OD190, ID100, PCD 150) | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.9 |  | RINSING TANK | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.10 |  | ISMC 125 X 65 X 1674 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.11 |  | ISMC 125 X 65 X 4444 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.12 |  | PLATE 5 THK. X 1760 X 4400 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.13 |  | PLATE 5 THK. X 4370 X 1420 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.14 |  | PLATE 5 THK. X 1420 X 1734 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.15 |  | FLANGE 12 THK. X ID 115 X OD 190XPCD 150. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.16 |  | PLATE 20 THK. X 120 X 260 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.17 |  | PIPE 50 NB X 40 SCH X 170 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.18 |  | 50NB(EN 1092-1 TYPE 01 PN06 PLATE FLANGE) | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.19 |  | SHEET 5 THK. X 191 X 1670 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.20 |  | PLATE 5 THK. X 52 X 149 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.21 |  | PIPE 100 NB X 20 SCH X 75 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.22 |  | SHEET 5 THK. X 615 X 2543 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.23 |  | PLATE 8 THK. X 32 X 1425 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.1.24 |  | ISMC 125x65X6.3THK ( 4314 LG.) | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.25 |  | PLATE 8 THK. X 32 X 2312 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.26 |  | SHEET 5 THK. X 72 X 220 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.27 |  | SHEET 5 THK. X 72 X 1730 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.28 |  | PLATE 8 THK. X 32 X 436 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.29 |  | PLATE 8 THK. X 32 X 566 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.30 |  | SHEET 5 THK. X 612 X 1724 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.31 |  | PIPE 200 NB X 20 SCH X 205 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.32 |  | FLANGE DN 200 (EN 1092-1 TYP 01 PN 06) | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.33 |  | SHEET 5 THK. X 92 X 1730 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.34 |  | ISA 50 X 50 X 6 THK. X 868 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.35 |  | PIPE 80 NB X 40 SCH X 170 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.36 |  | PLATE 25 THK. X 100 X 200 LG | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.37 |  | PLATE 5 THK. X 1740 X 1420 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.38 |  | TAPER WASHER FOR M20 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.39 |  | PIPE 25 NB X 40 SCH X 170 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.40 |  | PIPE 65 NB X 40 SCH X 170 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.41 |  | PLATE 8 THK. X 32 X 1060 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.42 |  | SHEET 5 THK. X 92 X 1730 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.43 |  | PLATE 5 THK. X 4370 X 1420 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.44 |  | ISA 50 X 50 X 6 X 800 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.45 |  | PLATE 5 THK. X 225 X 1740 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.46 |  | PLATE 5 THK. X 1740 X 858 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.47 |  | PLATE 8 THK. X 32 X 1026 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.48 |  | PLATE 8 THK. X 917 X 32 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.49 |  | 65NB (EN 1092-1 TYPE 01 PN 06 PLATE FLANGE) | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.50 |  | 80NB( EN 1092-1 TYPE 01 PN06 PLATE FLANGE) | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.51 |  | 50NB(EN 1092-1 TYPE 01 PN06 PLATE FLANGE) | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.52 |  | 25NB (EN 1092-1 TYPE 01 PN06 PLATE FLANGE) | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.53 |  | Hexagon Head Screw (Grade B) IS 1364(Part2) - M10 x 35 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.54 |  | SPRAY HEADER 1 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.55 |  | PIPE 32 NB X SCH 40 X 1995 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.56 |  | PLATE 16 THK. X O.D. Ø190 X I.D. Ø43 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.57 |  | PLATE 5 THK. X Ø 38 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.58 |  | ROUND Ø45 X 40 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.59 |  | O RING CHORD Ø3 X I.D. 40.5 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.60 |  | WELDING NIPPLE, 066.011.017 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.61 |  | FLAT FAN DOVETAIL NOZZLE, 660.806 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.62 |  | RETAINING NUT, 065.200.17 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.63 |  | SPRAY HEADER 2 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.64 |  | PIPE 32 NB X SCH 40 X 1995 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.65 |  | PLATE 12 THK. X O.D. Ø190 X I.D. Ø43 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.66 |  | PLATE 5 THK. X Ø 38 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.67 |  | ROUND Ø45 X 40 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.68 |  | O RING CHORD Ø3 X I.D. 40.5 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.69 |  | WELDING NIPPLE, 066.011.017 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.70 |  | FLAT FAN DOVETAIL NOZZLE, 660.806 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.71 |  | RETAINING NUT, 065.200.17 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.72 |  | SPRAY HEADER SUPPORT | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.73 |  | PIPE, 32NB X SCH 40 X 165.0 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.74 |  | PLATE 12.0 THK X O.D. 190.0 X I.D.43.0 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.75 |  | ROD Ø 75.0 X 105.0 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.76 |  | FLANGE, 32NB (SLIP ON) | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.77 |  | PIPE, 5 THK. X O.D 80 X 100 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.78 |  | HEADER CONNECTOR | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.79 |  | PIPE, 32 NB X SCH 40 X 261.3 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.80 |  | FLANGE 32 (EN 1092-1 TYP 01PN 06) | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.81 |  | PIPE, 32 NB X SCH 40 X 106.9 LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.82 |  | PIPE, 80 NB X SCH 40 X 251.5LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.83 |  | ELBOW 90L LR Inch 1.25 Sch 40 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.84 |  | PIPE, 32 NB XSCH 40 X 276.4LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.85 |  | REDUCER 3 x 1.25 SCH 40 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.86 |  | FLANGE, DN 80 (EN 1092-1 TYP 01 PN 06) | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.87 |  | PIPE, 80 NB X SCH 40 X 63.0LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.88 |  | PIPE, 80 NB X SCH 40 X 63.0LG. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.89 |  | Straight Tee Inch 3 Sch40 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.90 |  | Compound Elbow-90L SR Inch 3 Sch40 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.91 |  | 1/2 " PIPE &SOCKET ASSY | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.92 |  | PIPE 1/2 " OD 21.3, SCH 80, LONG 150 MM | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.93 |  | SOCKET 1/2" BSP THREAD ,CLASS 3000# | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.94 |  | HEXAGON HEAD SCREW (GRADE C) IS 1363(PART2) - M12 X 50 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.95 |  | HEXAGON NUT IS 1363- PART2 - M12-C | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.96 |  | HEXAGON NUT IS 1363- PART2 - M16-C | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.97 |  | HEXAGON HEAD SCREW (GRADE A) IS 1364(PART2) - M12 X 55 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.98 |  | HEXAGON HEAD SCREW (GRADE A) IS 1364(PART2) - M16 X 60 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.99 |  | HEXAGON NUT STYLE 2 IS 1364-PART6 - M10- W-N | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.100 |  | PLAIN WASHER (TYPE A) IS 2016 - 14 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.101 |  | SOCKET HEAD CAP SCREW IS 2269 - M12 X 35 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.102 |  | SPRING LOCK WASHER IS 6735 - 12 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.103 |  | SPRING LOCK WASHER IS 6735 - 12 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.104 |  | SPRING LOCK WASHER IS 6735 - 16 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.105 |  | PLAIN WASHER (TYPE A) IS 2016 - 22 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.106 |  | SPRING LOCK WASHER IS 6735 - 20 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.1.107 |  | HEXAGON HEAD SCREW (GRADE C) IS 1363(PART2) - M20 X 45 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2 |  | Ready for Assy | step |  |  |  | 71.4.1
71.4.2.1 |  | GASKET 3 X O.D.190 X I.D.115 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.2 |  | FLAP 6 THK X 150 X 1720 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.3 |  | PLATE 5 THK. X 30 X 1720 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.4 |  | BLIND FLANGE 80NB,PN6 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.5 |  | BLIND FLANGE 65NB(EN 1092-1,TYP01, PN 06 0 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.6 |  | GASKET OD 160, ID 85 , PCD 130 , 3 THK | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.7 |  | GASKET TO SUIT PN6 FLANGE AS PER EN- 1092, DN32, 3 THK | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.8 |  | GASKET 80 NB (OD190, ID100, PCD 150) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.9 |  | RINSING TANK | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.10 |  | ISMC 125 X 65 X 1674 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.11 |  | ISMC 125 X 65 X 4444 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.12 |  | PLATE 5 THK. X 1760 X 4400 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.13 |  | PLATE 5 THK. X 4370 X 1420 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.14 |  | PLATE 5 THK. X 1420 X 1734 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.15 |  | FLANGE 12 THK. X ID 115 X OD 190XPCD 150. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.16 |  | PLATE 20 THK. X 120 X 260 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.17 |  | PIPE 50 NB X 40 SCH X 170 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.18 |  | 50NB(EN 1092-1 TYPE 01 PN06 PLATE FLANGE) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.19 |  | SHEET 5 THK. X 191 X 1670 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.20 |  | PLATE 5 THK. X 52 X 149 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.21 |  | PIPE 100 NB X 20 SCH X 75 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.22 |  | SHEET 5 THK. X 615 X 2543 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.23 |  | PLATE 8 THK. X 32 X 1425 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.4.2.24 |  | ISMC 125x65X6.3THK ( 4314 LG.) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.25 |  | PLATE 8 THK. X 32 X 2312 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.26 |  | SHEET 5 THK. X 72 X 220 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.27 |  | SHEET 5 THK. X 72 X 1730 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.28 |  | PLATE 8 THK. X 32 X 436 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.29 |  | PLATE 8 THK. X 32 X 566 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.30 |  | SHEET 5 THK. X 612 X 1724 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.31 |  | PIPE 200 NB X 20 SCH X 205 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.32 |  | FLANGE DN 200 (EN 1092-1 TYP 01 PN 06) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.33 |  | SHEET 5 THK. X 92 X 1730 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.34 |  | ISA 50 X 50 X 6 THK. X 868 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.35 |  | PIPE 80 NB X 40 SCH X 170 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.36 |  | PLATE 25 THK. X 100 X 200 LG | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.37 |  | PLATE 5 THK. X 1740 X 1420 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.38 |  | TAPER WASHER FOR M20 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.39 |  | PIPE 25 NB X 40 SCH X 170 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.40 |  | PIPE 65 NB X 40 SCH X 170 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.41 |  | PLATE 8 THK. X 32 X 1060 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.42 |  | SHEET 5 THK. X 92 X 1730 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.43 |  | PLATE 5 THK. X 4370 X 1420 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.44 |  | ISA 50 X 50 X 6 X 800 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.45 |  | PLATE 5 THK. X 225 X 1740 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.46 |  | PLATE 5 THK. X 1740 X 858 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.47 |  | PLATE 8 THK. X 32 X 1026 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.48 |  | PLATE 8 THK. X 917 X 32 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.49 |  | 65NB (EN 1092-1 TYPE 01 PN 06 PLATE FLANGE) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.50 |  | 80NB( EN 1092-1 TYPE 01 PN06 PLATE FLANGE) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.51 |  | 50NB(EN 1092-1 TYPE 01 PN06 PLATE FLANGE) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.52 |  | 25NB (EN 1092-1 TYPE 01 PN06 PLATE FLANGE) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.53 |  | Hexagon Head Screw (Grade B) IS 1364(Part2) - M10 x 35 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.54 |  | SPRAY HEADER 1 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.55 |  | PIPE 32 NB X SCH 40 X 1995 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.56 |  | PLATE 16 THK. X O.D. Ø190 X I.D. Ø43 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.57 |  | PLATE 5 THK. X Ø 38 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.58 |  | ROUND Ø45 X 40 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.59 |  | O RING CHORD Ø3 X I.D. 40.5 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.60 |  | WELDING NIPPLE, 066.011.017 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.61 |  | FLAT FAN DOVETAIL NOZZLE, 660.806 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.62 |  | RETAINING NUT, 065.200.17 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.63 |  | SPRAY HEADER 2 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.64 |  | PIPE 32 NB X SCH 40 X 1995 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.65 |  | PLATE 12 THK. X O.D. Ø190 X I.D. Ø43 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.66 |  | PLATE 5 THK. X Ø 38 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.67 |  | ROUND Ø45 X 40 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.68 |  | O RING CHORD Ø3 X I.D. 40.5 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.69 |  | WELDING NIPPLE, 066.011.017 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.70 |  | FLAT FAN DOVETAIL NOZZLE, 660.806 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.71 |  | RETAINING NUT, 065.200.17 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.72 |  | SPRAY HEADER SUPPORT | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.73 |  | PIPE, 32NB X SCH 40 X 165.0 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.74 |  | PLATE 12.0 THK X O.D. 190.0 X I.D.43.0 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.75 |  | ROD Ø 75.0 X 105.0 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.76 |  | FLANGE, 32NB (SLIP ON) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.77 |  | PIPE, 5 THK. X O.D 80 X 100 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.78 |  | HEADER CONNECTOR | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.79 |  | PIPE, 32 NB X SCH 40 X 261.3 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.80 |  | FLANGE 32 (EN 1092-1 TYP 01PN 06) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.81 |  | PIPE, 32 NB X SCH 40 X 106.9 LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.82 |  | PIPE, 80 NB X SCH 40 X 251.5LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.83 |  | ELBOW 90L LR Inch 1.25 Sch 40 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.84 |  | PIPE, 32 NB XSCH 40 X 276.4LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.85 |  | REDUCER 3 x 1.25 SCH 40 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.86 |  | FLANGE, DN 80 (EN 1092-1 TYP 01 PN 06) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.87 |  | PIPE, 80 NB X SCH 40 X 63.0LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.88 |  | PIPE, 80 NB X SCH 40 X 63.0LG. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.89 |  | Straight Tee Inch 3 Sch40 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.90 |  | Compound Elbow-90L SR Inch 3 Sch40 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.91 |  | 1/2 " PIPE &SOCKET ASSY | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.92 |  | PIPE 1/2 " OD 21.3, SCH 80, LONG 150 MM | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.93 |  | SOCKET 1/2" BSP THREAD ,CLASS 3000# | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.94 |  | HEXAGON HEAD SCREW (GRADE C) IS 1363(PART2) - M12 X 50 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.95 |  | HEXAGON NUT IS 1363- PART2 - M12-C | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.96 |  | HEXAGON NUT IS 1363- PART2 - M16-C | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.97 |  | HEXAGON HEAD SCREW (GRADE A) IS 1364(PART2) - M12 X 55 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.98 |  | HEXAGON HEAD SCREW (GRADE A) IS 1364(PART2) - M16 X 60 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.99 |  | HEXAGON NUT STYLE 2 IS 1364-PART6 - M10- W-N | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.100 |  | PLAIN WASHER (TYPE A) IS 2016 - 14 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.101 |  | SOCKET HEAD CAP SCREW IS 2269 - M12 X 35 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.102 |  | SPRING LOCK WASHER IS 6735 - 12 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.103 |  | SPRING LOCK WASHER IS 6735 - 12 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.104 |  | SPRING LOCK WASHER IS 6735 - 16 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.105 |  | PLAIN WASHER (TYPE A) IS 2016 - 22 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.106 |  | SPRING LOCK WASHER IS 6735 - 20 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.4.2.107 |  | HEXAGON HEAD SCREW (GRADE C) IS 1363(PART2) - M20 X 45 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.5 |  | QUENCHING TANK ASSY | Subtask |  | 70d | 70d |  |  | NS | NO | [5 empty] | 70d | 70d |  |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
71.5.1 |  | Release of PO | step |  |  |  |  | 71.5.2
71.5.1.1 |  | HEAT EXCHANGER | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.5.1.2 |  | BEARING HOUSING | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.5.1.3 |  | RETAINER-RH | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.5.1.4 |  | RETAINER- LH | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.5.1.5 |  | END PLATE | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.5.1.6 |  | END COVER | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.5.1.7 |  | END COVER- 2 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.5.2 |  | Ready for Assy | step |  |  |  | 71.5.1
71.5.2.1 |  | HEAT EXCHANGER | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.5.2.2 |  | BEARING HOUSING | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.5.2.3 |  | RETAINER-RH | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.5.2.4 |  | RETAINER- LH | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.5.2.5 |  | END PLATE | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.5.2.6 |  | END COVER | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.5.2.7 |  | END COVER- 2 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6 |  | DIP TYPE CHROMATIC TANK ASSY | Subtask |  | 70d | 70d |  |  | NS | NO | [5 empty] | 70d | 70d |  |  |  | 10-Oct-25 07:00 PM | 26-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
71.6.1 |  | Release of PO | step |  |  |  |  | 71.6.2
71.6.1.1 |  | ISMC-75X40X1859MM LONG | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.2 |  | BLIND FLANGE_DIN 2527 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.3 |  | PLATE | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.4 |  | DIP ROLL | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.5 |  | DIP TYPE CHEMICAL TANK | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.6 |  | CONNECTOR-01 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.7 |  | BASE STAND | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.8 |  | BASE STAND | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.9 |  | SS TANK | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.10 |  | CONNECTOR-02 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.11 |  | 80 NB FLANGE | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.12 |  | 65 NB MOUNTING FLANGE | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.13 |  | BASE FRAME | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.14 |  | ROTARY UNION SUPPORT ASSY. | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.15 |  | RETAINER-RH | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.16 |  | RETAINER- LH | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.17 |  | END PLATE | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.18 |  | END COVER | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.19 |  | END COVER- 2 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.20 |  | BEARING HOUSING | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.21 |  | GRACO HEAVY DUTY AGITATOR | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.22 |  | 3.7KW*6.4 LPS*28 METER HEAD (S-80*D- 65) | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.23 |  | Ball Valve,Three Piece Design,Size- DN65,Service temp-30deg ,End Connection- Flanged As Per ANSI B16.5 Class-150,Make- L&T/EQ | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.1.24 |  | Ball Valve,Three Piece Design,Size- DN80,Service Fluid-Gas,Service temp-30deg C,Material:Body-CS,Ball-SS304,Seat- PTFE,Seals-Viton,End Connection-Flanged As Per ANSI B16.5 Class-150,Make-L&T/EQ | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.25 |  | Grease Nipple,Size-1/8" BSP(M) | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.26 |  | OIL SEAL-120ID x 150OD x 10THK | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.27 |  | BEARING,SPHERICAL,22222E/C3(SPHERIC AL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.28 |  | Gasket To Suit Flange As per ANSI B16.5 class 150,Size-DN65, 3 THK | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.29 |  | Gasket To Suit PN6 Flange AS PER EN-1092, DN80, 3 THK | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.30 |  | Gasket To Suit Flange As per ANSI B16.5 class 150,Size-DN80, 3 THK | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.31 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.32 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.34 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.35 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 80 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.37 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 50 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 25 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.40 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.41 |  | Hexagon nut IS 1363-Part2 - M16-C | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.42 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.43 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.44 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.45 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.46 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.47 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.48 |  | Socket Head Cap Screw IS 2269 - M16 x 120 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.49 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.50 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.51 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.52 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.53 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.54 |  | Spring Lock Washer IS 6735 - 16 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.55 |  | Clevis Pin IS 6862 - 12 x 24-A | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.1.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 10d |  |  |  | NS | NO | [5 empty] | 10d |  |  |  |  | 10-Oct-25 07:00 PM | 22-Oct-25 03:00 AM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2 |  | Ready for Assy | step |  |  |  | 71.6.1
71.6.2.1 |  | ISMC-75X40X1859MM LONG | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.2 |  | BLIND FLANGE_DIN 2527 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.3 |  | PLATE | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.4 |  | DIP ROLL | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.5 |  | DIP TYPE CHEMICAL TANK | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.6 |  | CONNECTOR-01 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.7 |  | BASE STAND | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.8 |  | BASE STAND | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.9 |  | SS TANK | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.10 |  | CONNECTOR-02 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.11 |  | 80 NB FLANGE | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.12 |  | 65 NB MOUNTING FLANGE | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.13 |  | BASE FRAME | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.14 |  | ROTARY UNION SUPPORT ASSY. | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.15 |  | RETAINER-RH | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.16 |  | RETAINER- LH | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.17 |  | END PLATE | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.18 |  | END COVER | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.19 |  | END COVER- 2 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.20 |  | BEARING HOUSING | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.21 |  | GRACO HEAVY DUTY AGITATOR | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.22 |  | 3.7KW*6.4 LPS*28 METER HEAD (S-80*D- 65) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.23 |  | Ball Valve,Three Piece Design,Size- DN65,Service temp-30deg ,End Connection- Flanged As Per ANSI B16.5 Class-150,Make- L&T/EQ | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 1 | 0 | 1 |  | 0 |  | 0
71.6.2.24 |  | Ball Valve,Three Piece Design,Size- DN80,Service Fluid-Gas,Service temp-30deg C,Material:Body-CS,Ball-SS304,Seat- PTFE,Seals-Viton,End Connection-Flanged As Per ANSI B16.5 Class-150,Make-L&T/EQ | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.25 |  | Grease Nipple,Size-1/8" BSP(M) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.26 |  | OIL SEAL-120ID x 150OD x 10THK | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.27 |  | BEARING,SPHERICAL,22222E/C3(SPHERIC AL ROLLER BRG D 110IDx200ODx53THK. mm) | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.28 |  | Gasket To Suit Flange As per ANSI B16.5 class 150,Size-DN65, 3 THK | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.29 |  | Gasket To Suit PN6 Flange AS PER EN-1092, DN80, 3 THK | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.30 |  | Gasket To Suit Flange As per ANSI B16.5 class 150,Size-DN80, 3 THK | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.31 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 30 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.32 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 45 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.33 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 55 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.34 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 50 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.35 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 65 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.36 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M16 x 80 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.37 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M20 x 50 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.38 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M24 x 65 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.39 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 25 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.40 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M8 x 35 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.41 |  | Hexagon nut IS 1363-Part2 - M16-C | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.42 |  | Plain Washer (Type A) IS 2016 - 14 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.43 |  | Plain Washer (Type A) IS 2016 - 18 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.44 |  | Plain Washer (Type A) IS 2016 - 22 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.45 |  | Plain Washer (Type A) IS 2016 - 26 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.46 |  | Plain Washer (Type A) IS 2016 - 9 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.47 |  | Plain Washer (Type B) IS 2016 - 18 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.48 |  | Socket Head Cap Screw IS 2269 - M16 x 120 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.49 |  | Spring Lock Washer IS 3063 - 12-A | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.50 |  | Spring Lock Washer IS 3063 - 16-A | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.51 |  | Spring Lock Washer IS 3063 - 20-A | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.52 |  | Spring Lock Washer IS 3063 - 24-A | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.53 |  | Spring Lock Washer IS 3063 - 8-A | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.54 |  | Spring Lock Washer IS 6735 - 16 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.55 |  | Clevis Pin IS 6862 - 12 x 24-A | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
71.6.2.56 |  | Hexagon Head Screw (Grade C) IS 1363(Part2) - M12 x 50 | date |  | 60d |  |  |  | NS | NO | [5 empty] | 60d |  |  |  |  | 22-Oct-25 03:00 AM | 26-Dec-25 02:00 PM | 13-Apr-26 07:25 PM | 18-Jun-26 08:25 AM | [9 empty] | At the Beginning | [7 empty] | On Closure | [10 empty] | On Closure | [20 empty] | 1 | 0 | 1
72 | 103 | Category 5 - BOI - Ordering & Manufacturing | TASK |  | 10d |  | 57 | 74 | NS | NO | 011-020 |  |  |  |  | 10d |  |  |  |  | 24-Nov-25 04:00 AM | 04-Dec-25 05:00 PM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM |  |  |  |  | CONSIDER EARLY START |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
73 | 3 | Category 0 - Ordering & Manufacturing | TASK |  | 10d |  | 34 | 75 | NS | NO | 015-021 |  |  |  |  | 10d |  |  |  |  | 11-Dec-25 08:00 AM | 22-Dec-25 02:00 PM | 02-Apr-26 03:25 PM | 13-Apr-26 07:25 PM |  |  |  |  | CONSIDER EARLY START |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
74 | 98 | Category 5 - Dispatch | TASK |  | 10d |  | 7,72 | 108 | NS | NO | 011-031 |  |  |  |  | 10d |  |  |  |  | 04-Dec-25 05:00 PM | 15-Dec-25 09:00 PM | 13-Apr-26 07:25 PM | 24-Apr-26 12:25 PM |  |  |  |  | CONSIDER EARLY START |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
75 | 4 | Category 0 - Assembly | TASK |  | 10d |  | 73 | 112 | NS | NO | 015-021 |  |  |  |  | 10d |  |  |  |  | 22-Dec-25 02:00 PM | 02-Jan-26 05:00 AM | 13-Apr-26 07:25 PM | 24-Apr-26 12:25 PM |  |  |  |  | CONSIDER EARLY START |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
76 | 82 | Category 1 - CHILL ROLL UNIT - Assembly | TASK |  | 10d |  | 37 | 97 | NS | NO | 006-019 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 19-May-26 08:25 PM | 30-May-26 01:25 PM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
77 | 46 | Category 1 - SUPPORT ROLL ASSY. - Assembly | TASK |  | 10d |  | 41 | 97 | NS | NO | 006-018 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 27-May-26 01:25 PM | 07-Jun-26 11:25 AM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
78 | 143 | Category 1 - PNEUMATIC & HYDRAULIC FITTINGS- Assembly | TASK |  | 10d |  | 66 | 97 | NS | NO | 006-017 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 29-May-26 01:25 PM | 09-Jun-26 05:25 PM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
79 | 67 | Category 1 - MANUAL TINSEL SCRAPPER - Assembly | TASK |  | 10d |  | 68 | 97 | NS | NO | 006-016 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 30-May-26 01:25 PM | 10-Jun-26 05:25 PM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
80 | 52 | Category 2 - BRUSHING ROLL ASSY - Assembly | TASK |  | 10d |  | 19 | 109 | NS | NO | 012-015 |  |  |  |  | 10d |  |  |  |  | 22-Nov-25 01:00 PM | 03-Dec-25 05:00 PM | 30-May-26 08:30 PM | 11-Jun-26 04:30 AM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
81 | 58 | Category 1 - TENSIOMETER ASSY - Assembly | TASK |  | 10d |  | 15 | 97 | NS | NO | 006-014 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 01-Jun-26 04:25 AM | 11-Jun-26 05:25 PM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
82 | 8 | Category 1 - COIL CAR ASSY @ UNCOILER - Assembly | TASK |  | 10d |  | 4 | 97 | NS | NO | 006-013 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 02-Jun-26 04:25 AM | 12-Jun-26 05:25 PM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
83 | 12 | Category 1 - COIL CAR ASSY @ RECOILER - Assembly | TASK |  | 10d |  | 5 | 97 | NS | NO | 006-011 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 04-Jun-26 04:25 AM | 15-Jun-26 08:25 AM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
84 | 134 | Category 1 - HOLE DETECTOR - Assembly | TASK |  | 10d |  | 70 | 97 | NS | NO | 006-010 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 12-Jun-26 05:25 PM | 24-Jun-26 01:25 AM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
85 | 105 | Category 3/4 - Dispatch | TASK |  | 10d |  | 9 | 111 | NS | NO | 014-012 |  |  |  |  | 10d |  |  |  |  | 22-Nov-25 02:00 AM | 03-Dec-25 06:00 AM | 12-Jun-26 05:25 PM | 24-Jun-26 01:25 AM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
86 | 140 | Category 1 - TANK - Assembly | TASK |  | 10d |  | 40 | 97 | NS | NO | 006-007 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 18-Jun-26 08:25 AM | 29-Jun-26 02:25 PM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
87 | 146 | Category 1 - ECL Process Tank Assembly- Assembly | TASK |  | 10d |  | 42 | 97 | NS | NO | 006-008 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 18-Jun-26 08:25 AM | 29-Jun-26 02:25 PM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
88 | 149 | Category 1 - DEGREASING TANK ASSY- Assembly | TASK |  | 10d |  | 71 | 97 | NS | NO | 006-009 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 18-Jun-26 08:25 AM | 29-Jun-26 02:25 PM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
89 | 76 | Category 2 - SQUEEZE ROLL ASSY. - Assembly | TASK |  | 10d |  | 14 | 110 | NS | NO | 013-006 |  |  |  |  | 10d |  |  |  |  | 21-Nov-25 01:00 PM | 02-Dec-25 05:00 PM | 02-Jul-26 02:25 PM | 13-Jul-26 06:25 PM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
90 | 93 | Category 2 - COATER STRUCTURE - Assembly | TASK |  | 10d |  | 56 | 107 | NS | NO | 010-005 |  |  |  |  | 10d |  |  |  |  | 04-Dec-25 05:00 PM | 15-Dec-25 09:00 PM | 10-Jul-26 05:25 AM | 21-Jul-26 09:25 AM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
91 | 64 | Category 2 - RECOILER ASSY - Assembly | TASK |  | 10d |  | 13 | 99 | NS | NO | 002-004 |  |  |  |  | 10d |  |  |  |  | 27-Dec-25 02:00 PM | 07-Jan-26 06:00 PM | 02-Aug-26 09:25 AM | 13-Aug-26 06:25 AM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
92 | 16 | Category 1 - TABLE - Assembly | TASK |  | 10d |  | 18 | 97 | NS | NO | 006-003 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 03-Aug-26 03:25 PM | 14-Aug-26 06:25 AM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
93 | 87 | Category 2 - LOGO MARKER ASSY - Assembly | TASK |  | 10d |  | 69 | 101 | NS | NO | 004-000 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 06-Aug-26 03:25 PM | 17-Aug-26 07:25 PM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
94 | 90 | Category 2 - DRYER - Assembly | TASK |  | 10d |  | 38 | 102 | NS | NO | 005-001 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 06-Aug-26 03:25 PM | 17-Aug-26 07:25 PM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
95 | 137 | Category 1 - SENSOR - Assembly | TASK |  | 10d |  | 39 | 97 | NS | NO | 006-002 |  |  |  |  | 10d |  |  |  |  | 26-Dec-25 02:00 PM | 06-Jan-26 06:00 PM | 06-Aug-26 03:25 PM | 17-Aug-26 07:25 PM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
96 | 97 | Category 2 - Dispatch | TASK |  | 10d |  | 64,109,99,104,105,106,110,100,101,102,107 | 113 | NS | NO | 001-023 |  |  |  |  | 10d |  |  |  |  | 07-Jan-26 06:00 PM | 19-Jan-26 02:00 AM | 17-Aug-26 07:25 PM | 28-Aug-26 12:25 PM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
97 | 5 | Category 1 - Dispatch | TASK |  | 10d |  | 82,92,83,61,67,54,77,81,79,76,62,84,95,86,78,87,88 | 103 | NS | NO | 006-002 |  |  |  |  | 10d |  |  |  |  | 06-Jan-26 06:00 PM | 17-Jan-26 09:00 AM | 17-Aug-26 07:25 PM | 28-Aug-26 12:25 PM |  |  |  |  | POSSIBLE CANDIDATE FOR CRASHING |  |  |  |  | At the Beginning |  |  |  | Distributed |  |  |  | Distributed | [10 empty] | Distributed
98 | 1 | Project End | PE | [5 empty] | NS | NO | [10 empty] | 19-Feb-26 03:36 PM | 19-Feb-26 03:36 PM | 29-Sep-26 01:25 PM | 29-Sep-26 01:25 PM
99 | 123 | Buffer(Category 2 - RECOILER ASSY - Assembly=>Category 2 - Dispatch) | CCFB | [6 empty] | NO | 002-004 |  |  |  |  | 4d |  |  |  |  | 07-Jan-26 06:00 PM | 07-Jan-26 06:00 PM |  | 17-Aug-26 07:25 PM
100 | 128 | Buffer(Category 2 - COATER - Assembly=>Category 2 - Dispatch) | CCFB |  | 1d |  |  |  |  | NO | 003-025 |  |  |  |  | 5d9h |  |  |  |  | 06-Jan-26 06:00 PM | 07-Jan-26 06:00 PM |  | 17-Aug-26 07:25 PM
101 | 129 | Buffer(Category 2 - LOGO MARKER ASSY - Assembly=>Category 2 - Dispatch) | CCFB |  | 1d |  |  |  |  | NO | 004-000 | [9 empty] | 06-Jan-26 06:00 PM | 07-Jan-26 06:00 PM |  | 17-Aug-26 07:25 PM
102 | 130 | Buffer(Category 2 - DRYER - Assembly=>Category 2 - Dispatch) | CCFB |  | 1d |  |  |  |  | NO | 005-001 | [9 empty] | 06-Jan-26 06:00 PM | 07-Jan-26 06:00 PM |  | 17-Aug-26 07:25 PM
103 | 120 | Buffer(Category 1 - Dispatch=>Project Buffer) | CCFB |  | 1d |  |  |  |  | NO | 006-002 | [9 empty] | 17-Jan-26 09:00 AM | 19-Jan-26 02:00 AM |  | 28-Aug-26 12:25 PM
104 | 124 | Buffer(Category 2 - BRIDLE ROLL ASSY. - Assembly=>Category 2 - Dispatch) | CCFB |  | 2d |  |  |  |  | NO | 007-029 |  |  |  |  | 5d |  |  |  |  | 05-Jan-26 06:00 PM | 07-Jan-26 06:00 PM |  | 17-Aug-26 07:25 PM
105 | 125 | Buffer(Category 2 - ENTRY ACCUMULATOR ASSY. - Assembly=>Category 2 - Dispatch) | CCFB |  | 2d |  |  |  |  | NO | 008-026 |  |  |  |  | 5d9h |  |  |  |  | 05-Jan-26 06:00 PM | 07-Jan-26 06:00 PM |  | 17-Aug-26 07:25 PM
106 | 126 | Buffer(Category 2 - EXIT ACCUMULATOR ASSY. - Assembly=>Category 2 - Dispatch) | CCFB |  | 2d |  |  |  |  | NO | 009-024 |  |  |  |  | 6d |  |  |  |  | 05-Jan-26 06:00 PM | 07-Jan-26 06:00 PM |  | 17-Aug-26 07:25 PM
107 | 131 | Buffer(Category 2 - COATER STRUCTURE - Assembly=>Category 2 - Dispatch) | CCFB |  | 21d |  |  |  |  | NO | 010-005 |  |  |  |  | 25d |  |  |  |  | 16-Dec-25 01:00 AM | 07-Jan-26 06:00 PM |  | 17-Aug-26 07:25 PM
108 | 106 | Buffer(Category 5 - Dispatch=>Project Buffer) | CCFB |  | 31d |  |  |  |  | NO | 011-031 |  |  |  |  | 15d |  |  |  |  | 16-Dec-25 01:00 AM | 19-Jan-26 02:00 AM |  | 28-Aug-26 12:25 PM
109 | 9 | Buffer(Category 2 - BRUSHING ROLL ASSY - Assembly=>Category 2 - Dispatch) | CCFB |  | 32d |  |  |  |  | NO | 012-015 |  |  |  |  | 36d13h |  |  |  |  | 03-Dec-25 05:00 PM | 07-Jan-26 06:00 PM |  | 17-Aug-26 07:25 PM
110 | 127 | Buffer(Category 2 - SQUEEZE ROLL ASSY. - Assembly=>Category 2 - Dispatch) | CCFB |  | 33d |  |  |  |  | NO | 013-006 |  |  |  |  | 32d |  |  |  |  | 02-Dec-25 05:00 PM | 07-Jan-26 06:00 PM |  | 17-Aug-26 07:25 PM
111 | 104 | Buffer(Category 3/4 - Dispatch=>Project Buffer) | CCFB |  | 42d9h |  |  |  |  | NO | 014-012 |  |  |  |  | 42d9h |  |  |  |  | 03-Dec-25 06:00 AM | 19-Jan-26 02:00 AM |  | 28-Aug-26 12:25 PM
112 | 107 | Buffer(Category 0 - Assembly=>Project Buffer) | CCFB |  | 15d |  |  |  |  | NO | 015-021 |  |  |  |  | 15d |  |  |  |  | 02-Jan-26 05:00 AM | 19-Jan-26 02:00 AM |  | 28-Aug-26 12:25 PM
113 | 83 | Project Buffer | CCCB |  | 29d4h |  |  |  |  | NO | 001-023 |  |  |  |  | 29d |  |  |  |  | 19-Jan-26 02:00 AM | 19-Feb-26 03:36 PM |  | 29-Sep-26 01:25 PM